## Field record
Check ID | Check, observation and method | Specific record field | Project criterion / source document and revision | Actual record / issue / evidence
CD-01 | Controlled pour and supply basis What to observe: Pour/lot boundary, approved order and mix revision, location map, project timing rule and named receipt role. How to check: Review current controlled documents at the workface and reconcile any revision or allocation conflict before recording receipt. Acceptance basis: The current controlled documents identify the pour, approved supply basis and assigned receiving role. Any essential missing timing rule or revision conflict is identified for project direction before the affected receipt decision. Reference to confirm: Controlled pour/element register, approved concrete order and mix submission revisions, project delivery procedure and ITP responsibility/decision register. | Element / lot / pour-map ref
Approved mix / order revision
Timing clause / source
Assigned receiver / role
Result / status (Pass / Fail / N/A / Pending)
Inspector name / role / date
Photo / certificate / report reference
Issue / disposition / recheck evidence and date
CD-02 | Truck docket and batch identity What to observe: Supplier, truck, docket, batch/mix designation and the actual ticket particulars required by the project. How to check: Compare each docket to the approved order; transcribe identifiers and retain the complete ticket reference. Acceptance basis: The docket identifiers and supplied mix can be reconciled with the current approved order and intended pour, against the project-required ticket details. Missing or mismatched identity remains open for assigned disposition. Reference to confirm: Approved concrete order/mix submission, project docket-detail requirements and the actual supplier delivery docket; cite the relevant identifier and revision. | Supplier / truck / docket
Batch ID / mix label
Ticket quantity / unit
Docket file / photo ref
Result / status (Pass / Fail / N/A / Pending)
Inspector name / role / date
Photo / certificate / report reference
Issue / disposition / recheck evidence and date
CD-03 | Mix change and site-addition trail What to observe: Any actual site water/admixture or other change, stated quantity, time, requesting person, written authorization and supplier ticket notation. How to check: Reconcile the order, docket and written instruction; never infer an addition or permission from appearance or verbal custom. Acceptance basis: Any recorded change has the permission, quantity, time, responsible authority and supplier trail required by the project. An undocumented addition is not treated as permitted; where no addition occurred, record that observation or N/A with its basis. Reference to confirm: Project-approved site-adjustment rule, written load-specific instruction and supplier docket/change record; record the authorising role and locator. | Change / actual amount and unit
Time / docket annotation
Instruction and authority ref
Supplier confirmation ref
Result / status (Pass / Fail / N/A / Pending)
Inspector name / role / date
Photo / certificate / report reference
Issue / disposition / recheck evidence and date
CD-04 | Batch, arrival and discharge times What to observe: Actual dispatch/batch, arrival and discharge times, sampling time if relevant, and any event used in a project-defined time check. How to check: Capture times from docket and contemporaneous site logs; calculate elapsed time only where the project defines origin and method. Acceptance basis: Recorded times have an identifiable source and, where a project time check applies, the elapsed assessment uses its stated origin and criterion. An unclear time basis or departure is referred; no universal time limit is supplied. Reference to confirm: Project specification or approved delivery procedure defining the timing origin, allowed condition and assessment method, plus the source docket and site log. | Batch / dispatch time + source
Arrival and discharge start/end
Project timing clause / origin
Elapsed time if project requires
Result / status (Pass / Fail / N/A / Pending)
Inspector name / role / date
Photo / certificate / report reference
Issue / disposition / recheck evidence and date
CD-05 | Quantity and placement allocation What to observe: Ticketed and actual used/returned quantity, units, element/grid and any split-load allocation. How to check: Cross-link docket to the placement diary and pour map; reconcile leftovers to actual return or disposition evidence. Acceptance basis: The docket quantity and used/returned allocation are traceable to the actual pour locations under the project reconciliation procedure. Any unresolved allocation or quantity discrepancy remains open; no generic tolerance is assumed. Reference to confirm: Project pour/allocation map, supplier docket, quantity reconciliation procedure and actual placement/return record references. | Ticket / used quantity + unit
Element / grid / placement ref
Returned / unused quantity + unit
Placement / return record ref
Result / status (Pass / Fail / N/A / Pending)
Inspector name / role / date
Photo / certificate / report reference
Issue / disposition / recheck evidence and date
CD-06 | Receipt observation and separate test links What to observe: Observable load condition or reported concern; any project-required fresh test/sample ID and actual test value/unit. How to check: Record facts without inferring properties; link to the separate tester/method/equipment/sample record required by the project. Acceptance basis: Observed concerns and required test/sample references are linked to the correct delivery and location. Any measured result is traceable to its original record and evaluated only against the governing project receipt criterion. Reference to confirm: Project receipt inspection/test requirements and linked fresh-test or sample record, including the tester/method and original evidence reference. | Observed condition / time
Sample or test ID
Actual value / unit if measured
Tester / method / evidence ref
Result / status (Pass / Fail / N/A / Pending)
Inspector name / role / date
Photo / certificate / report reference
Issue / disposition / recheck evidence and date
CD-07 | Receipt decision, exceptions and handover What to observe: Recorded status, authorized receiving decision, open docket/time/mix/quantity/test issues, corrective instruction and closeout evidence. How to check: Separate recorder observation from decision; link decision maker role, conditions, NCR and recheck/closeout records. Acceptance basis: The assigned role records the actual load decision, conditions and supporting instruction/evidence; unresolved issues carry into the ITP/NCR. Record completion is separate from any contractual release or permission to place. Reference to confirm: Project concrete ITP receipt decision/notice arrangements, assigned authority, load-specific instruction, NCR and evidence of closure or handover. | Load / affected location
Decision / role / instruction ref
NCR / action and recheck ref
Handover recipient / date
Result / status (Pass / Fail / N/A / Pending)
Inspector name / role / date
Photo / certificate / report reference
Issue / disposition / recheck evidence and date

## Project setup
Cavoren ITP | Concrete Delivery and Batch Record
Field | Project entry | Reason / instructions | Source / locator
Project name / contract
Client / principal
Contractor / trade
Jurisdiction / building class
Room / element / zone / lot
Inspection date / time
Checklist issue / revision
Project / contractor
Pour / lot / element and grid
Approved mix / order ref
Supplier / batch plant
Truck / docket no.
Arrival and discharge times
Recorder / receiving role
Open instruction / NCR ref
Required project input |  | Why it is needed
Approved mix/order and revisions |  | Compare actual docket identity and any changed supply with the controlled project basis.
Pour map and planned truck allocation |  | Link each load and actual quantity to the location receiving it.
Project timing and site-addition rules |  | Supply the exact time origin, limit, permission and responsible role where applicable.
Receipt tests and assigned roles |  | Identify only tests and decisions required by this project.
Discrepancy, unused/returned concrete and NCR process |  | Keep traceability and closeout for any affected load.
Included scope | Receipt and allocation of ordinary ready-mixed concrete to cast-in-place work, from each batch docket through reconciliation and handover.
Excluded scope | Mix design approval; detailed fresh concrete testing; placement quality; specimen/laboratory reports; concrete certification; precast, piles, shotcrete and special infrastructure requirements.
Use notice | Blank field record. Apply the approved project criteria and record actual facts. Do not authorize a site addition or accept/reject a load by assumption.
How to use
1 | Confirm the current approved order/mix, element map, project timing basis and assigned receiving role.
2 | Enter one record per actual truck/batch; transcribe docket, times and quantity from the source.
3 | Document any site addition or altered supply only from an actual written direction and supplier/docket trail.
4 | Link the load to the real pour location and separately required sample/test record.
5 | Keep a discrepancy open until the assigned project role records a decision and evidence; reconcile leftover/returned quantity.
6 | Use the delivery log for repeat entries; continue on another blank copy when needed and retain the linked original evidence.
Source title | Role and limits | URL | Locator
Cavoren cast-in-place concrete baseline | Scope context only; not independent technical authority or project acceptance criteria. | https://itp.cavoren.net/templates/concrete/ | Original proposed receipt topics CON-01, CON-09 and interfaces CON-10–11.
Queensland Department of Transport and Main Roads, MRTS70 Concrete (July 2022) | Topic guidance only. MRTS70 is for Queensland road/bridge infrastructure contracts (or other specified elements). Its values, timing limits, test frequencies, qualifications, H/W points, project roles and release rules are not generalized into these records. | https://www.tmr.qld.gov.au/-/media/busind/techstdpubs/Specifications-and-drawings/Specifications/2-Bridges-and-Structures/MRTS70.pdf | July 2022, Clause 1/Table 1 (infrastructure scope); 10.5 (transport and delivery docket); 11 (plastic concrete checks/departure topics). Clause references are printed specification locators, not PDF viewer page numbers.
Hutchies 040 Concrete Place Report (public Word report template) | Contractor-specific example of report layout and handover, not universal criteria. No Hutchies text is reproduced. | https://toolbox.hutchies.com.au/uploads/040-Concrete-Place-Report.docx | Public 040 Concrete Place Report: header and closeout fields, rows 6–13 on discharge, placement, protection, curing and final records review. Contractor example only; no technical acceptance conditions are adopted.

## Issues and handover
Concrete Delivery and Batch Record ¦ Issues and handover
Project | Location / area | Issue date | Open item reference | Person / role
Item ID / date | Affected location and issue | Immediate action / disposition | Recheck evidence / date | Responsible person / role
Concrete delivery receipt handover | Record handover status | Select one status only
[ ] Record completed; evidence filed
[ ] Action or recheck remains open
[ ] Project / technical disposition required
Decision boundary | Applies to docket traceability and delivery handover only. It does not approve a mix, prove test conformity, certify concrete, release a project point or authorize placement. Carry open loads into the concrete ITP/NCR.
Handover role | Delivery recorder name / role / date
Handover role | Assigned receiving decision role / date
Handover role | Supplier contact / role, if clarification needed
Handover role | Open NCR / instruction reference
Signature note | Signatures record the named person’s stated role and entry only. They do not by themselves approve design, certify compliance, release a contractual control point or authorize the next activity.

## Event log
Delivery log
Use one row for each actual truck/batch. Link split allocations and extra details by reference to a pour map or continuation sheet. Establish the project receipt criteria in the check pages first; record only actual events and the assigned receipt decision.
Project / contract |  |  | Element / pour / lot |  |  | Date / shift
Docket / truck ID | Batch / mix designation | Element / pour / allocation ref | Batch time / source | Arrival / discharge start-end | Quantity / unit / used-returned | Sample / test record ref | Receipt decision / role / NCR ref