## Start here
Concrete Footings Construction ITP Template
Reusable editable baseline for cast-in-place building pad, strip and ground-beam footings within a defined package. Covers approved foundation/design basis, excavation handover, set-out, reinforcement/starters, formwork/embeds, pre-pour authorization, concrete delivery/testing, placement, curing, stripping/loading controls and closeout. Excludes piles, bored piers, underpinning, retaining structures, precast footings and ground improvement unless separately specified. No geotechnical acceptance, design values, excavation safety method, tolerances, test rates or release authority is supplied.
Status | Free editable proposed baseline. It is not project-approved and is not evidence that work was inspected.
Project fields | Complete the project, jurisdiction, parties, document number/revision and scope in the controlled project copy.
Technical criteria | Replace every [Enter ...] prompt with the exact contract, approved drawing, specification or procedure reference and project condition. Confirm adopted editions and resolve conflicts.
Frequency and lot | These rows show proposed activity triggers only. Set the actual lot, sampling basis and frequency from project requirements.
Roles and control points | Confirm performing/reviewing roles, contractual or regulatory H/W rights, notice, evidence and release authority. No external control point is assigned.
Conditional work | Remove out-of-scope work or mark it not applicable with a reason. Include only processes required for this project.
Records | Use the matching blank Records sheet. Enter actual inspection date, observation, result and signature only when work is performed.
Evidence | Retain original certificates, test reports, survey records, photographs and written dispositions; index them rather than replacing them with a tick.
Scope boundary | Reusable editable baseline for cast-in-place building pad, strip and ground-beam footings within a defined package. Covers approved foundation/design basis, excavation handover, set-out, reinforcement/starters, formwork/embeds, pre-pour authorization, concrete delivery/testing, placement, curing, stripping/loading controls and closeout. Excludes piles, bored piers, underpinning, retaining structures, precast footings and ground improvement unless separately specified. No geotechnical acceptance, design values, excavation safety method, tolerances, test rates or release authority is supplied.
Project source prompts | Element / pour / lot: Identify the physical element, drawing grid/level, pour sequence and lot boundary. Approved drawings and revisions: List current structural drawings, details, schedules and approved design changes relevant to this element. Project specification and adopted standards: Enter exact contract clauses, adopted standards/editions and project criteria; do not infer adoption from a published edition. Approved concrete mix and supplier submission: Identify approved mix, supplier, delivery requirements and any project-authorised adjustments. Project test plan and acceptance: Identify specified test methods, sample/lot coverage, acceptance and designated tester/reviewer from controlled project documents. Performing, reviewing and release roles: Identify actual contractor, verifier/designer, notice duties, contractual Hold/Witness points and release authority. Project evidence and closeout requirements: Identify required pour records, test reports, survey, defect disposition and handover register. Foundation design and ground basis: Identify approved foundation design, geotechnical/ground classification, bearing criteria and excavation release responsibility. Footing schedule and interfaces: Identify footing type, grid/levels, starters, columns/walls supported, adjacent services and pour segmentation. Excavation and formation release: Identify required excavation inspection, geotechnical/design review, authority notification and evidence before concrete. Stripping / loading release requirements: Identify design- or project-controlled criteria, authorization and dependent-work release; no value is presumed.

## ITP
Concrete Footings Construction ITP Template ¦ Proposed Inspection and Test Plan
Document number: [Enter] Revision: [Enter] Date: [Enter] Project: [Enter] Jurisdiction: [Enter] Contractor: [Enter] Reusable editable baseline for cast-in-place building pad, strip and ground-beam footings within a defined package. Covers approved foundation/design basis, excavation handover, set-out, reinforcement/starters, formwork/embeds, pre-pour authorization, concrete delivery/testing, placement, curing, stripping/loading controls and closeout. Excludes piles, bored piers, underpinning, retaining structures, precast footings and ground improvement unless separately specified. No geotechnical acceptance, design values, excavation safety method, tolerances, test rates or release authority is supplied.
ITP field | Proposed plan entry
FND-01 | FND-01 ¦ Package design and footing schedule
Inspection / test | Confirm each footing type, location, support condition, drawings, mix and test requirements before excavation or procurement.
Method | Reconcile footing schedule, structural details, ground report, service conflicts, concrete mix and project-specific inspections; escalate conflicting or incomplete design inputs.
Project acceptance condition | For [Enter Element / pour / lot], current [Enter Approved drawings and revisions], [Enter Foundation design and ground basis] and [Enter Footing schedule and interfaces] control the footing geometry and ground basis; approved mix [Enter Approved concrete mix and supplier submission] and tests [Enter Project test plan and acceptance] are identified.
Reference / locator | Enter actual controlled project document, revision and locator; see Source Register for topic guidance.
Trigger / frequency | Proposed: Before excavation and whenever controlling design documents change.
Performing / reviewing role | Proposed: [Enter Person/role performing this check] performs and records; [Enter Person/role reviewing this check] reviews only where assigned by project documents.
Control point / external party | Proposed record point only. Confirm any contractual or regulatory Hold/Witness point, notice period, release authority and evidence from the project documents; none is assigned by this baseline. [Enter Notice and release authority]
Notice / release evidence | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external release authority is assigned.
Record | Footing schedule and design coordination register
Applicability / remarks
FND-02 | FND-02 ¦ Excavation and founding surface handover
Inspection / test | Record actual excavation limits and the assigned inspection/release of the founding condition before blinding, reinforcement or concrete conceals it.
Method | Identify each footing excavation; compare location and depth to approved details; arrange project-required geotechnical/designer inspection; record water, disturbed ground, unsuitable material and instructions.
Project acceptance condition | Excavation is accepted only against [Enter Excavation and formation release] and the assigned geotechnical/design authority; visual observation alone does not establish bearing capacity or soil classification.
Reference / locator | Enter actual controlled project document, revision and locator; see Source Register for topic guidance.
Trigger / frequency | Proposed: Each footing or agreed inspection lot before concealment, subject to project notice and coverage requirements.
Performing / reviewing role | Proposed: [Enter Person/role performing this check] performs and records; [Enter Person/role reviewing this check] reviews only where assigned by project documents.
Control point / external party | Proposed record point only. Confirm any contractual or regulatory Hold/Witness point, notice period, release authority and evidence from the project documents; none is assigned by this baseline. [Enter Notice and release authority]
Notice / release evidence | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external release authority is assigned.
Record | Footing excavation and founding release record
Applicability / remarks
FND-03 | FND-03 ¦ Set-out, footing geometry and adjacent services
Inspection / test | Check footing location, orientation, level, steps, offsets and clearance from adjacent works against current approved drawings.
Method | Record actual measurements and method; coordinate service crossings, easements, property interfaces and adjacent footing sequence with relevant package records.
Project acceptance condition | Measured location and geometry match [Enter Footing schedule and interfaces] and [Enter Approved drawings and revisions]; deviations and service conflicts have written design disposition before pour.
Reference / locator | Enter actual controlled project document, revision and locator; see Source Register for topic guidance.
Trigger / frequency | Proposed: Each defined footing lot before reinforcement limits access.
Performing / reviewing role | Proposed: [Enter Person/role performing this check] performs and records; [Enter Person/role reviewing this check] reviews only where assigned by project documents.
Control point / external party | Proposed record point only. Confirm any contractual or regulatory Hold/Witness point, notice period, release authority and evidence from the project documents; none is assigned by this baseline. [Enter Notice and release authority]
Notice / release evidence | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external release authority is assigned.
Record | Footing set-out and interface check
Applicability / remarks
FND-04 | FND-04 ¦ Reinforcement, starters and cast-in items
Inspection / test | Check scheduled bars, anchorage/lap locations, starter bars, column/wall interfaces, cover supports and cast-in items against approved details.
Method | Verify identifiers and placement from approved bar schedule; record locations and specified measurement method; reconcile starter projections, waterstops or embeds where designed.
Project acceptance condition | Reinforcement, starters and embeds match [Enter Approved drawings and revisions] and [Enter Project specification and adopted standards]; all dimensional/cover criteria are taken from those approved documents, not generic values.
Reference / locator | Enter actual controlled project document, revision and locator; see Source Register for topic guidance.
Trigger / frequency | Proposed: Before concrete placement for each designated footing area, with coverage set by project ITP.
Performing / reviewing role | Proposed: [Enter Person/role performing this check] performs and records; [Enter Person/role reviewing this check] reviews only where assigned by project documents.
Control point / external party | Proposed record point only. Confirm any contractual or regulatory Hold/Witness point, notice period, release authority and evidence from the project documents; none is assigned by this baseline. [Enter Notice and release authority]
Notice / release evidence | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external release authority is assigned.
Record | Footing reinforcement and embed pre-pour record
Applicability / remarks
FND-05 | FND-05 ¦ Formwork and pre-pour readiness
Inspection / test | Inspect any footing forms, construction joints, interfaces, access and final cleanliness; document the project-assigned pre-pour review and release.
Method | Walk each defined pour area; compare geometry, stability evidence, base condition, reinforcement/embeds and approved method with the pour checklist and actual ITP notice.
Project acceptance condition | Pre-pour status is recorded against [Enter Approved drawings and revisions], [Enter Project specification and adopted standards] and [Enter Notice and release authority]; only the identified authority can record formal release or contractual acceptance.
Reference / locator | Enter actual controlled project document, revision and locator; see Source Register for topic guidance.
Trigger / frequency | Proposed: Before each defined pour and before concrete placement begins.
Performing / reviewing role | Proposed: [Enter Person/role performing this check] performs and records; [Enter Person/role reviewing this check] reviews only where assigned by project documents.
Control point / external party | Proposed record point only. Confirm any contractual or regulatory Hold/Witness point, notice period, release authority and evidence from the project documents; none is assigned by this baseline. [Enter Notice and release authority]
Notice / release evidence | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external release authority is assigned.
Record | Footing pre-pour and release register
Applicability / remarks
FND-06 | FND-06 ¦ Concrete delivery and specified fresh tests
Inspection / test | Verify concrete docket/mix traceability and capture only project-required tests and samples.
Method | Compare load identity and delivery records to approved mix; record actual addition/rejection; tag fresh tests and specimens to footing, batch, location and named tester.
Project acceptance condition | Delivery and results are judged against [Enter Approved concrete mix and supplier submission] and [Enter Project test plan and acceptance]; strength, workability, temperature, sampling frequency and rejection rules are not filled in by this baseline.
Reference / locator | Enter actual controlled project document, revision and locator; see Source Register for topic guidance.
Trigger / frequency | Proposed: For each load/test/sample required by the project test plan.
Performing / reviewing role | Proposed: [Enter Person/role performing this check] performs and records; [Enter Person/role reviewing this check] reviews only where assigned by project documents.
Control point / external party | Proposed record point only. Confirm any contractual or regulatory Hold/Witness point, notice period, release authority and evidence from the project documents; none is assigned by this baseline. [Enter Notice and release authority]
Notice / release evidence | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external release authority is assigned.
Record | Footing delivery and fresh test register
Applicability / remarks
FND-07 | FND-07 ¦ Placement and consolidation around bars / starters
Inspection / test | Observe discharge, lift/sequence, consolidation around congested reinforcement, starter bars, forms and embedded items.
Method | Record observed zone and sequence; compare placement equipment and procedure with approved method; note interruptions, movement, leakage, segregation or corrective action.
Project acceptance condition | Placement follows approved [Enter Project specification and adopted standards] and method; movement, void risk, unplanned joints or other departures are documented and dispositioned before dependent construction.
Reference / locator | Enter actual controlled project document, revision and locator; see Source Register for topic guidance.
Trigger / frequency | Proposed: During each pour at the project-defined observation coverage.
Performing / reviewing role | Proposed: [Enter Person/role performing this check] performs and records; [Enter Person/role reviewing this check] reviews only where assigned by project documents.
Control point / external party | Proposed record point only. Confirm any contractual or regulatory Hold/Witness point, notice period, release authority and evidence from the project documents; none is assigned by this baseline. [Enter Notice and release authority]
Notice / release evidence | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external release authority is assigned.
Record | Footing placement log
Applicability / remarks
FND-08 | FND-08 ¦ Curing, stripping and loading control
Inspection / test | Record the specified curing/protection and any project-controlled form removal, backfill, column start or loading release.
Method | Compare actual timing, method and conditions to approved concrete/design instructions; record any engineer/project authorization for stripping or loading.
Project acceptance condition | Curing and subsequent work comply with [Enter Project specification and adopted standards] and documented [Enter Stripping / loading release requirements]; no stripping time, strength threshold, backfill permission or load allowance is presumed.
Reference / locator | Enter actual controlled project document, revision and locator; see Source Register for topic guidance.
Trigger / frequency | Proposed: Monitor from placement through each specified release milestone.
Performing / reviewing role | Proposed: [Enter Person/role performing this check] performs and records; [Enter Person/role reviewing this check] reviews only where assigned by project documents.
Control point / external party | Proposed record point only. Confirm any contractual or regulatory Hold/Witness point, notice period, release authority and evidence from the project documents; none is assigned by this baseline. [Enter Notice and release authority]
Notice / release evidence | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external release authority is assigned.
Record | Footing curing and early-work release record
Applicability / remarks
FND-09 | FND-09 ¦ Strength reports, defects and final handover
Inspection / test | Link specified concrete test results, survey, visible defects/repairs and footing records to the supported structure.
Method | Compare laboratory reports and as-built records against project criteria; refer adverse results, honeycombing or geometry issues for responsible design disposition and verify closure.
Project acceptance condition | Results and geometry satisfy [Enter Project test plan and acceptance] and [Enter Project specification and adopted standards] or are formally dispositioned; files and outstanding items reconcile with [Enter Project evidence and closeout requirements].
Reference / locator | Enter actual controlled project document, revision and locator; see Source Register for topic guidance.
Trigger / frequency | Proposed: On receipt of required reports, before dependent loading where specified, and at package closeout.
Performing / reviewing role | Proposed: [Enter Person/role performing this check] performs and records; [Enter Person/role reviewing this check] reviews only where assigned by project documents.
Control point / external party | Proposed record point only. Confirm any contractual or regulatory Hold/Witness point, notice period, release authority and evidence from the project documents; none is assigned by this baseline. [Enter Notice and release authority]
Notice / release evidence | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external release authority is assigned.
Record | Footing results and closeout register
Applicability / remarks

## Records
Blank Inspection Record Prompts
Complete during actual work. Actual result, date, names, approvals and signatures are intentionally blank. Retain original third-party reports.
ITP ID / event | Record field | Actual entry / observation | Evidence / report ref. | Disposition / action ref. | Performed by / date | Reviewed / decision ref.
FND-01 | Footing type / ID
FND-01 | Grid / level
FND-01 | Drawing / revision
FND-01 | Geotechnical/design basis ref
FND-01 | Conflict / RFI ref
FND-01 | Date / location / lot / result / status |  | Original report / photo / attachment reference | NCR / correction / recheck reference | Actual performer and date | Assigned review / decision reference
FND-02 | Footing / excavation ID
FND-02 | Grid / level
FND-02 | Measured dimensions / depth
FND-02 | Observed founding condition
FND-02 | Geotechnical/design inspection ref
FND-02 | Role / date / release ref
FND-02 | Date / location / lot / result / status |  | Original report / photo / attachment reference | NCR / correction / recheck reference | Actual performer and date | Assigned review / decision reference
FND-03 | Footing ID / grid
FND-03 | Actual location / level
FND-03 | Measure method / equipment
FND-03 | Service/interface ref
FND-03 | Deviation / disposition ref
FND-03 | Date / location / lot / result / status |  | Original report / photo / attachment reference | NCR / correction / recheck reference | Actual performer and date | Assigned review / decision reference
FND-04 | Footing / grid
FND-04 | Bar / schedule mark
FND-04 | Starter / supported element ID
FND-04 | Measured cover / method
FND-04 | Embed / waterstop ref
FND-04 | Issue / disposition ref
FND-04 | Date / location / lot / result / status |  | Original report / photo / attachment reference | NCR / correction / recheck reference | Actual performer and date | Assigned review / decision reference
FND-05 | Pour / footing IDs
FND-05 | Formwork / method ref
FND-05 | Base / cleanliness observation
FND-05 | Open item / action
FND-05 | Installer / role / date
FND-05 | Release person / role / date / ref
FND-05 | Date / location / lot / result / status |  | Original report / photo / attachment reference | NCR / correction / recheck reference | Actual performer and date | Assigned review / decision reference
FND-06 | Footing / pour ID
FND-06 | Batch / docket
FND-06 | Mix ID
FND-06 | Sample / test ID
FND-06 | Actual result / units
FND-06 | Tester / role / report ref
FND-06 | Date / location / lot / result / status |  | Original report / photo / attachment reference | NCR / correction / recheck reference | Actual performer and date | Assigned review / decision reference
FND-07 | Footing / placement zone
FND-07 | Placement time
FND-07 | Sequence / lift
FND-07 | Starter / embed observation
FND-07 | Interruption / issue / action ref
FND-07 | Date / location / lot / result / status |  | Original report / photo / attachment reference | NCR / correction / recheck reference | Actual performer and date | Assigned review / decision reference
FND-08 | Footing / pour ID
FND-08 | Curing / protection method
FND-08 | Start date/time
FND-08 | Strip / backfill date and authority ref
FND-08 | Loading / next-stage release ref
FND-08 | Date / location / lot / result / status |  | Original report / photo / attachment reference | NCR / correction / recheck reference | Actual performer and date | Assigned review / decision reference
FND-09 | Footing / supported element
FND-09 | Sample / batch ID
FND-09 | Lab / survey report ref
FND-09 | Actual result / units
FND-09 | Defect / repair / disposition ref
FND-09 | Handover record ref
FND-09 | Date / location / lot / result / status |  | Original report / photo / attachment reference | NCR / correction / recheck reference | Actual performer and date | Assigned review / decision reference

## Source Register
Topic Guidance Source Register
Source ID | Title | Locator and URL | Use and limitation
NSW-QMG | NSW Government Quality Management Guidelines for Construction, Appendix D (ITP guidance) | Public webpage description and Appendix D download listing; Appendix D DOCX content was not inspected. https://www.info.buy.nsw.gov.au/resources/construction/quality-management-guidelines-for-construction | Limited methodology context only: the NSW public page identifies a construction ITP guideline/checklist resource and contract-level quality planning. The linked Appendix D document itself was not inspected, so no detailed template fields or technical acceptance rules are attributed to it.
TMR-MRTS70 | Queensland TMR MRTS70 Concrete (July 2022) | MRTS70 July 2022: Sections 5 (quality system), 6 (concrete class), 7 (materials), 8 (storage), 9 (mix design/acceptance), 10 (batching/mixing/transport), 11 (plastic concrete acceptance), 12 (hardened concrete acceptance incl. sampling), 13 (environmental limits), 14 (defects/rectification), and 15 (in-situ concrete: tests, falsework/formwork, placement/compaction, tolerances, stripping/loading). Section 17 covers normal-class concrete-specific requirements including placement, finishing, curing and early loading. Local searchable extract: industry-library/text/tmr-mrts70.txt. https://www.tmr.qld.gov.au/_/media/busind/techstdpubs/specifications-and-drawings/specifications/2-bridges-and-structures/mrts70.pdf?extension=pdf&hash=BD4A48371C386F32622F6862572AA56A&rev=24517261eac44ddb86310c7980172050&sc_lang=en&size=1730809 | Inspected topic-specific technical example for Queensland transport/infrastructure concrete. In-situ topics are supported by Section 15; Section 17 is only relevant to its stated normal-class scope. Use numerical or procedural criteria only where the customer project adopts this edition and relevant annexures; not a general building requirement.
HUTCHIES-SUITE | Hutchinson Builders, Construction ITPs and Reports suite (downloadable Word examples) | Groundworks ITP/Report, Concrete Place ITP/Report, Structural Steel ITP/Report; downloaded public DOCX files inspected 2026-10-06 https://subbies.hutchies.com.au/resources/videos/safety-and-quality-planning | Australian builder industry examples support high-level task sequencing, separate groundworks/concrete/steel process stages, records and lot/report fields only. Examples are explicitly marked EXAMPLE; they are not standards and provide no universal acceptance values or test rates. Original templates are not redistributed or copied.
SA-AS1379-CATALOGUE | Standards Australia catalogue — AS 1379:2026, Specification and supply of concrete (metadata only) | Public catalogue listing: AS 1379:2026, Current, published 22 May 2026; metadata checked 7 October 2026. Designation, title, status and publication date only. Full standard text was not inspected. https://store.standards.org.au/explore-standards/manufacturing?page=104 | Edition-awareness pointer only; full standard text was not inspected. A new publication does not automatically amend a contract, adopted standard edition or MRTS70 July 2022. Confirm project adoption and applicable amendments before citing clauses or using acceptance values.
SA-AS3600-CATALOGUE | Standards Australia catalogue — AS 3600:2018, Concrete structures (metadata only) | Public catalogue lists AS 3600:2018 as Pending Revision and amendments 1:2018 and 2:2021 as Current; metadata checked 7 October 2026. Full standard and amendment texts were not inspected. https://store.standards.org.au/search?query=AS3600%3A2018%E2%80%93ConcreteStructures&status=Current_PendingRevision | Optional structural-reference pointer only; full standard and amendment texts were not inspected. Confirm applicability, project-adopted edition and amendments. Catalogue metadata does not establish technical compliance or supply project acceptance criteria.