# concrete-itp-template | Inspection and Test Plan

[Fill: project name] | Cast-in-place concrete inspection and test plan template — free editable baseline | [Fill: Australian state/territory] | Rev 00 | 2026-10-06 | For review

Contractor: [Fill: contractor]    Client: [Fill: client]
Scope: Reusable baseline for cast-in-place reinforced or plain concrete elements: footings, slabs, walls, beams and similar work. Confirm scope, concrete type, project criteria and whether the client requires a separate form. Excludes precast manufacture, prestressing, shotcrete, piles and specialist repair unless expressly added. This is a free, editable, proposed baseline and is not tailored to a project, approved by a client, or evidence of completed inspection. Before use, complete the scope questions and bracketed fields, confirm every criterion and control against current project documents, and remove non-applicable rows.
Exclusions: Confirm exclusions for this project; use the scope notes above.

| ID | Stage | Inspection / test | Method | Acceptance requirement | Reference | Frequency | Responsible role | Point | Approval / witness party | Notice / release | Record | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CON-01 | Planning and submittals | Proposed: baseline — Confirm scope, concrete element, drawings, specifications, approved mix and test plan are identified. | Proposed: baseline — Review current approved document register and pour schedule. | Proposed: baseline — For [Fill: Element / pour], current approved [Fill: Approved drawing/revision], [Fill: Mix design reference], specified [Fill: Specified class/strength] and [Fill: Project fresh/hardened test methods, frequency and acceptance] are available and consistent; list unresolved conflicts before work. | Guidance only; see Source Register: NSW-QMG, TMR-MRTS70 | Proposed: Before ordering or starting the pour. | Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Concrete submittal and document review register | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply. |
| CON-02 | Set-out | Proposed: baseline — Check element location, levels, dimensions and reference marks before formwork close-up. | Proposed: baseline — Survey or measure against approved drawings and established control marks. | Proposed: baseline — Location, dimensions and levels match [Fill: Approved drawings and revisions] and [Fill: Project dimensional criteria]; record each deviation for disposition. | Guidance only; see Source Register: NSW-QMG, TMR-MRTS70, HUTCHIES-SUITE | Proposed: Each pour / element before reinforcement or closure. | Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Concrete set-out check | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply. |
| CON-03 | Founding / substrate | Proposed: baseline — Check exposed founding surface or substrate is the specified type, level and condition before placing concrete. | Proposed: baseline — Visual inspection; compare geotechnical/design release and drawing; request geotechnical or design review where specified. | Proposed: baseline — Founding/substrate corresponds to [Fill: Founding / substrate requirement] and any required geotechnical release is recorded; unsuitable or changed conditions are referred for instruction. | Guidance only; see Source Register: NSW-QMG, TMR-MRTS70 | Proposed: Each footing, pour area or changed founding condition before blinding / placement. | Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Founding release and pre-pour checklist | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply. |
| CON-04 | Formwork and falsework | Proposed: baseline — Inspect formwork dimensions, line, level, support, cleanliness, tightness, release agent and access. | Proposed: baseline — Visual and dimensional inspection against drawings and approved temporary-works design/checks. | Proposed: baseline — Formwork matches [Fill: Formwork and temporary-works criteria]; supports/bracing and any required temporary-works release are documented; forms are clean and do not obstruct reinforcement or embeds. | Guidance only; see Source Register: NSW-QMG, TMR-MRTS70, HUTCHIES-SUITE | Proposed: Each form before reinforcement inspection / pour release. | Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Formwork / falsework inspection | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply. |
| CON-05 | Reinforcement materials | Proposed: baseline — Verify reinforcement product identification, grade, size and traceability before fixing. | Proposed: baseline — Check tags, delivery documents and material certificates against bar schedule and approved drawings. | Proposed: baseline — Each reinforcement type and size is identifiable and matches [Fill: Reinforcement schedule criteria]; retain certificates / traceability evidence required by project. | Guidance only; see Source Register: NSW-QMG, TMR-MRTS70 | Proposed: Each delivery/type before installation. | Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Reinforcement material register | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply. |
| CON-06 | Reinforcement installation | Proposed: baseline — Check bar position, spacing, laps, anchorage, cover supports and congestion against structural details. | Proposed: baseline — Visual inspection and measurement before concrete placement. | Proposed: baseline — Reinforcement arrangement matches [Fill: Bar arrangement criteria] and cover requirement [Fill: Specified cover]; resolve clashes or deviations through design instruction before pour. | Guidance only; see Source Register: NSW-QMG, TMR-MRTS70 | Proposed: Each element / pour before concrete placement. | Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Reinforcement inspection checklist | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply. |
| CON-07 | Cast-in items and joints | Proposed: baseline — Check cast-in plates, bolts, sleeves, conduits, waterstops, construction joints and isolation joints. | Proposed: baseline — Compare location, type and fixing against approved coordination/structural details; measure critical set-out. | Proposed: baseline — Installed items and joint preparation match [Fill: Embedment / joint detail references]; all required items are secured and remain clear for placement. | Guidance only; see Source Register: NSW-QMG, TMR-MRTS70, HUTCHIES-SUITE | Proposed: Each element before form closure / concrete placement. | Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Cast-in item and joint checklist | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply. |
| CON-08 | Pre-pour release | Proposed: baseline — Confirm prerequisites are complete and the pour area is ready; record the actual release decision. | Proposed: baseline — Complete pre-pour checklist covering formwork, reinforcement, embeds, cleanliness, access, weather/contingency and required approvals. | Proposed: baseline — All applicable checks CON-02 to CON-07 are accepted or have an approved disposition; required project release evidence [Fill: Required pre-pour release roles / documents] is recorded before placement. | Guidance only; see Source Register: NSW-QMG, TMR-MRTS70, HUTCHIES-SUITE | Proposed: Each pour before truck discharge / placement. | Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Signed pre-pour inspection checklist | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply. |
| CON-09 | Concrete delivery and batch identity | Proposed: baseline — Check each delivery docket and identify the supplied mix, batch, quantity and arrival/discharge times. | Proposed: baseline — Review docket at receipt and reconcile mix ID against approved order and pour location. | Proposed: baseline — Docket identifies the approved [Fill: Approved mix ID] and required batch details; mismatches, unauthorised additions or incomplete traceability are recorded and referred before use. | Guidance only; see Source Register: NSW-QMG, TMR-MRTS70, HUTCHIES-SUITE | Proposed: Every truck / batch. | Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Concrete delivery and placement log | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply. |
| CON-10 | Fresh concrete checks | Proposed: baseline — Perform specified fresh concrete tests and sampling and identify specimens to the relevant pour/batch. | Proposed: baseline — Use project-nominated test method, equipment and competent tester; label specimens with sample, batch and element IDs. | Proposed: baseline — Results meet the project values in [Fill: Fresh concrete methods / limits / frequency]; sample rate, test method, acceptance and any rejection authority come from project documents, not this template. | Guidance only; see Source Register: NSW-QMG, TMR-MRTS70, HUTCHIES-SUITE | Proposed: At the project-defined frequency for each pour/batch. | Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Fresh concrete test and sample register | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply. |
| CON-11 | Placement and consolidation | Proposed: baseline — Observe placement sequence, discharge location, continuity, segregation, consolidation and construction-joint treatment. | Proposed: baseline — Site observation during placement; note interruptions, method and corrective action. | Proposed: baseline — Placement follows [Fill: Approved placement / joint method] and approved method; no visible segregation, displacement of reinforcement/embeds or unapproved joint is left unresolved. | Guidance only; see Source Register: NSW-QMG, TMR-MRTS70, HUTCHIES-SUITE | Proposed: Continuously during each pour or at documented inspection intervals. | Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Concrete placement log | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply. |
| CON-12 | Finishing and surface | Proposed: baseline — Inspect finish, falls, edges, joints and surface condition against drawings and finish schedule. | Proposed: baseline — Visual and dimensional checks with straightedge/level or survey method stated by project. | Proposed: baseline — Finish, falls and joints meet [Fill: Finish / fall criteria]; surface defects are recorded and receive an approved disposition before concealment. | Guidance only; see Source Register: NSW-QMG, TMR-MRTS70, HUTCHIES-SUITE | Proposed: Each finished area before protection / handover. | Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Concrete finish inspection | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply. |
| CON-13 | Curing and protection | Proposed: baseline — Start and maintain specified curing and protect concrete from weather, early loading, impact and contamination. | Proposed: baseline — Record curing method, start/end, interruptions and protection measures. | Proposed: baseline — Curing follows [Fill: Curing method / duration] for the specified period/conditions; loading, stripping and exposure restrictions follow project/design instructions. | Guidance only; see Source Register: NSW-QMG, TMR-MRTS70, HUTCHIES-SUITE | Proposed: Start after finishing when permitted; monitor at project-defined intervals until release. | Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Curing and protection log | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply. |
| CON-14 | Strength specimen results | Proposed: baseline — Track laboratory reports for specimens to their concrete batch, element, test age and specified strength. | Proposed: baseline — Review lab report identity, method, curing/custody details and results against project criteria; refer adverse or missing results. | Proposed: baseline — Specimen traceability is complete and results satisfy [Fill: Specified strength and acceptance] at required test age; any nonconformance receives engineer/project disposition before dependent work. | Guidance only; see Source Register: NSW-QMG, TMR-MRTS70, HUTCHIES-SUITE | Proposed: On receipt of each specified test report. | Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Concrete strength test register and lab reports | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply. |
| CON-15 | Strip, survey, defects and closeout | Proposed: baseline — Verify approved stripping/loading status, finished geometry and defect/repair disposition; compile records. | Proposed: baseline — Check release instructions, survey/measure against drawings, inspect defects and close out records/NCRs. | Proposed: baseline — No stripping or loading before [Fill: Stripping / loading release]; dimensions comply with [Fill: Final geometry criteria]; defects/repairs have recorded approved dispositions and required test records are filed. | Guidance only; see Source Register: NSW-QMG, TMR-MRTS70 | Proposed: Before form removal where restricted, before follow-on concealment and at package completion. | Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Concrete completion, survey and defect register | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply. |

## Inspection point key

Inspection point key: H = Proposed Hold Point - use only if assigned in the contract | W = Proposed Witness Point - use only if assigned in the contract | R = Proposed Review | S = Proposed Surveillance | TBC = To be confirmed | N/A = Not applicable. External H/W rights and whether work may proceed are governed by the project contract and approved process; proposed points require agreement.

# Blank Inspection Record Forms

[Fill: project name] | concrete-itp-template | Record actual observations during the work. No results or signatures are pre-filled.

| ITP ID / Stage | Inspection / method / acceptance | Location / lot | Date and result | Evidence / record ref. | Performed by / signature | Reviewed by / signature |
| --- | --- | --- | --- | --- | --- | --- |
| CON-01 ¦ Planning and submittals | Proposed: baseline — Confirm scope, concrete element, drawings, specifications, approved mix and test plan are identified. Method: Proposed: baseline — Review current approved document register and pour schedule. Accept when: Proposed: baseline — For [Fill: Element / pour], current approved [Fill: Approved drawing/revision], [Fill: Mix design reference], specified [Fill: Specified class/strength] and [Fill: Project fresh/hardened test methods, frequency and acceptance] are available and consistent; list unresolved conflicts before work. Record: Concrete submittal and document review register |  | Date: __________ Document title / number: __________ Revision / issue date: __________ Conflict / missing input: __________ Approval / submission ref: __________ Result / disposition: __________ Corrective action / retest ref.: __________ |  |  |  |
| CON-02 ¦ Set-out | Proposed: baseline — Check element location, levels, dimensions and reference marks before formwork close-up. Method: Proposed: baseline — Survey or measure against approved drawings and established control marks. Accept when: Proposed: baseline — Location, dimensions and levels match [Fill: Approved drawings and revisions] and [Fill: Project dimensional criteria]; record each deviation for disposition. Record: Concrete set-out check |  | Date: __________ Location / grid: __________ Measured level: __________ Measured dimension (mm): __________ Deviation / disposition: __________ Result / disposition: __________ Corrective action / retest ref.: __________ |  |  |  |
| CON-03 ¦ Founding / substrate | Proposed: baseline — Check exposed founding surface or substrate is the specified type, level and condition before placing concrete. Method: Proposed: baseline — Visual inspection; compare geotechnical/design release and drawing; request geotechnical or design review where specified. Accept when: Proposed: baseline — Founding/substrate corresponds to [Fill: Founding / substrate requirement] and any required geotechnical release is recorded; unsuitable or changed conditions are referred for instruction. Record: Founding release and pre-pour checklist |  | Date: __________ Grid / area: __________ Founding level: __________ Geotechnical / design release ref: __________ Result / disposition: __________ Corrective action / retest ref.: __________ |  |  |  |
| CON-04 ¦ Formwork and falsework | Proposed: baseline — Inspect formwork dimensions, line, level, support, cleanliness, tightness, release agent and access. Method: Proposed: baseline — Visual and dimensional inspection against drawings and approved temporary-works design/checks. Accept when: Proposed: baseline — Formwork matches [Fill: Formwork and temporary-works criteria]; supports/bracing and any required temporary-works release are documented; forms are clean and do not obstruct reinforcement or embeds. Record: Formwork / falsework inspection |  | Date: __________ Line / level result: __________ Dimensions checked: __________ Temporary works release: __________ Result / disposition: __________ Corrective action / retest ref.: __________ |  |  |  |
| CON-05 ¦ Reinforcement materials | Proposed: baseline — Verify reinforcement product identification, grade, size and traceability before fixing. Method: Proposed: baseline — Check tags, delivery documents and material certificates against bar schedule and approved drawings. Accept when: Proposed: baseline — Each reinforcement type and size is identifiable and matches [Fill: Reinforcement schedule criteria]; retain certificates / traceability evidence required by project. Record: Reinforcement material register |  | Date: __________ Bar mark / type: __________ Specified grade: __________ Nominal diameter (mm): __________ Certificate / docket reference: __________ Result / disposition: __________ Corrective action / retest ref.: __________ |  |  |  |
| CON-06 ¦ Reinforcement installation | Proposed: baseline — Check bar position, spacing, laps, anchorage, cover supports and congestion against structural details. Method: Proposed: baseline — Visual inspection and measurement before concrete placement. Accept when: Proposed: baseline — Reinforcement arrangement matches [Fill: Bar arrangement criteria] and cover requirement [Fill: Specified cover]; resolve clashes or deviations through design instruction before pour. Record: Reinforcement inspection checklist |  | Date: __________ Bar mark: __________ Measured spacing (mm): __________ Lap length (mm): __________ Measured cover (mm): __________ Result / disposition: __________ Corrective action / retest ref.: __________ |  |  |  |
| CON-07 ¦ Cast-in items and joints | Proposed: baseline — Check cast-in plates, bolts, sleeves, conduits, waterstops, construction joints and isolation joints. Method: Proposed: baseline — Compare location, type and fixing against approved coordination/structural details; measure critical set-out. Accept when: Proposed: baseline — Installed items and joint preparation match [Fill: Embedment / joint detail references]; all required items are secured and remain clear for placement. Record: Cast-in item and joint checklist |  | Date: __________ Item / type: __________ Grid / offset: __________ Projection / level (mm): __________ Result / disposition: __________ Corrective action / retest ref.: __________ |  |  |  |
| CON-08 ¦ Pre-pour release | Proposed: baseline — Confirm prerequisites are complete and the pour area is ready; record the actual release decision. Method: Proposed: baseline — Complete pre-pour checklist covering formwork, reinforcement, embeds, cleanliness, access, weather/contingency and required approvals. Accept when: Proposed: baseline — All applicable checks CON-02 to CON-07 are accepted or have an approved disposition; required project release evidence [Fill: Required pre-pour release roles / documents] is recorded before placement. Record: Signed pre-pour inspection checklist |  | Date: __________ Release date/time: __________ Open items / disposition: __________ Result / disposition: __________ Corrective action / retest ref.: __________ |  |  |  |
| CON-09 ¦ Concrete delivery and batch identity | Proposed: baseline — Check each delivery docket and identify the supplied mix, batch, quantity and arrival/discharge times. Method: Proposed: baseline — Review docket at receipt and reconcile mix ID against approved order and pour location. Accept when: Proposed: baseline — Docket identifies the approved [Fill: Approved mix ID] and required batch details; mismatches, unauthorised additions or incomplete traceability are recorded and referred before use. Record: Concrete delivery and placement log |  | Date: __________ Truck / docket no.: __________ Batch / mix ID: __________ Quantity (m³): __________ Arrival time: __________ Discharge start/end: __________ Result / disposition: __________ Corrective action / retest ref.: __________ |  |  |  |
| CON-10 ¦ Fresh concrete checks | Proposed: baseline — Perform specified fresh concrete tests and sampling and identify specimens to the relevant pour/batch. Method: Proposed: baseline — Use project-nominated test method, equipment and competent tester; label specimens with sample, batch and element IDs. Accept when: Proposed: baseline — Results meet the project values in [Fill: Fresh concrete methods / limits / frequency]; sample rate, test method, acceptance and any rejection authority come from project documents, not this template. Record: Fresh concrete test and sample register |  | Date: __________ Sample ID: __________ Slump / flow result (mm): __________ Concrete temperature (°C): __________ Air content (%): __________ Method / equipment ID: __________ Result / disposition: __________ Corrective action / retest ref.: __________ |  |  |  |
| CON-11 ¦ Placement and consolidation | Proposed: baseline — Observe placement sequence, discharge location, continuity, segregation, consolidation and construction-joint treatment. Method: Proposed: baseline — Site observation during placement; note interruptions, method and corrective action. Accept when: Proposed: baseline — Placement follows [Fill: Approved placement / joint method] and approved method; no visible segregation, displacement of reinforcement/embeds or unapproved joint is left unresolved. Record: Concrete placement log |  | Date: __________ Zone / lift: __________ Time: __________ Interruption / duration: __________ Corrective action: __________ Result / disposition: __________ Corrective action / retest ref.: __________ |  |  |  |
| CON-12 ¦ Finishing and surface | Proposed: baseline — Inspect finish, falls, edges, joints and surface condition against drawings and finish schedule. Method: Proposed: baseline — Visual and dimensional checks with straightedge/level or survey method stated by project. Accept when: Proposed: baseline — Finish, falls and joints meet [Fill: Finish / fall criteria]; surface defects are recorded and receive an approved disposition before concealment. Record: Concrete finish inspection |  | Date: __________ Area / grid: __________ Measured fall: __________ Defect / location: __________ Result / disposition: __________ Corrective action / retest ref.: __________ |  |  |  |
| CON-13 ¦ Curing and protection | Proposed: baseline — Start and maintain specified curing and protect concrete from weather, early loading, impact and contamination. Method: Proposed: baseline — Record curing method, start/end, interruptions and protection measures. Accept when: Proposed: baseline — Curing follows [Fill: Curing method / duration] for the specified period/conditions; loading, stripping and exposure restrictions follow project/design instructions. Record: Curing and protection log |  | Date: __________ Curing method: __________ Start date/time: __________ End date/time: __________ Conditions / protection: __________ Result / disposition: __________ Corrective action / retest ref.: __________ |  |  |  |
| CON-14 ¦ Strength specimen results | Proposed: baseline — Track laboratory reports for specimens to their concrete batch, element, test age and specified strength. Method: Proposed: baseline — Review lab report identity, method, curing/custody details and results against project criteria; refer adverse or missing results. Accept when: Proposed: baseline — Specimen traceability is complete and results satisfy [Fill: Specified strength and acceptance] at required test age; any nonconformance receives engineer/project disposition before dependent work. Record: Concrete strength test register and lab reports |  | Date: __________ Sample ID: __________ Batch ID: __________ Test age (days): __________ Strength result (MPa): __________ Lab report ref: __________ Result / disposition: __________ Corrective action / retest ref.: __________ |  |  |  |
| CON-15 ¦ Strip, survey, defects and closeout | Proposed: baseline — Verify approved stripping/loading status, finished geometry and defect/repair disposition; compile records. Method: Proposed: baseline — Check release instructions, survey/measure against drawings, inspect defects and close out records/NCRs. Accept when: Proposed: baseline — No stripping or loading before [Fill: Stripping / loading release]; dimensions comply with [Fill: Final geometry criteria]; defects/repairs have recorded approved dispositions and required test records are filed. Record: Concrete completion, survey and defect register |  | Date: __________ Element ID: __________ Survey report: __________ Defect / repair ref: __________ Record pack ref: __________ Result / disposition: __________ Corrective action / retest ref.: __________ |  |  |  |

# Source Register

| Source ID | Title / filename | Revision | Type | Path / URL |
| --- | --- | --- | --- | --- |
| NSW-QMG | NSW Government Quality Management Guidelines for Construction, Appendix D (ITP guidance) | See linked source; verify current edition and project adoption | guidance | https://www.info.buy.nsw.gov.au/resources/construction/quality-management-guidelines-for-construction |
| TMR-MRTS70 | Queensland TMR MRTS70 Concrete (July 2022) | See linked source; verify current edition and project adoption | guidance | https://www.tmr.qld.gov.au/_/media/busind/techstdpubs/specifications-and-drawings/specifications/2-bridges-and-structures/mrts70.pdf?extension=pdf&hash=BD4A48371C386F32622F6862572AA56A&rev=24517261eac44ddb86310c7980172050&sc_lang=en&size=1730809 |
| HUTCHIES-SUITE | Hutchinson Builders, Construction ITPs and Reports suite (downloadable Word examples) | See linked source; verify current edition and project adoption | guidance | https://subbies.hutchies.com.au/resources/videos/safety-and-quality-planning |

# Open Confirmations

| Issue ID | Priority | ITP rows | Open item | Action needed |
| --- | --- | --- | --- | --- |
| CONF-001 | confirmation | CON-01 | CON-01: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed. |
| CONF-002 | confirmation | CON-02 | CON-02: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed. |
| CONF-003 | confirmation | CON-03 | CON-03: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed. |
| CONF-004 | confirmation | CON-04 | CON-04: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed. |
| CONF-005 | confirmation | CON-05 | CON-05: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed. |
| CONF-006 | confirmation | CON-06 | CON-06: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed. |
| CONF-007 | confirmation | CON-07 | CON-07: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed. |
| CONF-008 | confirmation | CON-08 | CON-08: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed. |
| CONF-009 | confirmation | CON-09 | CON-09: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed. |
| CONF-010 | confirmation | CON-10 | CON-10: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed. |
| CONF-011 | confirmation | CON-11 | CON-11: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed. |
| CONF-012 | confirmation | CON-12 | CON-12: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed. |
| CONF-013 | confirmation | CON-13 | CON-13: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed. |
| CONF-014 | confirmation | CON-14 | CON-14: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed. |
| CONF-015 | confirmation | CON-15 | CON-15: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed. |