concrete-itp-template | Inspection and Test Plan
[Fill: project name] | Cast-in-place concrete inspection and test plan template — free editable baseline | [Fill: Australian state/territory] | Rev 00 | 2026-10-06 | For review
Contractor: [Fill: contractor]    Client: [Fill: client]
Scope: Reusable baseline for cast-in-place reinforced or plain concrete elements: footings, slabs, walls, beams and similar work. Confirm scope, concrete type, project criteria and whether the client requires a separate form. Excludes precast manufacture, prestressing, shotcrete, piles and specialist repair unless expressly added. This is a free, editable, proposed baseline and is not tailored to a project, approved by a client, or evidence of completed inspection. Before use, complete the scope questions and bracketed fields, confirm every criterion and control against current project documents, and remove non-applicable rows.
Exclusions: Confirm exclusions for this project; use the scope notes above.
	ID
	Stage
	Inspection / test
	Method
	Acceptance requirement
	Reference
	Frequency
	Responsible role
	Point
	Approval / witness party
	Notice / release
	Record
	Remarks

	CON-01
	Planning and submittals
	Proposed: baseline — Confirm scope, concrete element, drawings, specifications, approved mix and test plan are identified.
	Proposed: baseline — Review current approved document register and pour schedule.
	Proposed: baseline — For [Fill: Element / pour], current approved [Fill: Approved drawing/revision], [Fill: Mix design reference], specified [Fill: Specified class/strength] and [Fill: Project fresh/hardened test methods, frequency and acceptance] are available and consistent; list unresolved conflicts before work.
	Guidance only; see Source Register: NSW-QMG, TMR-MRTS70
	Proposed: Before ordering or starting the pour.
	Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review.
	TBC
	Proposed: [Fill: reviewing role / authority assigned by project]
	Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies.
	Concrete submittal and document review register
	Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.

	CON-02
	Set-out
	Proposed: baseline — Check element location, levels, dimensions and reference marks before formwork close-up.
	Proposed: baseline — Survey or measure against approved drawings and established control marks.
	Proposed: baseline — Location, dimensions and levels match [Fill: Approved drawings and revisions] and [Fill: Project dimensional criteria]; record each deviation for disposition.
	Guidance only; see Source Register: NSW-QMG, TMR-MRTS70, HUTCHIES-SUITE
	Proposed: Each pour / element before reinforcement or closure.
	Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review.
	TBC
	Proposed: [Fill: reviewing role / authority assigned by project]
	Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies.
	Concrete set-out check
	Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.

	CON-03
	Founding / substrate
	Proposed: baseline — Check exposed founding surface or substrate is the specified type, level and condition before placing concrete.
	Proposed: baseline — Visual inspection; compare geotechnical/design release and drawing; request geotechnical or design review where specified.
	Proposed: baseline — Founding/substrate corresponds to [Fill: Founding / substrate requirement] and any required geotechnical release is recorded; unsuitable or changed conditions are referred for instruction.
	Guidance only; see Source Register: NSW-QMG, TMR-MRTS70
	Proposed: Each footing, pour area or changed founding condition before blinding / placement.
	Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review.
	TBC
	Proposed: [Fill: reviewing role / authority assigned by project]
	Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies.
	Founding release and pre-pour checklist
	Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.

	CON-04
	Formwork and falsework
	Proposed: baseline — Inspect formwork dimensions, line, level, support, cleanliness, tightness, release agent and access.
	Proposed: baseline — Visual and dimensional inspection against drawings and approved temporary-works design/checks.
	Proposed: baseline — Formwork matches [Fill: Formwork and temporary-works criteria]; supports/bracing and any required temporary-works release are documented; forms are clean and do not obstruct reinforcement or embeds.
	Guidance only; see Source Register: NSW-QMG, TMR-MRTS70, HUTCHIES-SUITE
	Proposed: Each form before reinforcement inspection / pour release.
	Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review.
	TBC
	Proposed: [Fill: reviewing role / authority assigned by project]
	Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies.
	Formwork / falsework inspection
	Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.

	CON-05
	Reinforcement materials
	Proposed: baseline — Verify reinforcement product identification, grade, size and traceability before fixing.
	Proposed: baseline — Check tags, delivery documents and material certificates against bar schedule and approved drawings.
	Proposed: baseline — Each reinforcement type and size is identifiable and matches [Fill: Reinforcement schedule criteria]; retain certificates / traceability evidence required by project.
	Guidance only; see Source Register: NSW-QMG, TMR-MRTS70
	Proposed: Each delivery/type before installation.
	Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review.
	TBC
	Proposed: [Fill: reviewing role / authority assigned by project]
	Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies.
	Reinforcement material register
	Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.

	CON-06
	Reinforcement installation
	Proposed: baseline — Check bar position, spacing, laps, anchorage, cover supports and congestion against structural details.
	Proposed: baseline — Visual inspection and measurement before concrete placement.
	Proposed: baseline — Reinforcement arrangement matches [Fill: Bar arrangement criteria] and cover requirement [Fill: Specified cover]; resolve clashes or deviations through design instruction before pour.
	Guidance only; see Source Register: NSW-QMG, TMR-MRTS70
	Proposed: Each element / pour before concrete placement.
	Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review.
	TBC
	Proposed: [Fill: reviewing role / authority assigned by project]
	Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies.
	Reinforcement inspection checklist
	Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.

	CON-07
	Cast-in items and joints
	Proposed: baseline — Check cast-in plates, bolts, sleeves, conduits, waterstops, construction joints and isolation joints.
	Proposed: baseline — Compare location, type and fixing against approved coordination/structural details; measure critical set-out.
	Proposed: baseline — Installed items and joint preparation match [Fill: Embedment / joint detail references]; all required items are secured and remain clear for placement.
	Guidance only; see Source Register: NSW-QMG, TMR-MRTS70, HUTCHIES-SUITE
	Proposed: Each element before form closure / concrete placement.
	Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review.
	TBC
	Proposed: [Fill: reviewing role / authority assigned by project]
	Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies.
	Cast-in item and joint checklist
	Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.

	CON-08
	Pre-pour release
	Proposed: baseline — Confirm prerequisites are complete and the pour area is ready; record the actual release decision.
	Proposed: baseline — Complete pre-pour checklist covering formwork, reinforcement, embeds, cleanliness, access, weather/contingency and required approvals.
	Proposed: baseline — All applicable checks CON-02 to CON-07 are accepted or have an approved disposition; required project release evidence [Fill: Required pre-pour release roles / documents] is recorded before placement.
	Guidance only; see Source Register: NSW-QMG, TMR-MRTS70, HUTCHIES-SUITE
	Proposed: Each pour before truck discharge / placement.
	Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review.
	TBC
	Proposed: [Fill: reviewing role / authority assigned by project]
	Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies.
	Signed pre-pour inspection checklist
	Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.

	CON-09
	Concrete delivery and batch identity
	Proposed: baseline — Check each delivery docket and identify the supplied mix, batch, quantity and arrival/discharge times.
	Proposed: baseline — Review docket at receipt and reconcile mix ID against approved order and pour location.
	Proposed: baseline — Docket identifies the approved [Fill: Approved mix ID] and required batch details; mismatches, unauthorised additions or incomplete traceability are recorded and referred before use.
	Guidance only; see Source Register: NSW-QMG, TMR-MRTS70, HUTCHIES-SUITE
	Proposed: Every truck / batch.
	Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review.
	TBC
	Proposed: [Fill: reviewing role / authority assigned by project]
	Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies.
	Concrete delivery and placement log
	Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.

	CON-10
	Fresh concrete checks
	Proposed: baseline — Perform specified fresh concrete tests and sampling and identify specimens to the relevant pour/batch.
	Proposed: baseline — Use project-nominated test method, equipment and competent tester; label specimens with sample, batch and element IDs.
	Proposed: baseline — Results meet the project values in [Fill: Fresh concrete methods / limits / frequency]; sample rate, test method, acceptance and any rejection authority come from project documents, not this template.
	Guidance only; see Source Register: NSW-QMG, TMR-MRTS70, HUTCHIES-SUITE
	Proposed: At the project-defined frequency for each pour/batch.
	Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review.
	TBC
	Proposed: [Fill: reviewing role / authority assigned by project]
	Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies.
	Fresh concrete test and sample register
	Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.

	CON-11
	Placement and consolidation
	Proposed: baseline — Observe placement sequence, discharge location, continuity, segregation, consolidation and construction-joint treatment.
	Proposed: baseline — Site observation during placement; note interruptions, method and corrective action.
	Proposed: baseline — Placement follows [Fill: Approved placement / joint method] and approved method; no visible segregation, displacement of reinforcement/embeds or unapproved joint is left unresolved.
	Guidance only; see Source Register: NSW-QMG, TMR-MRTS70, HUTCHIES-SUITE
	Proposed: Continuously during each pour or at documented inspection intervals.
	Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review.
	TBC
	Proposed: [Fill: reviewing role / authority assigned by project]
	Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies.
	Concrete placement log
	Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.

	CON-12
	Finishing and surface
	Proposed: baseline — Inspect finish, falls, edges, joints and surface condition against drawings and finish schedule.
	Proposed: baseline — Visual and dimensional checks with straightedge/level or survey method stated by project.
	Proposed: baseline — Finish, falls and joints meet [Fill: Finish / fall criteria]; surface defects are recorded and receive an approved disposition before concealment.
	Guidance only; see Source Register: NSW-QMG, TMR-MRTS70, HUTCHIES-SUITE
	Proposed: Each finished area before protection / handover.
	Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review.
	TBC
	Proposed: [Fill: reviewing role / authority assigned by project]
	Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies.
	Concrete finish inspection
	Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.

	CON-13
	Curing and protection
	Proposed: baseline — Start and maintain specified curing and protect concrete from weather, early loading, impact and contamination.
	Proposed: baseline — Record curing method, start/end, interruptions and protection measures.
	Proposed: baseline — Curing follows [Fill: Curing method / duration] for the specified period/conditions; loading, stripping and exposure restrictions follow project/design instructions.
	Guidance only; see Source Register: NSW-QMG, TMR-MRTS70, HUTCHIES-SUITE
	Proposed: Start after finishing when permitted; monitor at project-defined intervals until release.
	Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review.
	TBC
	Proposed: [Fill: reviewing role / authority assigned by project]
	Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies.
	Curing and protection log
	Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.

	CON-14
	Strength specimen results
	Proposed: baseline — Track laboratory reports for specimens to their concrete batch, element, test age and specified strength.
	Proposed: baseline — Review lab report identity, method, curing/custody details and results against project criteria; refer adverse or missing results.
	Proposed: baseline — Specimen traceability is complete and results satisfy [Fill: Specified strength and acceptance] at required test age; any nonconformance receives engineer/project disposition before dependent work.
	Guidance only; see Source Register: NSW-QMG, TMR-MRTS70, HUTCHIES-SUITE
	Proposed: On receipt of each specified test report.
	Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review.
	TBC
	Proposed: [Fill: reviewing role / authority assigned by project]
	Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies.
	Concrete strength test register and lab reports
	Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.

	CON-15
	Strip, survey, defects and closeout
	Proposed: baseline — Verify approved stripping/loading status, finished geometry and defect/repair disposition; compile records.
	Proposed: baseline — Check release instructions, survey/measure against drawings, inspect defects and close out records/NCRs.
	Proposed: baseline — No stripping or loading before [Fill: Stripping / loading release]; dimensions comply with [Fill: Final geometry criteria]; defects/repairs have recorded approved dispositions and required test records are filed.
	Guidance only; see Source Register: NSW-QMG, TMR-MRTS70
	Proposed: Before form removal where restricted, before follow-on concealment and at package completion.
	Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review.
	TBC
	Proposed: [Fill: reviewing role / authority assigned by project]
	Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies.
	Concrete completion, survey and defect register
	Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.



Inspection point key
Inspection point key: H = Proposed Hold Point - use only if assigned in the contract | W = Proposed Witness Point - use only if assigned in the contract | R = Proposed Review | S = Proposed Surveillance | TBC = To be confirmed | N/A = Not applicable. External H/W rights and whether work may proceed are governed by the project contract and approved process; proposed points require agreement.


Blank Inspection Record Forms
[Fill: project name] | concrete-itp-template | Record actual observations during the work. No results or signatures are pre-filled.
	ITP ID / Stage
	Inspection / method / acceptance
	Location / lot
	Date and result
	Evidence / record ref.
	Performed by / signature
	Reviewed by / signature

	CON-01 | Planning and submittals
	Proposed: baseline — Confirm scope, concrete element, drawings, specifications, approved mix and test plan are identified.
Method: Proposed: baseline — Review current approved document register and pour schedule.
Accept when: Proposed: baseline — For [Fill: Element / pour], current approved [Fill: Approved drawing/revision], [Fill: Mix design reference], specified [Fill: Specified class/strength] and [Fill: Project fresh/hardened test methods, frequency and acceptance] are available and consistent; list unresolved conflicts before work.
Record: Concrete submittal and document review register
	
	Date: __________
Document title / number: __________
Revision / issue date: __________
Conflict / missing input: __________
Approval / submission ref: __________
Result / disposition: __________
Corrective action / retest ref.: __________
	
	
	

	CON-02 | Set-out
	Proposed: baseline — Check element location, levels, dimensions and reference marks before formwork close-up.
Method: Proposed: baseline — Survey or measure against approved drawings and established control marks.
Accept when: Proposed: baseline — Location, dimensions and levels match [Fill: Approved drawings and revisions] and [Fill: Project dimensional criteria]; record each deviation for disposition.
Record: Concrete set-out check
	
	Date: __________
Location / grid: __________
Measured level: __________
Measured dimension (mm): __________
Deviation / disposition: __________
Result / disposition: __________
Corrective action / retest ref.: __________
	
	
	

	CON-03 | Founding / substrate
	Proposed: baseline — Check exposed founding surface or substrate is the specified type, level and condition before placing concrete.
Method: Proposed: baseline — Visual inspection; compare geotechnical/design release and drawing; request geotechnical or design review where specified.
Accept when: Proposed: baseline — Founding/substrate corresponds to [Fill: Founding / substrate requirement] and any required geotechnical release is recorded; unsuitable or changed conditions are referred for instruction.
Record: Founding release and pre-pour checklist
	
	Date: __________
Grid / area: __________
Founding level: __________
Geotechnical / design release ref: __________
Result / disposition: __________
Corrective action / retest ref.: __________
	
	
	

	CON-04 | Formwork and falsework
	Proposed: baseline — Inspect formwork dimensions, line, level, support, cleanliness, tightness, release agent and access.
Method: Proposed: baseline — Visual and dimensional inspection against drawings and approved temporary-works design/checks.
Accept when: Proposed: baseline — Formwork matches [Fill: Formwork and temporary-works criteria]; supports/bracing and any required temporary-works release are documented; forms are clean and do not obstruct reinforcement or embeds.
Record: Formwork / falsework inspection
	
	Date: __________
Line / level result: __________
Dimensions checked: __________
Temporary works release: __________
Result / disposition: __________
Corrective action / retest ref.: __________
	
	
	

	CON-05 | Reinforcement materials
	Proposed: baseline — Verify reinforcement product identification, grade, size and traceability before fixing.
Method: Proposed: baseline — Check tags, delivery documents and material certificates against bar schedule and approved drawings.
Accept when: Proposed: baseline — Each reinforcement type and size is identifiable and matches [Fill: Reinforcement schedule criteria]; retain certificates / traceability evidence required by project.
Record: Reinforcement material register
	
	Date: __________
Bar mark / type: __________
Specified grade: __________
Nominal diameter (mm): __________
Certificate / docket reference: __________
Result / disposition: __________
Corrective action / retest ref.: __________
	
	
	

	CON-06 | Reinforcement installation
	Proposed: baseline — Check bar position, spacing, laps, anchorage, cover supports and congestion against structural details.
Method: Proposed: baseline — Visual inspection and measurement before concrete placement.
Accept when: Proposed: baseline — Reinforcement arrangement matches [Fill: Bar arrangement criteria] and cover requirement [Fill: Specified cover]; resolve clashes or deviations through design instruction before pour.
Record: Reinforcement inspection checklist
	
	Date: __________
Bar mark: __________
Measured spacing (mm): __________
Lap length (mm): __________
Measured cover (mm): __________
Result / disposition: __________
Corrective action / retest ref.: __________
	
	
	

	CON-07 | Cast-in items and joints
	Proposed: baseline — Check cast-in plates, bolts, sleeves, conduits, waterstops, construction joints and isolation joints.
Method: Proposed: baseline — Compare location, type and fixing against approved coordination/structural details; measure critical set-out.
Accept when: Proposed: baseline — Installed items and joint preparation match [Fill: Embedment / joint detail references]; all required items are secured and remain clear for placement.
Record: Cast-in item and joint checklist
	
	Date: __________
Item / type: __________
Grid / offset: __________
Projection / level (mm): __________
Result / disposition: __________
Corrective action / retest ref.: __________
	
	
	

	CON-08 | Pre-pour release
	Proposed: baseline — Confirm prerequisites are complete and the pour area is ready; record the actual release decision.
Method: Proposed: baseline — Complete pre-pour checklist covering formwork, reinforcement, embeds, cleanliness, access, weather/contingency and required approvals.
Accept when: Proposed: baseline — All applicable checks CON-02 to CON-07 are accepted or have an approved disposition; required project release evidence [Fill: Required pre-pour release roles / documents] is recorded before placement.
Record: Signed pre-pour inspection checklist
	
	Date: __________
Release date/time: __________
Open items / disposition: __________
Result / disposition: __________
Corrective action / retest ref.: __________
	
	
	

	CON-09 | Concrete delivery and batch identity
	Proposed: baseline — Check each delivery docket and identify the supplied mix, batch, quantity and arrival/discharge times.
Method: Proposed: baseline — Review docket at receipt and reconcile mix ID against approved order and pour location.
Accept when: Proposed: baseline — Docket identifies the approved [Fill: Approved mix ID] and required batch details; mismatches, unauthorised additions or incomplete traceability are recorded and referred before use.
Record: Concrete delivery and placement log
	
	Date: __________
Truck / docket no.: __________
Batch / mix ID: __________
Quantity (m³): __________
Arrival time: __________
Discharge start/end: __________
Result / disposition: __________
Corrective action / retest ref.: __________
	
	
	

	CON-10 | Fresh concrete checks
	Proposed: baseline — Perform specified fresh concrete tests and sampling and identify specimens to the relevant pour/batch.
Method: Proposed: baseline — Use project-nominated test method, equipment and competent tester; label specimens with sample, batch and element IDs.
Accept when: Proposed: baseline — Results meet the project values in [Fill: Fresh concrete methods / limits / frequency]; sample rate, test method, acceptance and any rejection authority come from project documents, not this template.
Record: Fresh concrete test and sample register
	
	Date: __________
Sample ID: __________
Slump / flow result (mm): __________
Concrete temperature (°C): __________
Air content (%): __________
Method / equipment ID: __________
Result / disposition: __________
Corrective action / retest ref.: __________
	
	
	

	CON-11 | Placement and consolidation
	Proposed: baseline — Observe placement sequence, discharge location, continuity, segregation, consolidation and construction-joint treatment.
Method: Proposed: baseline — Site observation during placement; note interruptions, method and corrective action.
Accept when: Proposed: baseline — Placement follows [Fill: Approved placement / joint method] and approved method; no visible segregation, displacement of reinforcement/embeds or unapproved joint is left unresolved.
Record: Concrete placement log
	
	Date: __________
Zone / lift: __________
Time: __________
Interruption / duration: __________
Corrective action: __________
Result / disposition: __________
Corrective action / retest ref.: __________
	
	
	

	CON-12 | Finishing and surface
	Proposed: baseline — Inspect finish, falls, edges, joints and surface condition against drawings and finish schedule.
Method: Proposed: baseline — Visual and dimensional checks with straightedge/level or survey method stated by project.
Accept when: Proposed: baseline — Finish, falls and joints meet [Fill: Finish / fall criteria]; surface defects are recorded and receive an approved disposition before concealment.
Record: Concrete finish inspection
	
	Date: __________
Area / grid: __________
Measured fall: __________
Defect / location: __________
Result / disposition: __________
Corrective action / retest ref.: __________
	
	
	

	CON-13 | Curing and protection
	Proposed: baseline — Start and maintain specified curing and protect concrete from weather, early loading, impact and contamination.
Method: Proposed: baseline — Record curing method, start/end, interruptions and protection measures.
Accept when: Proposed: baseline — Curing follows [Fill: Curing method / duration] for the specified period/conditions; loading, stripping and exposure restrictions follow project/design instructions.
Record: Curing and protection log
	
	Date: __________
Curing method: __________
Start date/time: __________
End date/time: __________
Conditions / protection: __________
Result / disposition: __________
Corrective action / retest ref.: __________
	
	
	

	CON-14 | Strength specimen results
	Proposed: baseline — Track laboratory reports for specimens to their concrete batch, element, test age and specified strength.
Method: Proposed: baseline — Review lab report identity, method, curing/custody details and results against project criteria; refer adverse or missing results.
Accept when: Proposed: baseline — Specimen traceability is complete and results satisfy [Fill: Specified strength and acceptance] at required test age; any nonconformance receives engineer/project disposition before dependent work.
Record: Concrete strength test register and lab reports
	
	Date: __________
Sample ID: __________
Batch ID: __________
Test age (days): __________
Strength result (MPa): __________
Lab report ref: __________
Result / disposition: __________
Corrective action / retest ref.: __________
	
	
	

	CON-15 | Strip, survey, defects and closeout
	Proposed: baseline — Verify approved stripping/loading status, finished geometry and defect/repair disposition; compile records.
Method: Proposed: baseline — Check release instructions, survey/measure against drawings, inspect defects and close out records/NCRs.
Accept when: Proposed: baseline — No stripping or loading before [Fill: Stripping / loading release]; dimensions comply with [Fill: Final geometry criteria]; defects/repairs have recorded approved dispositions and required test records are filed.
Record: Concrete completion, survey and defect register
	
	Date: __________
Element ID: __________
Survey report: __________
Defect / repair ref: __________
Record pack ref: __________
Result / disposition: __________
Corrective action / retest ref.: __________
	
	
	





Source Register
	Source ID
	Title / filename
	Revision
	Type
	Path / URL

	NSW-QMG
	NSW Government Quality Management Guidelines for Construction, Appendix D (ITP guidance)
	See linked source; verify current edition and project adoption
	guidance
	https://www.info.buy.nsw.gov.au/resources/construction/quality-management-guidelines-for-construction

	TMR-MRTS70
	Queensland TMR MRTS70 Concrete (July 2022)
	See linked source; verify current edition and project adoption
	guidance
	https://www.tmr.qld.gov.au/_/media/busind/techstdpubs/specifications-and-drawings/specifications/2-bridges-and-structures/mrts70.pdf?extension=pdf&hash=BD4A48371C386F32622F6862572AA56A&rev=24517261eac44ddb86310c7980172050&sc_lang=en&size=1730809

	HUTCHIES-SUITE
	Hutchinson Builders, Construction ITPs and Reports suite (downloadable Word examples)
	See linked source; verify current edition and project adoption
	guidance
	https://subbies.hutchies.com.au/resources/videos/safety-and-quality-planning



Open Confirmations
	Issue ID
	Priority
	ITP rows
	Open item
	Action needed

	CONF-001
	confirmation
	CON-01
	CON-01: verify scope and project-specific requirements for this proposed baseline row.
	Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.

	CONF-002
	confirmation
	CON-02
	CON-02: verify scope and project-specific requirements for this proposed baseline row.
	Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.

	CONF-003
	confirmation
	CON-03
	CON-03: verify scope and project-specific requirements for this proposed baseline row.
	Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.

	CONF-004
	confirmation
	CON-04
	CON-04: verify scope and project-specific requirements for this proposed baseline row.
	Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.

	CONF-005
	confirmation
	CON-05
	CON-05: verify scope and project-specific requirements for this proposed baseline row.
	Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.

	CONF-006
	confirmation
	CON-06
	CON-06: verify scope and project-specific requirements for this proposed baseline row.
	Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.

	CONF-007
	confirmation
	CON-07
	CON-07: verify scope and project-specific requirements for this proposed baseline row.
	Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.

	CONF-008
	confirmation
	CON-08
	CON-08: verify scope and project-specific requirements for this proposed baseline row.
	Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.

	CONF-009
	confirmation
	CON-09
	CON-09: verify scope and project-specific requirements for this proposed baseline row.
	Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.

	CONF-010
	confirmation
	CON-10
	CON-10: verify scope and project-specific requirements for this proposed baseline row.
	Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.

	CONF-011
	confirmation
	CON-11
	CON-11: verify scope and project-specific requirements for this proposed baseline row.
	Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.

	CONF-012
	confirmation
	CON-12
	CON-12: verify scope and project-specific requirements for this proposed baseline row.
	Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.

	CONF-013
	confirmation
	CON-13
	CON-13: verify scope and project-specific requirements for this proposed baseline row.
	Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.

	CONF-014
	confirmation
	CON-14
	CON-14: verify scope and project-specific requirements for this proposed baseline row.
	Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.

	CONF-015
	confirmation
	CON-15
	CON-15: verify scope and project-specific requirements for this proposed baseline row.
	Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.







