## Start here
Concrete Slab Construction ITP Template
Reusable editable baseline for conventional cast-in-place building slabs on ground and suspended floor slabs within one clearly identified project work package. Includes pre-pour substrate/interface coordination, set-out, formwork, reinforcement and embeds, concrete supply/placement/testing, finish, joints, curing, protection and records. Suspended slab-specific temporary works, post-tensioning, precast, toppings/screeds, industrial floors, pavements and specialist slabs require separate scope unless expressly included. Design, soil classification, mix criteria, tolerances, test rates, statutory duties and contractual Hold/Witness points are not supplied.
Status | Free editable proposed baseline. It is not project-approved and is not evidence that work was inspected.
Project fields | Complete the project, jurisdiction, parties, document number/revision and scope in the controlled project copy.
Technical criteria | Replace every [Enter ...] prompt with the exact contract, approved drawing, specification or procedure reference and project condition. Confirm adopted editions and resolve conflicts.
Frequency and lot | These rows show proposed activity triggers only. Set the actual lot, sampling basis and frequency from project requirements.
Roles and control points | Confirm performing/reviewing roles, contractual or regulatory H/W rights, notice, evidence and release authority. No external control point is assigned.
Conditional work | Remove out-of-scope work or mark it not applicable with a reason. Include only processes required for this project.
Records | Use the matching blank Records sheet. Enter actual inspection date, observation, result and signature only when work is performed.
Evidence | Retain original certificates, test reports, survey records, photographs and written dispositions; index them rather than replacing them with a tick.
Scope boundary | Reusable editable baseline for conventional cast-in-place building slabs on ground and suspended floor slabs within one clearly identified project work package. Includes pre-pour substrate/interface coordination, set-out, formwork, reinforcement and embeds, concrete supply/placement/testing, finish, joints, curing, protection and records. Suspended slab-specific temporary works, post-tensioning, precast, toppings/screeds, industrial floors, pavements and specialist slabs require separate scope unless expressly included. Design, soil classification, mix criteria, tolerances, test rates, statutory duties and contractual Hold/Witness points are not supplied.
Project source prompts | Element / pour / lot: Identify the physical element, drawing grid/level, pour sequence and lot boundary. Approved drawings and revisions: List current structural drawings, details, schedules and approved design changes relevant to this element. Project specification and adopted standards: Enter exact contract clauses, adopted standards/editions and project criteria; do not infer adoption from a published edition. Approved concrete mix and supplier submission: Identify approved mix, supplier, delivery requirements and any project-authorised adjustments. Project test plan and acceptance: Identify specified test methods, sample/lot coverage, acceptance and designated tester/reviewer from controlled project documents. Performing, reviewing and release roles: Identify actual contractor, verifier/designer, notice duties, contractual Hold/Witness points and release authority. Project evidence and closeout requirements: Identify required pour records, test reports, survey, defect disposition and handover register. Slab system and boundaries: Identify slab-on-ground or suspended construction, included pours, levels and adjoining packages. Subgrade / support handover: Identify geotechnical/design basis, prepared support release, fill records and membrane/termite interfaces where applicable. Joint and finish schedule: Identify approved construction/isolation/control joints, floor finish, falls, levels and survey/tolerance sources. Stripping / loading release requirements: Identify design- or project-controlled criteria, authorization and dependent-work release; no value is presumed.

## ITP
Concrete Slab Construction ITP Template ¦ Proposed Inspection and Test Plan
Document number: [Enter] Revision: [Enter] Date: [Enter] Project: [Enter] Jurisdiction: [Enter] Contractor: [Enter] Reusable editable baseline for conventional cast-in-place building slabs on ground and suspended floor slabs within one clearly identified project work package. Includes pre-pour substrate/interface coordination, set-out, formwork, reinforcement and embeds, concrete supply/placement/testing, finish, joints, curing, protection and records. Suspended slab-specific temporary works, post-tensioning, precast, toppings/screeds, industrial floors, pavements and specialist slabs require separate scope unless expressly included. Design, soil classification, mix criteria, tolerances, test rates, statutory duties and contractual Hold/Witness points are not supplied.
ITP field | Proposed plan entry
SLB-01 | SLB-01 ¦ Package basis and pour segmentation
Inspection / test | Confirm slab system, pour boundaries, drawings, mix, test plan, interfaces and required records are current and consistent.
Method | Reconcile pour schedule, structural/architectural drawings, specification, subgrade/support handover and package responsibilities before procurement or work.
Project acceptance condition | For [Enter Element / pour / lot], approved [Enter Approved drawings and revisions] and [Enter Project specification and adopted standards] define the slab system and limits; approved mix [Enter Approved concrete mix and supplier submission] and test plan [Enter Project test plan and acceptance] are identified; unresolved conflicts and interfaces remain open.
Reference / locator | Enter actual controlled project document, revision and locator; see Source Register for topic guidance.
Trigger / frequency | Proposed: Before ordering and before the first affected pour; revisit approved revisions.
Performing / reviewing role | Proposed: [Enter Person/role performing this check] performs and records; [Enter Person/role reviewing this check] reviews only where assigned by project documents.
Control point / external party | Proposed record point only. Confirm any contractual or regulatory Hold/Witness point, notice period, release authority and evidence from the project documents; none is assigned by this baseline. [Enter Notice and release authority]
Notice / release evidence | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external release authority is assigned.
Record | Slab package and pour register
Applicability / remarks
SLB-02 | SLB-02 ¦ Support and pre-pour handover
Inspection / test | Verify the prepared subgrade, fill/support layer and interfaces below the slab are released and traceable before they are covered.
Method | Compare area limits and levels with approved geotechnical/design records and required compaction, drainage, membrane, termite or service-penetration evidence; do not perform geotechnical acceptance from visual inspection.
Project acceptance condition | Support condition and each required predecessor record match [Enter Subgrade / support handover] and project acceptance documents; any missing test, release or protection/interface remains Pending.
Reference / locator | Enter actual controlled project document, revision and locator; see Source Register for topic guidance.
Trigger / frequency | Proposed: Each identified slab area before reinforcement or concrete hides the support evidence.
Performing / reviewing role | Proposed: [Enter Person/role performing this check] performs and records; [Enter Person/role reviewing this check] reviews only where assigned by project documents.
Control point / external party | Proposed record point only. Confirm any contractual or regulatory Hold/Witness point, notice period, release authority and evidence from the project documents; none is assigned by this baseline. [Enter Notice and release authority]
Notice / release evidence | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external release authority is assigned.
Record | Slab support and predecessor release record
Applicability / remarks
SLB-03 | SLB-03 ¦ Set-out, formwork and edge details
Inspection / test | Check slab line, level, dimensions, rebates, thickenings, penetrations, construction joints and formwork against current details.
Method | Record the measured location and method; compare formwork stability/design evidence and geometry with the approved drawings and project formwork release.
Project acceptance condition | Set-out and formwork correspond to [Enter Approved drawings and revisions] and [Enter Project specification and adopted standards]; project-defined tolerances and any design/temporary-works release are evidenced before pour.
Reference / locator | Enter actual controlled project document, revision and locator; see Source Register for topic guidance.
Trigger / frequency | Proposed: Before reinforcement restricts access and at the project-defined pre-pour review.
Performing / reviewing role | Proposed: [Enter Person/role performing this check] performs and records; [Enter Person/role reviewing this check] reviews only where assigned by project documents.
Control point / external party | Proposed record point only. Confirm any contractual or regulatory Hold/Witness point, notice period, release authority and evidence from the project documents; none is assigned by this baseline. [Enter Notice and release authority]
Notice / release evidence | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external release authority is assigned.
Record | Slab set-out and formwork inspection
Applicability / remarks
SLB-04 | SLB-04 ¦ Reinforcement, cover and embedded items
Inspection / test | Confirm reinforcement type, marks, laps, supports and specified cover, plus cast-in services, conduits, starters and embeds, are located against approved details.
Method | Trace bar or mesh identifiers and placement to schedules; record actual check locations and cover method where specified; reconcile embedded services and openings with coordinated drawings.
Project acceptance condition | Reinforcement and embeds match [Enter Approved drawings and revisions] and [Enter Project specification and adopted standards] at checked areas; project-specified cover, support, laps and clearances are documented without supplying generic values.
Reference / locator | Enter actual controlled project document, revision and locator; see Source Register for topic guidance.
Trigger / frequency | Proposed: At identified pour zones before placement; include required project coverage and repeat after significant disturbance.
Performing / reviewing role | Proposed: [Enter Person/role performing this check] performs and records; [Enter Person/role reviewing this check] reviews only where assigned by project documents.
Control point / external party | Proposed record point only. Confirm any contractual or regulatory Hold/Witness point, notice period, release authority and evidence from the project documents; none is assigned by this baseline. [Enter Notice and release authority]
Notice / release evidence | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external release authority is assigned.
Record | Slab reinforcement and embedment pre-pour record
Applicability / remarks
SLB-05 | SLB-05 ¦ Pre-pour release and readiness
Inspection / test | Record the final accessible pre-pour review, required notices and actual release decisions for the defined slab area.
Method | Walk the pour limits; reconcile support, forms, steel, embeds, access, approved mix, weather/placement plan, test arrangements and outstanding issues to the project checklist and ITP.
Project acceptance condition | Pour proceeds only under the project-assigned authorization and documented status for [Enter Element / pour / lot]; installer completion, verifier observation and formal release are separately attributed.
Reference / locator | Enter actual controlled project document, revision and locator; see Source Register for topic guidance.
Trigger / frequency | Proposed: Once for each defined pour before concrete discharge, subject to the actual ITP notice and coverage.
Performing / reviewing role | Proposed: [Enter Person/role performing this check] performs and records; [Enter Person/role reviewing this check] reviews only where assigned by project documents.
Control point / external party | Proposed record point only. Confirm any contractual or regulatory Hold/Witness point, notice period, release authority and evidence from the project documents; none is assigned by this baseline. [Enter Notice and release authority]
Notice / release evidence | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external release authority is assigned.
Record | Slab pre-pour release register
Applicability / remarks
SLB-06 | SLB-06 ¦ Concrete delivery and fresh testing
Inspection / test | Reconcile delivered concrete and perform only the project-specified fresh tests and sampling with batch/sample traceability.
Method | Check delivery docket and approved mix identity; record additions or rejected loads; identify test method, equipment, sample IDs, tester and results from the controlled test plan.
Project acceptance condition | Delivery and fresh results are evaluated against [Enter Approved concrete mix and supplier submission] and [Enter Project test plan and acceptance]; no class, slump, temperature, sampling frequency or acceptance value is implied by this template.
Reference / locator | Enter actual controlled project document, revision and locator; see Source Register for topic guidance.
Trigger / frequency | Proposed: Each delivery/sample the project requires; exact lot linkage and frequency come from [Enter Project test plan and acceptance].
Performing / reviewing role | Proposed: [Enter Person/role performing this check] performs and records; [Enter Person/role reviewing this check] reviews only where assigned by project documents.
Control point / external party | Proposed record point only. Confirm any contractual or regulatory Hold/Witness point, notice period, release authority and evidence from the project documents; none is assigned by this baseline. [Enter Notice and release authority]
Notice / release evidence | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external release authority is assigned.
Record | Slab delivery and fresh concrete test register
Applicability / remarks
SLB-07 | SLB-07 ¦ Placement, consolidation and construction joints
Inspection / test | Observe slab placement sequence, continuity, consolidation around reinforcement/embeds, and treatment of planned or unplanned interruptions.
Method | Record zone and time sequence; compare equipment/method and joint preparation with approved pour plan; record delays, segregation, displacement or corrective action.
Project acceptance condition | Placement follows [Enter Project specification and adopted standards] and approved method; interruptions, defects or unapproved joints are referred and dispositioned by assigned authority before dependent work.
Reference / locator | Enter actual controlled project document, revision and locator; see Source Register for topic guidance.
Trigger / frequency | Proposed: During each pour at the coverage/interval defined in the project plan.
Performing / reviewing role | Proposed: [Enter Person/role performing this check] performs and records; [Enter Person/role reviewing this check] reviews only where assigned by project documents.
Control point / external party | Proposed record point only. Confirm any contractual or regulatory Hold/Witness point, notice period, release authority and evidence from the project documents; none is assigned by this baseline. [Enter Notice and release authority]
Notice / release evidence | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external release authority is assigned.
Record | Slab placement and joint log
Applicability / remarks
SLB-08 | SLB-08 ¦ Screeding, finish, levels and surface
Inspection / test | Record the specified slab finish and actual levels, falls, edges, joints and surface observations.
Method | Use the project-defined survey or measuring method; identify location, equipment and finish sample/reference; map defects and protect finished areas.
Project acceptance condition | Finish and geometry comply with [Enter Joint and finish schedule] and [Enter Project specification and adopted standards]; actual results are compared only with project tolerances and finish criteria.
Reference / locator | Enter actual controlled project document, revision and locator; see Source Register for topic guidance.
Trigger / frequency | Proposed: At defined zones during finishing and before protection or follow-on finishes.
Performing / reviewing role | Proposed: [Enter Person/role performing this check] performs and records; [Enter Person/role reviewing this check] reviews only where assigned by project documents.
Control point / external party | Proposed record point only. Confirm any contractual or regulatory Hold/Witness point, notice period, release authority and evidence from the project documents; none is assigned by this baseline. [Enter Notice and release authority]
Notice / release evidence | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external release authority is assigned.
Record | Slab surface and finish inspection
Applicability / remarks
SLB-09 | SLB-09 ¦ Curing, joints and early-age protection
Inspection / test | Track the specified curing method and period, joint operations where applicable, and protection/load restrictions.
Method | Record actual start/stop, interruptions, environmental observations, curing product/method and protection; verify release only against approved project instructions.
Project acceptance condition | Curing, joint timing and loading follow [Enter Project specification and adopted standards] and approved instructions; this baseline supplies no curing duration, saw-cut timing, load permission or weather limit.
Reference / locator | Enter actual controlled project document, revision and locator; see Source Register for topic guidance.
Trigger / frequency | Proposed: Start at the project-defined stage and maintain monitoring until the documented project release.
Performing / reviewing role | Proposed: [Enter Person/role performing this check] performs and records; [Enter Person/role reviewing this check] reviews only where assigned by project documents.
Control point / external party | Proposed record point only. Confirm any contractual or regulatory Hold/Witness point, notice period, release authority and evidence from the project documents; none is assigned by this baseline. [Enter Notice and release authority]
Notice / release evidence | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external release authority is assigned.
Record | Slab curing and protection log
Applicability / remarks
SLB-10 | SLB-10 ¦ Hardened test results, survey and closeout
Inspection / test | Reconcile specified laboratory results, as-built survey, defects, repairs and handover records to each pour.
Method | Link reports to mix, batch, sample, element and test age; compare geometry and results with controlled criteria; record authorized engineering disposition of adverse results.
Project acceptance condition | Required results and geometry satisfy [Enter Project test plan and acceptance] and [Enter Project specification and adopted standards] or have documented disposition by the assigned authority; closeout matches [Enter Project evidence and closeout requirements].
Reference / locator | Enter actual controlled project document, revision and locator; see Source Register for topic guidance.
Trigger / frequency | Proposed: On each required report/release and at package completion.
Performing / reviewing role | Proposed: [Enter Person/role performing this check] performs and records; [Enter Person/role reviewing this check] reviews only where assigned by project documents.
Control point / external party | Proposed record point only. Confirm any contractual or regulatory Hold/Witness point, notice period, release authority and evidence from the project documents; none is assigned by this baseline. [Enter Notice and release authority]
Notice / release evidence | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external release authority is assigned.
Record | Slab results, defects and handover register
Applicability / remarks

## Records
Blank Inspection Record Prompts
Complete during actual work. Actual result, date, names, approvals and signatures are intentionally blank. Retain original third-party reports.
ITP ID / event | Record field | Actual entry / observation | Evidence / report ref. | Disposition / action ref. | Performed by / date | Reviewed / decision ref.
SLB-01 | Pour / lot ID
SLB-01 | Slab type / boundary
SLB-01 | Drawing / revision
SLB-01 | Open interface / RFI
SLB-01 | Review / submission ref
SLB-01 | Date / location / lot / result / status |  | Original report / photo / attachment reference | NCR / correction / recheck reference | Actual performer and date | Assigned review / decision reference
SLB-02 | Area / grid
SLB-02 | Survey / level reference
SLB-02 | Support test / report ref
SLB-02 | Predecessor release / role / date
SLB-02 | Membrane / termite / service interface
SLB-02 | Date / location / lot / result / status |  | Original report / photo / attachment reference | NCR / correction / recheck reference | Actual performer and date | Assigned review / decision reference
SLB-03 | Grid / edge / pour zone
SLB-03 | Measured dimension / level
SLB-03 | Measure method / equipment
SLB-03 | Joint / rebate / opening ref
SLB-03 | Formwork design / release ref
SLB-03 | Date / location / lot / result / status |  | Original report / photo / attachment reference | NCR / correction / recheck reference | Actual performer and date | Assigned review / decision reference
SLB-04 | Pour zone / grid
SLB-04 | Bar / mesh mark
SLB-04 | Measured cover / method
SLB-04 | Embed / service ID
SLB-04 | Displacement / disposition ref
SLB-04 | Date / location / lot / result / status |  | Original report / photo / attachment reference | NCR / correction / recheck reference | Actual performer and date | Assigned review / decision reference
SLB-05 | Pour / area
SLB-05 | Open item / disposition
SLB-05 | Installer / role / date
SLB-05 | Verifier / role / date
SLB-05 | Release authority / decision / reference
SLB-05 | Date / location / lot / result / status |  | Original report / photo / attachment reference | NCR / correction / recheck reference | Actual performer and date | Assigned review / decision reference
SLB-06 | Batch / docket ID
SLB-06 | Mix ID
SLB-06 | Sample ID / location
SLB-06 | Test method / equipment
SLB-06 | Actual result / units
SLB-06 | Tester / role / report ref
SLB-06 | Date / location / lot / result / status |  | Original report / photo / attachment reference | NCR / correction / recheck reference | Actual performer and date | Assigned review / decision reference
SLB-07 | Placement zone
SLB-07 | Start / interruption times
SLB-07 | Joint / interruption ref
SLB-07 | Placement / consolidation method
SLB-07 | Issue / corrective action ref
SLB-07 | Date / location / lot / result / status |  | Original report / photo / attachment reference | NCR / correction / recheck reference | Actual performer and date | Assigned review / decision reference
SLB-08 | Zone / grid
SLB-08 | Finish designation
SLB-08 | Measured level / fall
SLB-08 | Method / equipment
SLB-08 | Defect / location / photo ref
SLB-08 | Date / location / lot / result / status |  | Original report / photo / attachment reference | NCR / correction / recheck reference | Actual performer and date | Assigned review / decision reference
SLB-09 | Curing method / product
SLB-09 | Start date/time
SLB-09 | End date/time
SLB-09 | Conditions / interruption
SLB-09 | Loading / follow-on release ref
SLB-09 | Date / location / lot / result / status |  | Original report / photo / attachment reference | NCR / correction / recheck reference | Actual performer and date | Assigned review / decision reference
SLB-10 | Element / pour
SLB-10 | Sample / batch ID
SLB-10 | Lab / survey report ref
SLB-10 | Actual result / units
SLB-10 | Defect / repair / disposition ref
SLB-10 | Dossier index ref
SLB-10 | Date / location / lot / result / status |  | Original report / photo / attachment reference | NCR / correction / recheck reference | Actual performer and date | Assigned review / decision reference

## Source Register
Topic Guidance Source Register
Source ID | Title | Locator and URL | Use and limitation
NSW-QMG | NSW Government Quality Management Guidelines for Construction, Appendix D (ITP guidance) | Public webpage description and Appendix D download listing; Appendix D DOCX content was not inspected. https://www.info.buy.nsw.gov.au/resources/construction/quality-management-guidelines-for-construction | Limited methodology context only: the NSW public page identifies a construction ITP guideline/checklist resource and contract-level quality planning. The linked Appendix D document itself was not inspected, so no detailed template fields or technical acceptance rules are attributed to it.
TMR-MRTS70 | Queensland TMR MRTS70 Concrete (July 2022) | MRTS70 July 2022: Sections 5 (quality system), 6 (concrete class), 7 (materials), 8 (storage), 9 (mix design/acceptance), 10 (batching/mixing/transport), 11 (plastic concrete acceptance), 12 (hardened concrete acceptance incl. sampling), 13 (environmental limits), 14 (defects/rectification), and 15 (in-situ concrete: tests, falsework/formwork, placement/compaction, tolerances, stripping/loading). Section 17 covers normal-class concrete-specific requirements including placement, finishing, curing and early loading. Local searchable extract: industry-library/text/tmr-mrts70.txt. https://www.tmr.qld.gov.au/_/media/busind/techstdpubs/specifications-and-drawings/specifications/2-bridges-and-structures/mrts70.pdf?extension=pdf&hash=BD4A48371C386F32622F6862572AA56A&rev=24517261eac44ddb86310c7980172050&sc_lang=en&size=1730809 | Inspected topic-specific technical example for Queensland transport/infrastructure concrete. In-situ topics are supported by Section 15; Section 17 is only relevant to its stated normal-class scope. Use numerical or procedural criteria only where the customer project adopts this edition and relevant annexures; not a general building requirement.
HUTCHIES-SUITE | Hutchinson Builders, Construction ITPs and Reports suite (downloadable Word examples) | Groundworks ITP/Report, Concrete Place ITP/Report, Structural Steel ITP/Report; downloaded public DOCX files inspected 2026-10-06 https://subbies.hutchies.com.au/resources/videos/safety-and-quality-planning | Australian builder industry examples support high-level task sequencing, separate groundworks/concrete/steel process stages, records and lot/report fields only. Examples are explicitly marked EXAMPLE; they are not standards and provide no universal acceptance values or test rates. Original templates are not redistributed or copied.
SA-AS1379-CATALOGUE | Standards Australia catalogue — AS 1379:2026, Specification and supply of concrete (metadata only) | Public catalogue listing: AS 1379:2026, Current, published 22 May 2026; metadata checked 7 October 2026. Designation, title, status and publication date only. Full standard text was not inspected. https://store.standards.org.au/explore-standards/manufacturing?page=104 | Edition-awareness pointer only; full standard text was not inspected. A new publication does not automatically amend a contract, adopted standard edition or MRTS70 July 2022. Confirm project adoption and applicable amendments before citing clauses or using acceptance values.
SA-AS3600-CATALOGUE | Standards Australia catalogue — AS 3600:2018, Concrete structures (metadata only) | Public catalogue lists AS 3600:2018 as Pending Revision and amendments 1:2018 and 2:2021 as Current; metadata checked 7 October 2026. Full standard and amendment texts were not inspected. https://store.standards.org.au/search?query=AS3600%3A2018%E2%80%93ConcreteStructures&status=Current_PendingRevision | Optional structural-reference pointer only; full standard and amendment texts were not inspected. Confirm applicability, project-adopted edition and amendments. Catalogue metadata does not establish technical compliance or supply project acceptance criteria.