## ITP
earthworks-itp-template ¦ Inspection and Test Plan
[Fill: project name] ¦ Earthworks and excavation inspection and test plan template — free editable baseline ¦ [Fill: Australian state/territory] ¦ Rev 00 ¦ 2026-10-06 ¦ For review Contractor: [Fill: contractor] Client: [Fill: client] Scope: Reusable baseline for site clearing, bulk cut/fill, foundation excavation, subgrade and trench backfill as applicable. Split the plan by material/use zone and identify geotechnical release interfaces. Excludes deep foundations, contaminated-land remediation, blasting, ground improvement and pavement-specific acceptance unless expressly included. This is a free, editable, proposed baseline and is not tailored to a project, approved by a client, or evidence of completed inspection. Before use, complete the scope questions and bracketed fields, confirm every criterion and control against current project documents, and remove non-applicable rows. Exclusions: Confirm exclusions for this project; use the scope notes above.
ID | Stage | Inspection / test | Method | Acceptance requirement | Reference | Frequency | Responsible role | Point | Approval / witness party | Notice / release | Record | Remarks
EAR-01 | Planning and geotechnical basis | Proposed: baseline — Confirm earthworks zones, cut/fill limits, geotechnical design, material classes, lot/testing rules and service constraints. | Proposed: baseline — Review current drawings, geotechnical report, specification, survey control, services information and approved work method. | Proposed: baseline — Current documents define [Fill: Scope / earthworks zones], [Fill: Material classification / acceptance], [Fill: Compaction criteria], [Fill: Lot size / test frequency] and [Fill: Design geometry, survey tolerances and deliverables]; identify conflicts and missing geotechnical dispositions. | Guidance only; see Source Register: NSW-QMG, TMR-MRTS04, HUTCHIES-SUITE | Proposed: Before clearing, excavation or fill placement. | Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Earthworks document and lot plan | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
EAR-02 | Survey control and set-out | Proposed: baseline — Verify survey control, limits, formation levels and service/set-out references before disturbance. | Proposed: baseline — Check control marks and survey set-out against approved drawings and survey plan. | Proposed: baseline — Control points are current and protected; limits and levels match [Fill: Set-out / tolerances]; conflicts with services or boundaries are resolved before excavation. | Guidance only; see Source Register: NSW-QMG, TMR-MRTS04, HUTCHIES-SUITE | Proposed: Before starting each area and after control disturbance. | Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Survey control and set-out record | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
EAR-03 | Service clearance and permits | Proposed: baseline — Confirm service searches, locating, permits and protection/diversion arrangements for the planned excavation. | Proposed: baseline — Review current service plans and clearance permits; record field locating/marking and required authority releases. | Proposed: baseline — Required services are located/protected and permits/clearances for [Fill: Earthworks activity and physical boundaries] are current before excavation; unknown services stop affected work for instruction. | Guidance only; see Source Register: NSW-QMG, TMR-MRTS04, HUTCHIES-SUITE | Proposed: Before ground penetration in each work area. | Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Services clearance / excavation permit | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
EAR-04 | Clearing and topsoil stripping | Proposed: baseline — Check clearing boundaries, topsoil/vegetation stripping, salvage and stockpile locations. | Proposed: baseline — Observe limits and compare stripped material handling with environmental and earthworks requirements. | Proposed: baseline — Work remains within [Fill: Clearing / topsoil handling limits]; topsoil and unsuitable material are segregated, identified and stored/disposed as specified. | Guidance only; see Source Register: NSW-QMG, TMR-MRTS04 | Proposed: Each clearing/stripping area before bulk excavation or fill. | Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Clearing and stripping checklist | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
EAR-05 | Unsuitable material and groundwater | Proposed: baseline — Identify soft, wet, contaminated or otherwise unsuitable material and unexpected groundwater during excavation. | Proposed: baseline — Visual inspection and geotechnical review where required; record extent, photographs, removal and replacement instructions. | Proposed: baseline — Unexpected conditions are referred under [Fill: Geotechnical referral and release process]; removal limits and replacement material are documented before covering. | Guidance only; see Source Register: NSW-QMG, TMR-MRTS04, HUTCHIES-SUITE | Proposed: Continuously as excavation exposes changed ground; before replacement. | Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Unsuitable material / geotechnical disposition record | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
EAR-06 | Excavation dimensions and formation | Proposed: baseline — Check excavation limits, lines, levels, stability and formation against drawings/geotechnical requirements. | Proposed: baseline — Measure/survey formation and inspect condition; involve geotechnical engineer where specified. | Proposed: baseline — Excavation geometry matches [Fill: Excavation geometry / level criteria] and founding condition meets documented [Fill: Founding condition / bearing criteria]; changed conditions receive written disposition before blinding/fill/structure. | Guidance only; see Source Register: NSW-QMG, TMR-MRTS04, HUTCHIES-SUITE | Proposed: Each foundation/formation area before covering or placing over. | Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Excavation and formation release | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
EAR-07 | Fill source and material approval | Proposed: baseline — Verify source, classification, sampling and approval for each proposed fill material. | Proposed: baseline — Review source approval and lab classification/test certificates; reconcile delivered material with approved source/material ID. | Proposed: baseline — Material is approved for [Fill: Fill use / zone] and meets [Fill: Required material properties]; any source or material change is approved and tested before placement. | Guidance only; see Source Register: NSW-QMG, TMR-MRTS04, HUTCHIES-SUITE | Proposed: Each source/material type and source change before use. | Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Fill material approval register | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
EAR-08 | Subgrade preparation and proof condition | Proposed: baseline — Check exposed subgrade is trimmed, drained and free from unacceptable disturbance before placing fill or pavement layers. | Proposed: baseline — Visual walkover and specified proof roll or geotechnical inspection; record soft spots and remediation. | Proposed: baseline — Subgrade matches [Fill: Subgrade condition / proof criteria] and any required proof/engineer release is documented; remedial areas are retested or re-released. | Guidance only; see Source Register: NSW-QMG, TMR-MRTS04, HUTCHIES-SUITE | Proposed: Each work area before first fill/pavement layer. | Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Subgrade inspection and release | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
EAR-09 | Fill placement layer controls | Proposed: baseline — Check placed material type, placement area, loose layer thickness and segregation before compaction. | Proposed: baseline — Observe placement; measure layer thickness and compare material and equipment/work method with approved trial or specification. | Proposed: baseline — Material matches approved source; layer and method comply with [Fill: Layer thickness / method criteria] and project/geotechnical requirements. | Guidance only; see Source Register: NSW-QMG, TMR-MRTS04, HUTCHIES-SUITE | Proposed: Each layer, area and material change before compaction. | Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Layer placement log | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
EAR-10 | Moisture conditioning and compaction | Proposed: baseline — Verify moisture conditioning and compaction method are appropriate to approved material and project requirement. | Proposed: baseline — Observe water addition/aeration and compaction passes/equipment; record method where required by project. | Proposed: baseline — Conditioning and compaction follow [Fill: Compaction / moisture conditioning method] for the approved material; do not infer target moisture or density. | Guidance only; see Source Register: NSW-QMG, TMR-MRTS04, HUTCHIES-SUITE | Proposed: Each layer and material/condition change. | Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Compaction process log | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
EAR-11 | In-situ density and material testing | Proposed: baseline — Arrange specified field/lab testing and link each result to the correct lot, layer, location and material. | Proposed: baseline — Use project-nominated methods and qualified/lab personnel; map test locations and compare results with exact project limits. | Proposed: baseline — Test method, rate, lot coverage and acceptance match [Fill: Density / compaction limits] and [Fill: Lot/test frequency]; failed/invalid tests trigger documented rework and retest. | Guidance only; see Source Register: NSW-QMG, TMR-MRTS04, HUTCHIES-SUITE | Proposed: At project-defined rate for each applicable lot/layer/material. | Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Earthworks lot and test register | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
EAR-12 | Nonconformance, rework and retest | Proposed: baseline — Track failed tests, unsuitable areas and corrective work through acceptable retest or written disposition. | Proposed: baseline — Review test/NCR records, identify affected lot and layer, verify rework boundaries and retest. | Proposed: baseline — Affected work is not covered or released until retest meets [Fill: Compaction acceptance values and test methods by zone/material] or a documented authorised disposition is issued; preserve test-to-lot traceability. | Guidance only; see Source Register: NSW-QMG, TMR-MRTS04 | Proposed: For each failure/deviation before covering subsequent layer. | Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Earthworks NCR and retest register | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
EAR-13 | Trench backfill and reinstatement | Proposed: baseline — Check bedding, haunch/side support, pipe protection and backfill material/layers for trench works. | Proposed: baseline — Inspect before concealment and record material, layer placement, specified compaction tests and surface reinstatement. | Proposed: baseline — Trench components and backfill comply with [Fill: Trench zone materials / compaction / cover criteria]; record service owner/inspection release and test evidence before cover. | Guidance only; see Source Register: NSW-QMG, TMR-MRTS04, HUTCHIES-SUITE | Proposed: Each trench section before cover and at specified compaction lot stages. | Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Trench backfill and pre-cover record | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
EAR-14 | Drainage, erosion and water management | Proposed: baseline — Check temporary drainage, dewatering, erosion/sediment controls and protection of completed formation/fill. | Proposed: baseline — Inspect controls before and during work and after rainfall/change events against approved environmental/site plans. | Proposed: baseline — Controls and discharge arrangements match [Fill: Water / erosion control requirements]; erosion, contamination or softening is corrected and affected work reassessed before acceptance. | Guidance only; see Source Register: NSW-QMG, TMR-MRTS04, HUTCHIES-SUITE | Proposed: Before disturbance, during active work and after triggering weather/events as project specifies. | Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Water and erosion control inspection log | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
EAR-15 | Final levels, geometry and closeout | Proposed: baseline — Survey completed surfaces, batters, slopes, formation and interfaces; compile material, lot and test records. | Proposed: baseline — Survey/measure against final design and compare register for all lots, nonconformances and geotechnical releases. | Proposed: baseline — Final geometry meets [Fill: As-built tolerances / survey coverage]; every lot has linked test/acceptance evidence and open deviations have approved disposition before handover. | Guidance only; see Source Register: NSW-QMG, TMR-MRTS04, HUTCHIES-SUITE | Proposed: Each completed zone before subsequent work / package closeout. | Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Earthworks as-built survey and lot closeout register | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
Point key: H = Proposed Hold Point - use only if assigned in the contract ¦ W = Proposed Witness Point - use only if assigned in the contract ¦ R = Proposed Review ¦ S = Proposed Surveillance ¦ TBC = To be confirmed ¦ N/A = Not applicable. External H/W rights and release rules must come from the project contract and approved process.

## Record Forms
Blank Inspection Record Forms
[Fill: project name] ¦ earthworks-itp-template ¦ Record actual observations during the work. No results or signatures are pre-filled.
ITP ID / Stage | Inspection / method / acceptance | Location / lot | Date and result | Evidence / record ref. | Performed by / signature | Reviewed by / signature
EAR-01 ¦ Planning and geotechnical basis | Proposed: baseline — Confirm earthworks zones, cut/fill limits, geotechnical design, material classes, lot/testing rules and service constraints. Method: Proposed: baseline — Review current drawings, geotechnical report, specification, survey control, services information and approved work method. Accept when: Proposed: baseline — Current documents define [Fill: Scope / earthworks zones], [Fill: Material classification / acceptance], [Fill: Compaction criteria], [Fill: Lot size / test frequency] and [Fill: Design geometry, survey tolerances and deliverables]; identify conflicts and missing geotechnical dispositions. Record: Earthworks document and lot plan |  | Date: __________ Document title / number: __________ Revision / issue date: __________ Geotechnical report reference: __________ Lot/testing plan reference: __________ Result / disposition: __________ Corrective action / retest ref.: __________
EAR-02 ¦ Survey control and set-out | Proposed: baseline — Verify survey control, limits, formation levels and service/set-out references before disturbance. Method: Proposed: baseline — Check control marks and survey set-out against approved drawings and survey plan. Accept when: Proposed: baseline — Control points are current and protected; limits and levels match [Fill: Set-out / tolerances]; conflicts with services or boundaries are resolved before excavation. Record: Survey control and set-out record |  | Date: __________ Area / chainage: __________ Control mark ID: __________ Design level (m): __________ Set-out level (m): __________ Result / disposition: __________ Corrective action / retest ref.: __________
EAR-03 ¦ Service clearance and permits | Proposed: baseline — Confirm service searches, locating, permits and protection/diversion arrangements for the planned excavation. Method: Proposed: baseline — Review current service plans and clearance permits; record field locating/marking and required authority releases. Accept when: Proposed: baseline — Required services are located/protected and permits/clearances for [Fill: Earthworks activity and physical boundaries] are current before excavation; unknown services stop affected work for instruction. Record: Services clearance / excavation permit |  | Date: __________ Service type / owner: __________ Marked location: __________ Permit / clearance ref: __________ Result / disposition: __________ Corrective action / retest ref.: __________
EAR-04 ¦ Clearing and topsoil stripping | Proposed: baseline — Check clearing boundaries, topsoil/vegetation stripping, salvage and stockpile locations. Method: Proposed: baseline — Observe limits and compare stripped material handling with environmental and earthworks requirements. Accept when: Proposed: baseline — Work remains within [Fill: Clearing / topsoil handling limits]; topsoil and unsuitable material are segregated, identified and stored/disposed as specified. Record: Clearing and stripping checklist |  | Date: __________ Area / chainage: __________ Stripped depth (mm): __________ Stockpile ID/location: __________ Result / disposition: __________ Corrective action / retest ref.: __________
EAR-05 ¦ Unsuitable material and groundwater | Proposed: baseline — Identify soft, wet, contaminated or otherwise unsuitable material and unexpected groundwater during excavation. Method: Proposed: baseline — Visual inspection and geotechnical review where required; record extent, photographs, removal and replacement instructions. Accept when: Proposed: baseline — Unexpected conditions are referred under [Fill: Geotechnical referral and release process]; removal limits and replacement material are documented before covering. Record: Unsuitable material / geotechnical disposition record |  | Date: __________ Location / depth: __________ Extent / volume (m³): __________ Observed condition: __________ Geotechnical instruction ref: __________ Result / disposition: __________ Corrective action / retest ref.: __________
EAR-06 ¦ Excavation dimensions and formation | Proposed: baseline — Check excavation limits, lines, levels, stability and formation against drawings/geotechnical requirements. Method: Proposed: baseline — Measure/survey formation and inspect condition; involve geotechnical engineer where specified. Accept when: Proposed: baseline — Excavation geometry matches [Fill: Excavation geometry / level criteria] and founding condition meets documented [Fill: Founding condition / bearing criteria]; changed conditions receive written disposition before blinding/fill/structure. Record: Excavation and formation release |  | Date: __________ Area / footing ID: __________ Formation level (m): __________ Depth (m): __________ Geotechnical release ref: __________ Result / disposition: __________ Corrective action / retest ref.: __________
EAR-07 ¦ Fill source and material approval | Proposed: baseline — Verify source, classification, sampling and approval for each proposed fill material. Method: Proposed: baseline — Review source approval and lab classification/test certificates; reconcile delivered material with approved source/material ID. Accept when: Proposed: baseline — Material is approved for [Fill: Fill use / zone] and meets [Fill: Required material properties]; any source or material change is approved and tested before placement. Record: Fill material approval register |  | Date: __________ Source / quarry: __________ Material / class: __________ Sample / report ID: __________ Approval reference: __________ Result / disposition: __________ Corrective action / retest ref.: __________
EAR-08 ¦ Subgrade preparation and proof condition | Proposed: baseline — Check exposed subgrade is trimmed, drained and free from unacceptable disturbance before placing fill or pavement layers. Method: Proposed: baseline — Visual walkover and specified proof roll or geotechnical inspection; record soft spots and remediation. Accept when: Proposed: baseline — Subgrade matches [Fill: Subgrade condition / proof criteria] and any required proof/engineer release is documented; remedial areas are retested or re-released. Record: Subgrade inspection and release |  | Date: __________ Area / chainage: __________ Proof method: __________ Soft spot / treatment: __________ Release reference: __________ Result / disposition: __________ Corrective action / retest ref.: __________
EAR-09 ¦ Fill placement layer controls | Proposed: baseline — Check placed material type, placement area, loose layer thickness and segregation before compaction. Method: Proposed: baseline — Observe placement; measure layer thickness and compare material and equipment/work method with approved trial or specification. Accept when: Proposed: baseline — Material matches approved source; layer and method comply with [Fill: Layer thickness / method criteria] and project/geotechnical requirements. Record: Layer placement log |  | Date: __________ Lot ID: __________ Layer number: __________ Material ID: __________ Loose thickness (mm): __________ Compaction plant: __________ Result / disposition: __________ Corrective action / retest ref.: __________
EAR-10 ¦ Moisture conditioning and compaction | Proposed: baseline — Verify moisture conditioning and compaction method are appropriate to approved material and project requirement. Method: Proposed: baseline — Observe water addition/aeration and compaction passes/equipment; record method where required by project. Accept when: Proposed: baseline — Conditioning and compaction follow [Fill: Compaction / moisture conditioning method] for the approved material; do not infer target moisture or density. Record: Compaction process log |  | Date: __________ Lot ID: __________ Layer number: __________ Conditioning action: __________ Plant / passes: __________ Result / disposition: __________ Corrective action / retest ref.: __________
EAR-11 ¦ In-situ density and material testing | Proposed: baseline — Arrange specified field/lab testing and link each result to the correct lot, layer, location and material. Method: Proposed: baseline — Use project-nominated methods and qualified/lab personnel; map test locations and compare results with exact project limits. Accept when: Proposed: baseline — Test method, rate, lot coverage and acceptance match [Fill: Density / compaction limits] and [Fill: Lot/test frequency]; failed/invalid tests trigger documented rework and retest. Record: Earthworks lot and test register |  | Date: __________ Lot ID: __________ Layer number: __________ Test location / coordinates: __________ Test method: __________ Measured result: __________ Applicable criterion: __________ Lab report ID: __________ Result / disposition: __________ Corrective action / retest ref.: __________
EAR-12 ¦ Nonconformance, rework and retest | Proposed: baseline — Track failed tests, unsuitable areas and corrective work through acceptable retest or written disposition. Method: Proposed: baseline — Review test/NCR records, identify affected lot and layer, verify rework boundaries and retest. Accept when: Proposed: baseline — Affected work is not covered or released until retest meets [Fill: Compaction acceptance values and test methods by zone/material] or a documented authorised disposition is issued; preserve test-to-lot traceability. Record: Earthworks NCR and retest register |  | Date: __________ NCR ID: __________ Affected lot/layer: __________ Rework performed: __________ Retest report / result: __________ Approval reference: __________ Result / disposition: __________ Corrective action / retest ref.: __________
EAR-13 ¦ Trench backfill and reinstatement | Proposed: baseline — Check bedding, haunch/side support, pipe protection and backfill material/layers for trench works. Method: Proposed: baseline — Inspect before concealment and record material, layer placement, specified compaction tests and surface reinstatement. Accept when: Proposed: baseline — Trench components and backfill comply with [Fill: Trench zone materials / compaction / cover criteria]; record service owner/inspection release and test evidence before cover. Record: Trench backfill and pre-cover record |  | Date: __________ Chainage / section: __________ Bedding material / thickness: __________ Cover / level: __________ Density test report / result: __________ Result / disposition: __________ Corrective action / retest ref.: __________
EAR-14 ¦ Drainage, erosion and water management | Proposed: baseline — Check temporary drainage, dewatering, erosion/sediment controls and protection of completed formation/fill. Method: Proposed: baseline — Inspect controls before and during work and after rainfall/change events against approved environmental/site plans. Accept when: Proposed: baseline — Controls and discharge arrangements match [Fill: Water / erosion control requirements]; erosion, contamination or softening is corrected and affected work reassessed before acceptance. Record: Water and erosion control inspection log |  | Date: __________ Area: __________ Control inspected: __________ Rain/event/time: __________ Action / closeout: __________ Result / disposition: __________ Corrective action / retest ref.: __________
EAR-15 ¦ Final levels, geometry and closeout | Proposed: baseline — Survey completed surfaces, batters, slopes, formation and interfaces; compile material, lot and test records. Method: Proposed: baseline — Survey/measure against final design and compare register for all lots, nonconformances and geotechnical releases. Accept when: Proposed: baseline — Final geometry meets [Fill: As-built tolerances / survey coverage]; every lot has linked test/acceptance evidence and open deviations have approved disposition before handover. Record: Earthworks as-built survey and lot closeout register |  | Date: __________ Zone / chainage: __________ Design level (m): __________ As-built level (m): __________ Survey report ref: __________ Lot closeout ref: __________ Result / disposition: __________ Corrective action / retest ref.: __________

## Source Register
Source Register
Source ID | Title | Revision / check | Type | Path / URL
NSW-QMG | NSW Government Quality Management Guidelines for Construction, Appendix D (ITP guidance) | See linked source; verify current edition and project adoption | guidance | https://www.info.buy.nsw.gov.au/resources/construction/quality-management-guidelines-for-construction
TMR-MRTS04 | Queensland TMR MRTS04 General Earthworks (March 2025) | See linked source; verify current edition and project adoption | guidance | https://www.tmr.qld.gov.au/_/media/busind/techstdpubs/specifications-and-drawings/specifications/3-roadworks-drainage-culverts-and-geotechnical/mrts04.pdf?extension=pdf&hash=840B4677F54FF4F65E5C80A7EF563206&rev=d832abe7f4fb4ca1bb13425291c3faca&sc_lang=en&size=2763810
HUTCHIES-SUITE | Hutchinson Builders, Construction ITPs and Reports suite (downloadable Word examples) | See linked source; verify current edition and project adoption | guidance | https://subbies.hutchies.com.au/resources/videos/safety-and-quality-planning

## Confirmations
Open Confirmations
Issue ID | Priority | ITP rows | Open item | Action needed
CONF-001 | confirmation | EAR-01 | EAR-01: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-002 | confirmation | EAR-02 | EAR-02: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-003 | confirmation | EAR-03 | EAR-03: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-004 | confirmation | EAR-04 | EAR-04: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-005 | confirmation | EAR-05 | EAR-05: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-006 | confirmation | EAR-06 | EAR-06: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-007 | confirmation | EAR-07 | EAR-07: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-008 | confirmation | EAR-08 | EAR-08: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-009 | confirmation | EAR-09 | EAR-09: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-010 | confirmation | EAR-10 | EAR-10: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-011 | confirmation | EAR-11 | EAR-11: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-012 | confirmation | EAR-12 | EAR-12: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-013 | confirmation | EAR-13 | EAR-13: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-014 | confirmation | EAR-14 | EAR-14: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-015 | confirmation | EAR-15 | EAR-15: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.