## Start here
Electrical Rough-in ITP Template
Ordinary building low-voltage electrical installation rough-in and associated circuit installation evidence. Covers only the identified project package and approved drawings. Excludes high voltage, hazardous areas, generation/storage/PV, fire alarm, security, communications/data, specialist controls and utility/network-owned works unless separately identified and supported by project-specific scope. No live-work guide is provided. Electrical work and tests belong to appropriately licensed/authorised personnel under applicable jurisdictional law; project values, legal Hold/Witness points and release authority are not supplied.
Status | Free editable proposed baseline. It is not project-approved and is not evidence that work was inspected.
Project fields | Complete the project, jurisdiction, parties, document number/revision and scope in the controlled project copy.
Technical criteria | Replace every [Enter ...] prompt with the exact contract, approved drawing, specification or procedure reference and project condition. Confirm adopted editions and resolve conflicts.
Frequency and lot | These rows show proposed activity triggers only. Set the actual lot, sampling basis and frequency from project requirements.
Roles and control points | Confirm performing/reviewing roles, contractual or regulatory H/W rights, notice, evidence and release authority. No external control point is assigned.
Conditional work | Remove out-of-scope work or mark it not applicable with a reason. Include only processes required for this project.
Records | Use the matching blank Records sheet. Enter actual inspection date, observation, result and signature only when work is performed.
Evidence | Retain original certificates, test reports, survey records, photographs and written dispositions; index them rather than replacing them with a tick.
Scope boundary | Ordinary building low-voltage electrical installation rough-in and associated circuit installation evidence. Covers only the identified project package and approved drawings. Excludes high voltage, hazardous areas, generation/storage/PV, fire alarm, security, communications/data, specialist controls and utility/network-owned works unless separately identified and supported by project-specific scope. No live-work guide is provided. Electrical work and tests belong to appropriately licensed/authorised personnel under applicable jurisdictional law; project values, legal Hold/Witness points and release authority are not supplied.
Project source prompts | Jurisdiction and regulator basis: Identify state/territory, electrical safety regulator, applicable licence classes, adopted requirements and notification/certificate rules; confirm current law. Approved electrical drawings and revisions: Identify controlled layouts, single-line diagrams, schedules, details and approved changes. Project specification and adopted standards: List exact project requirements, edition/revision and clauses from controlled sources; do not assume an edition. Electrical work scope and boundaries: Identify included circuits, equipment, work areas, package limits, interfaces and exclusions. Approved equipment and product evidence: Identify approved switchboards, protective devices, cables, accessories and required product evidence. Licensed roles, reviews and release authority: Identify licensed electrical contractor/worker, designer, inspector, network operator and contractual review/release roles; do not infer authority. Project verification and test criteria: Enter applicable test methods, acceptance criteria, coverage and record from current jurisdiction/project sources; no values supplied. Isolation and alternate supply arrangements: Identify all supply sources, isolation/lockout coordination and approved work controls; this baseline contains no live-work procedure. Certificates, test records and handover: Identify jurisdictional certificates, test schedules, as-builts, board schedules and dossier requirements. Network connection / energisation interface: Identify who requests inspection/connection, network owner prerequisites and separate supply-authorisation decision.

## ITP
Electrical Rough-in ITP Template ¦ Proposed Inspection and Test Plan
Document number: [Enter] Revision: [Enter] Date: [Enter] Project: [Enter] Jurisdiction: [Enter] Contractor: [Enter] Ordinary building low-voltage electrical installation rough-in and associated circuit installation evidence. Covers only the identified project package and approved drawings. Excludes high voltage, hazardous areas, generation/storage/PV, fire alarm, security, communications/data, specialist controls and utility/network-owned works unless separately identified and supported by project-specific scope. No live-work guide is provided. Electrical work and tests belong to appropriately licensed/authorised personnel under applicable jurisdictional law; project values, legal Hold/Witness points and release authority are not supplied.
ITP field | Proposed plan entry
ER-01 | ER-01 ¦ Scope, circuits and design release
Inspection / test | Confirm electrical work limits, circuits, area and approved drawings before installation.
Method | Compare scope matrix, latest approved layouts/single-line diagrams, circuit and equipment schedules; record interfaces and unresolved design decisions.
Project acceptance condition | Only the documented ordinary building low-voltage installation scope and current approved revisions are released; unresolved design or interface issues go to the assigned designer. Project source: [Enter Approved electrical drawings and revisions]; [Enter Project specification and adopted standards]; [Enter Jurisdiction and regulator basis]. Supporting controlled inputs: [Enter Approved equipment and product evidence]; [Enter Project verification and test criteria].
Reference / locator | Enter actual controlled project document, revision and locator; see Source Register for topic guidance.
Trigger / frequency | Proposed: Check the identified circuit, board or work lot before concealment or the next activity removes access; project coverage and timing must be confirmed.
Performing / reviewing role | Proposed: Assigned appropriately licensed electrical contractor/worker performs and records electrical work and tests within their authority. Other review roles act only within documented jurisdictional or contractual authority. Project role basis: [Enter Licensed roles, reviews and release authority]
Control point / external party | Proposed: Contractor check only. Confirm any statutory inspection, contractual Hold/Witness point, notice and release authority from jurisdiction and contract; none is assigned by this template. Project basis: [Enter Licensed roles, reviews and release authority]; [Enter Jurisdiction and regulator basis]
Notice / release evidence | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external release authority is assigned.
Record | Electrical scope and design release register
Applicability / remarks | Include when this activity is in the contracted work package. Baseline topic only. Resolve project criteria from the controlling source and preserve document/revision/clause or drawing/sheet/item locator; do not enter guessed values, inspection rates, legal H/W points or signatures.
ER-02 | ER-02 ¦ Product receipt and identification
Inspection / test | Check cables, conduits, accessories, supports and devices against approved submittals before installation.
Method | Match product/type and identification to approved schedule, required evidence and intended installation; record damage or mismatch disposition.
Project acceptance condition | Items match approved submittals and applicable jurisdictional/product evidence; unapproved items are held for disposition. Project source: [Enter Approved electrical drawings and revisions]; [Enter Project specification and adopted standards]; [Enter Jurisdiction and regulator basis]. Supporting controlled inputs: [Enter Approved equipment and product evidence].
Reference / locator | Enter actual controlled project document, revision and locator; see Source Register for topic guidance.
Trigger / frequency | Proposed: Check the identified circuit, board or work lot before concealment or the next activity removes access; project coverage and timing must be confirmed.
Performing / reviewing role | Proposed: Assigned appropriately licensed electrical contractor/worker performs and records electrical work and tests within their authority. Other review roles act only within documented jurisdictional or contractual authority. Project role basis: [Enter Licensed roles, reviews and release authority]
Control point / external party | Proposed: Contractor check only. Confirm any statutory inspection, contractual Hold/Witness point, notice and release authority from jurisdiction and contract; none is assigned by this template. Project basis: [Enter Licensed roles, reviews and release authority]; [Enter Jurisdiction and regulator basis]
Notice / release evidence | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external release authority is assigned.
Record | Electrical product receipt register
Applicability / remarks | Include when this activity is in the contracted work package. Baseline topic only. Resolve project criteria from the controlling source and preserve document/revision/clause or drawing/sheet/item locator; do not enter guessed values, inspection rates, legal H/W points or signatures.
ER-03 | ER-03 ¦ Containment route and support
Inspection / test | Inspect accessible containment, sleeves, routes, segregation and supports before cables are drawn or concealed.
Method | Walk the identified run; compare route, support method, penetrations and separation with controlled drawings and coordination documents; record obstruction or deviation.
Project acceptance condition | Route, support and interface details follow approved documents and applicable project criteria; unresolved clashes or fire/separation interfaces are closed by assigned authority. Project source: [Enter Approved electrical drawings and revisions]; [Enter Project specification and adopted standards]; [Enter Jurisdiction and regulator basis]. Supporting controlled inputs: [Enter Approved equipment and product evidence]; [Enter Project verification and test criteria].
Reference / locator | Enter actual controlled project document, revision and locator; see Source Register for topic guidance.
Trigger / frequency | Proposed: Check the identified circuit, board or work lot before concealment or the next activity removes access; project coverage and timing must be confirmed.
Performing / reviewing role | Proposed: Assigned appropriately licensed electrical contractor/worker performs and records electrical work and tests within their authority. Other review roles act only within documented jurisdictional or contractual authority. Project role basis: [Enter Licensed roles, reviews and release authority]
Control point / external party | Proposed: Contractor check only. Confirm any statutory inspection, contractual Hold/Witness point, notice and release authority from jurisdiction and contract; none is assigned by this template. Project basis: [Enter Licensed roles, reviews and release authority]; [Enter Jurisdiction and regulator basis]
Notice / release evidence | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external release authority is assigned.
Record | Containment route and support inspection record
Applicability / remarks | Include when this activity is in the contracted work package. Baseline topic only. Resolve project criteria from the controlling source and preserve document/revision/clause or drawing/sheet/item locator; do not enter guessed values, inspection rates, legal H/W points or signatures.
ER-04 | ER-04 ¦ Cable installation and identification
Inspection / test | Check installed cable identity, route, termination allowance and damage while accessible.
Method | Trace cable from source/destination, check labels against approved schedules, inspect visible sheath condition and record drum/circuit references where required.
Project acceptance condition | Installed cable is traceable to the approved circuit and product schedule; damage or unidentified conductors are dispositioned before termination. Project source: [Enter Approved electrical drawings and revisions]; [Enter Project specification and adopted standards]; [Enter Jurisdiction and regulator basis]. Supporting controlled inputs: [Enter Approved equipment and product evidence].
Reference / locator | Enter actual controlled project document, revision and locator; see Source Register for topic guidance.
Trigger / frequency | Proposed: Check the identified circuit, board or work lot before concealment or the next activity removes access; project coverage and timing must be confirmed.
Performing / reviewing role | Proposed: Assigned appropriately licensed electrical contractor/worker performs and records electrical work and tests within their authority. Other review roles act only within documented jurisdictional or contractual authority. Project role basis: [Enter Licensed roles, reviews and release authority]
Control point / external party | Proposed: Contractor check only. Confirm any statutory inspection, contractual Hold/Witness point, notice and release authority from jurisdiction and contract; none is assigned by this template. Project basis: [Enter Licensed roles, reviews and release authority]; [Enter Jurisdiction and regulator basis]
Notice / release evidence | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external release authority is assigned.
Record | Cable installation and identification inspection record
Applicability / remarks | Include when this activity is in the contracted work package. Baseline topic only. Resolve project criteria from the controlling source and preserve document/revision/clause or drawing/sheet/item locator; do not enter guessed values, inspection rates, legal H/W points or signatures.
ER-05 | ER-05 ¦ Concealed work and penetrations
Inspection / test | Capture required pre-cover evidence for concealed electrical routes, supports, fire-rated penetrations and accessible junctions.
Method | Review site location against approved drawings and specified penetration system; photograph/map only where required; record any required inspection/release before cover.
Project acceptance condition | Project-required concealed-work checks and approvals are recorded before concealment; no universal firestop or inspection release is inferred. Project source: [Enter Approved electrical drawings and revisions]; [Enter Project specification and adopted standards]; [Enter Jurisdiction and regulator basis]. Supporting controlled inputs: [Enter Approved equipment and product evidence].
Reference / locator | Enter actual controlled project document, revision and locator; see Source Register for topic guidance.
Trigger / frequency | Proposed: Check the identified circuit, board or work lot before concealment or the next activity removes access; project coverage and timing must be confirmed.
Performing / reviewing role | Proposed: Assigned appropriately licensed electrical contractor/worker performs and records electrical work and tests within their authority. Other review roles act only within documented jurisdictional or contractual authority. Project role basis: [Enter Licensed roles, reviews and release authority]
Control point / external party | Proposed: Contractor check only. Confirm any statutory inspection, contractual Hold/Witness point, notice and release authority from jurisdiction and contract; none is assigned by this template. Project basis: [Enter Licensed roles, reviews and release authority]; [Enter Jurisdiction and regulator basis]
Notice / release evidence | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external release authority is assigned.
Record | Concealed work and penetrations inspection record
Applicability / remarks | Include when this activity is in the contracted work package. Baseline topic only. Resolve project criteria from the controlling source and preserve document/revision/clause or drawing/sheet/item locator; do not enter guessed values, inspection rates, legal H/W points or signatures.
ER-06 | ER-06 ¦ Terminations, earthing and circuit completion
Inspection / test | Inspect completed terminations, protective conductor and bonding interfaces against approved details before testing.
Method | Assigned electrical worker checks identified terminations and earthing/bonding continuity arrangements using applicable approved method; reference circuit/device IDs and source criteria.
Project acceptance condition | Connections and earthing/bonding evidence meet project and applicable adopted requirements; actual measurements and disposition are entered in test record by authorised personnel. Project source: [Enter Approved electrical drawings and revisions]; [Enter Project specification and adopted standards]; [Enter Jurisdiction and regulator basis]. Supporting controlled inputs: [Enter Approved equipment and product evidence]; [Enter Project verification and test criteria]; [Enter Network connection / energisation interface].
Reference / locator | Enter actual controlled project document, revision and locator; see Source Register for topic guidance.
Trigger / frequency | Proposed: Check the identified circuit, board or work lot before concealment or the next activity removes access; project coverage and timing must be confirmed.
Performing / reviewing role | Proposed: Assigned appropriately licensed electrical contractor/worker performs and records electrical work and tests within their authority. Other review roles act only within documented jurisdictional or contractual authority. Project role basis: [Enter Licensed roles, reviews and release authority]
Control point / external party | Proposed: Contractor check only. Confirm any statutory inspection, contractual Hold/Witness point, notice and release authority from jurisdiction and contract; none is assigned by this template. Project basis: [Enter Licensed roles, reviews and release authority]; [Enter Jurisdiction and regulator basis]
Notice / release evidence | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external release authority is assigned.
Record | Terminations, earthing and circuit completion inspection record
Applicability / remarks | Include when this activity is in the contracted work package. Baseline topic only. Resolve project criteria from the controlling source and preserve document/revision/clause or drawing/sheet/item locator; do not enter guessed values, inspection rates, legal H/W points or signatures.
ER-07 | ER-07 ¦ Installation verification and testing
Inspection / test | Review required electrical verification evidence for identified installed circuits before handover or connection.
Method | Assigned licensed electrical worker carries out tests/examination required by applicable law and project documents; identify instruments, methods, criteria and actual results in controlled test record. Do not provide live-work instructions.
Project acceptance condition | Required test and examination evidence is complete for identified scope and meets criteria from the jurisdiction and project source; failed or missing results remain open. Project source: [Enter Approved electrical drawings and revisions]; [Enter Project specification and adopted standards]; [Enter Jurisdiction and regulator basis]. Supporting controlled inputs: [Enter Approved equipment and product evidence]; [Enter Project verification and test criteria]; [Enter Network connection / energisation interface].
Reference / locator | Enter actual controlled project document, revision and locator; see Source Register for topic guidance.
Trigger / frequency | Proposed: Check the identified circuit, board or work lot before concealment or the next activity removes access; project coverage and timing must be confirmed.
Performing / reviewing role | Proposed: Assigned appropriately licensed electrical contractor/worker performs and records electrical work and tests within their authority. Other review roles act only within documented jurisdictional or contractual authority. Project role basis: [Enter Licensed roles, reviews and release authority]
Control point / external party | Proposed: Contractor check only. Confirm any statutory inspection, contractual Hold/Witness point, notice and release authority from jurisdiction and contract; none is assigned by this template. Project basis: [Enter Licensed roles, reviews and release authority]; [Enter Jurisdiction and regulator basis]
Notice / release evidence | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external release authority is assigned.
Record | Installation verification and testing inspection record
Applicability / remarks | Include when this activity is in the contracted work package. Baseline topic only. Resolve project criteria from the controlling source and preserve document/revision/clause or drawing/sheet/item locator; do not enter guessed values, inspection rates, legal H/W points or signatures.
ER-08 | ER-08 ¦ As-built, certificates and handover
Inspection / test | Confirm final circuit schedules, as-builts, test records and jurisdictional certificates are collated for the package.
Method | Reconcile installed circuit IDs and approved changes to handover documents; verify certificate issuer and recipient requirements with jurisdictional regulator.
Project acceptance condition | Package records are complete to contract and jurisdictional requirements; project acceptance/release remains with assigned authority. Project source: [Enter Approved electrical drawings and revisions]; [Enter Project specification and adopted standards]; [Enter Jurisdiction and regulator basis]. Supporting controlled inputs: [Enter Project verification and test criteria]; [Enter Network connection / energisation interface].
Reference / locator | Enter actual controlled project document, revision and locator; see Source Register for topic guidance.
Trigger / frequency | Proposed: Check the identified circuit, board or work lot before concealment or the next activity removes access; project coverage and timing must be confirmed.
Performing / reviewing role | Proposed: Assigned appropriately licensed electrical contractor/worker performs and records electrical work and tests within their authority. Other review roles act only within documented jurisdictional or contractual authority. Project role basis: [Enter Licensed roles, reviews and release authority]
Control point / external party | Proposed: Contractor check only. Confirm any statutory inspection, contractual Hold/Witness point, notice and release authority from jurisdiction and contract; none is assigned by this template. Project basis: [Enter Licensed roles, reviews and release authority]; [Enter Jurisdiction and regulator basis]
Notice / release evidence | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external release authority is assigned.
Record | Electrical completion and certificate dossier
Applicability / remarks | Include when this activity is in the contracted work package. Baseline topic only. Resolve project criteria from the controlling source and preserve document/revision/clause or drawing/sheet/item locator; do not enter guessed values, inspection rates, legal H/W points or signatures.

## Records
Blank Inspection Record Prompts
Complete during actual work. Actual result, date, names, approvals and signatures are intentionally blank. Retain original third-party reports.
ITP ID / event | Record field | Actual entry / observation | Evidence / report ref. | Disposition / action ref. | Performed by / date | Reviewed / decision ref.
ER-01 | Area / level / drawing locator
ER-01 | Board / circuit schedule revision
ER-01 | Included circuit or run limits
ER-01 | Excluded work / interface owner
ER-01 | Open design decision / disposition
ER-01 | Date / location / lot / result / status |  | Original report / photo / attachment reference | NCR / correction / recheck reference | Actual performer and date | Assigned review / decision reference
ER-02 | Product type / identification
ER-02 | Cable drum / item batch where required
ER-02 | Approved submittal / instruction revision
ER-02 | Intended circuit / location
ER-02 | Damage / substitution / disposition
ER-02 | Date / location / lot / result / status |  | Original report / photo / attachment reference | NCR / correction / recheck reference | Actual performer and date | Assigned review / decision reference
ER-03 | Containment run / start and end
ER-03 | Support detail / instruction reference
ER-03 | Route / separation detail
ER-03 | Observed support / interface condition
ER-03 | Penetration / clash / correction reference
ER-03 | Date / location / lot / result / status |  | Original report / photo / attachment reference | NCR / correction / recheck reference | Actual performer and date | Assigned review / decision reference
ER-04 | Circuit / cable identification
ER-04 | Source and destination
ER-04 | Cable type / drum reference
ER-04 | Route / drawing revision
ER-04 | Visible damage / identification issue
ER-04 | Photo / corrective-action reference
ER-04 | Date / location / lot / result / status |  | Original report / photo / attachment reference | NCR / correction / recheck reference | Actual performer and date | Assigned review / decision reference
ER-05 | Area / concealed run / circuit
ER-05 | Drawing / penetration detail revision
ER-05 | Pre-cover observation / photo reference
ER-05 | Fire-separation system / installer evidence
ER-05 | Required notice / inspection reference
ER-05 | Outstanding item / assigned cover decision
ER-05 | Date / location / lot / result / status |  | Original report / photo / attachment reference | NCR / correction / recheck reference | Actual performer and date | Assigned review / decision reference
ER-06 | Board / circuit / termination ID
ER-06 | Connection / bonding detail reference
ER-06 | Supplier instruction / torque criterion source
ER-06 | Required tool / installation evidence
ER-06 | Actual observation / defect reference
ER-06 | Separate verification report reference
ER-06 | Date / location / lot / result / status |  | Original report / photo / attachment reference | NCR / correction / recheck reference | Actual performer and date | Assigned review / decision reference
ER-07 | Board / circuit / device identity
ER-07 | Verification scope / exclusion
ER-07 | Test type / method / criterion source
ER-07 | Instrument ID / validity evidence
ER-07 | Original report / actual result and unit
ER-07 | Failure / correction / retest link
ER-07 | Licensed test performer / report reference
ER-07 | Date / location / lot / result / status |  | Original report / photo / attachment reference | NCR / correction / recheck reference | Actual performer and date | Assigned review / decision reference
ER-08 | Board / circuit / included boundary
ER-08 | As-built / schedule revision
ER-08 | Verification report / certificate reference
ER-08 | Certificate issuer / jurisdiction pathway
ER-08 | Outstanding defect / exclusion
ER-08 | Contract handover / connection role reference
ER-08 | Date / location / lot / result / status |  | Original report / photo / attachment reference | NCR / correction / recheck reference | Actual performer and date | Assigned review / decision reference

## Source Register
Topic Guidance Source Register
Source ID | Title | Locator and URL | Use and limitation
QLD-TEST-LV | WorkSafe Queensland Electrical Safety Office, Testing | Accessed 7 October 2026; sections Who can test electrical equipment; What is energised electrical work; When is testing a form of energised electrical work; de-energised and isolated testing; requirements for energised testing. https://www.worksafe.qld.gov.au/safety-and-prevention/hazards/electricity/testing | Queensland-specific regulator guidance supports licensed testing and distinction between de-energised/isolated testing and energised work, including testing for dead. Use only as topic guidance; confirm current law and licensing in the project jurisdiction. No live-work procedure or numeric test criteria reproduced.
QLD-ESO-GUIDES | WorkSafe Queensland Electrical Safety Office, Electrical Safety Office technical guides | Accessed 7 October 2026; sections Guide to testing low voltage electrical installations, Guide to working on electrical installations with connections to alternate supplies, Guide to isolation and lockout procedures, Guide to service and submain polarity testing. https://www.worksafe.qld.gov.au/eso-technical-guides | Queensland regulator topic guidance for installation verification, alternate supplies and isolation/lockout. Apply only after confirming jurisdiction and current issue; it does not supply project acceptance values or project H/W points.
QLD-CERT | WorkSafe Queensland Electrical Safety Office, Issuing certificates of compliance | Accessed 7 October 2026; Requirements of certificates and FAQ: issuer, when certificate required, tested installation details, recipient, retention and signature. https://www.worksafe.qld.gov.au/laws-and-compliance/electrical-safety-laws/issuing-certificates-of-compliance | Queensland-specific example of electrical contractor certification following installation work. Do not generalise certificate name, trigger, retention or signatory rules nationally; identify applicable jurisdictional certificates from the regulator.
NSW-SIR-2026 | NSW Government, NSW Service and Installation Rules, April 2026 | Official PDF accessed 7 October 2026; sections for service and installation requirements, inspection/testing, certificates and supply connection (specific clause locator to be confirmed against applicable network rules). https://www.energy.nsw.gov.au/sites/default/files/2026-05/Service-and-Installation-Rules-NSW-April-2026.pdf | NSW-specific service/network interface reference only. Use to prompt separate network-owner connection and service requirements; not a national installation criterion or approval by this template.
SA-OTR-VERIFY | South Australia Office of the Technical Regulator, Electrical trades and testing/verification resources | Accessed 7 October 2026; Testing and verification section and linked Visual Inspection and Verification Form / Schedule of Test Results. The public form groups checks under general, consumers mains, switchboards, wiring systems, electrical equipment and earthing. https://www.energymining.sa.gov.au/industry/regulatory-services/office-of-the-technical-regulator/electrical-trades | Public example of inspection and test-record structure and separate compliance/reconnection interface. South Australia only; do not import its legal steps into another jurisdiction or use its form as project acceptance criteria.
VIC-DEFECTS | Energy Safe Victoria, Electrical installation defects | Accessed 7 October 2026; updated defect list and Top 10 Prescribed Inspections General defects, including switchboard, visual inspection and wiring-system topics. https://www.energysafe.vic.gov.au/certificates-electrical-safety/electrical-installation-defects | Victoria-specific public defect taxonomy supporting practical inspection topics and location-specific defect records. It is not a substitute for the adopted project standard or inspection by an authorised inspector.
VIC-POWER-INSPECTION | Energy Safe Victoria, Ensuring power is off until inspection FAQ | Accessed 7 October 2026; FAQ on keeping power off until inspection, including prescribed work and switchboard replacement context. https://www.energysafe.vic.gov.au/industry-guidance/electrical/frequently-asked-questions/ensuring-power-until-inspection | Victoria-specific illustration that inspection timing and restoration-of-supply requirements can be jurisdictional and work-type dependent. Do not generalise its rules nationally; confirm the actual local pathway and responsible party.