## Field record
Check ID | Check, observation and method | Specific record field | Project criterion / source document and revision | Actual record / issue / evidence
RIR-01 | Area, circuit and drawing identity What to observe: Area, level, circuit or cable ID, origin/destination and current drawing/schedule revision. How to check: Trace visible work to approved drawing and circuit schedule; note deviations for disposition. Acceptance basis: Installed extent is identifiable and checked against current approved design documents. Reference to confirm: Approved project electrical specification, jurisdictional rules, drawings and controlled test/inspection plan; record exact revision/clause. | Area / circuit
Drawing revision
Origin / destination
Result / status (Pass / Fail / N/A / Pending)
Inspector name / role / date
Photo / certificate / report reference
Issue / disposition / recheck evidence and date
RIR-02 | Route, supports and mechanical protection What to observe: Visible route, containment type, support arrangement, edge protection and exposure to damage. How to check: Compare installed arrangement to project details and approved product instructions; record locations without generic intervals. Acceptance basis: Project-specified support and protection are evidenced for this route. Reference to confirm: Approved project electrical specification, jurisdictional rules, drawings and controlled test/inspection plan; record exact revision/clause. | Route / containment
Support / protection detail
Photo / deviation ref
Result / status (Pass / Fail / N/A / Pending)
Inspector name / role / date
Photo / certificate / report reference
Issue / disposition / recheck evidence and date
RIR-03 | Segregation and service interfaces What to observe: Proximity/crossings with other services, incompatible systems, access zones and later trade interfaces. How to check: Compare interface to coordinated approved drawings and project requirements; document unresolved crossings. Acceptance basis: Required project separation and interface treatment are traceable. Reference to confirm: Approved project electrical specification, jurisdictional rules, drawings and controlled test/inspection plan; record exact revision/clause. | Crossing / interface
Coordination drawing
Disposition ref
Result / status (Pass / Fail / N/A / Pending)
Inspector name / role / date
Photo / certificate / report reference
Issue / disposition / recheck evidence and date
RIR-04 | Penetrations and fire-compartment interfaces What to observe: Penetration location, affected barrier identity and specified fire-stopping system/status. How to check: Match penetration to current fire strategy/detail and approved system submittal; record fire-stop evidence separately. Acceptance basis: Penetration treatment is traceable to approved project documents. Reference to confirm: Approved project electrical specification, jurisdictional rules, drawings and controlled test/inspection plan; record exact revision/clause. | Penetration ID
Barrier/detail ref
Fire-stop submittal
Result / status (Pass / Fail / N/A / Pending)
Inspector name / role / date
Photo / certificate / report reference
Issue / disposition / recheck evidence and date
RIR-05 | Cable / enclosure condition and ends What to observe: Visible damage, contamination, open ends, identification and protection at exposed terminations. How to check: Visually inspect accessible work and compare identification/protection to project requirements; no electrical testing implied. Acceptance basis: No unresolved visible damage or identification issue remains for this extent. Reference to confirm: Approved project electrical specification, jurisdictional rules, drawings and controlled test/inspection plan; record exact revision/clause. | Cable / enclosure ID
Observed defect
Repair ref
Result / status (Pass / Fail / N/A / Pending)
Inspector name / role / date
Photo / certificate / report reference
Issue / disposition / recheck evidence and date
RIR-06 | Concealment notice and evidence handover What to observe: Inspection request, witness requirement, open issues, photo coverage and authorised project release reference. How to check: Reconcile notice and required witness with project inspection plan; record release evidence from assigned role. Acceptance basis: Project-required pre-cover evidence and decisions are linked before concealment. Reference to confirm: Approved project electrical specification, jurisdictional rules, drawings and controlled test/inspection plan; record exact revision/clause. | Notice / witness ref
Open items
Release decision ref
Result / status (Pass / Fail / N/A / Pending)
Inspector name / role / date
Photo / certificate / report reference
Issue / disposition / recheck evidence and date

## Project setup
Cavoren ITP | Electrical Rough-In Inspection Record
Field | Project entry | Reason / instructions | Source / locator
Project name / contract
Client / principal
Contractor / trade
Jurisdiction / building class
Room / element / zone / lot
Inspection date / time
Checklist issue / revision
Project / jurisdiction / contractor
Area / level / room / grid
Drawing / revision / circuit schedule ref
Circuit / cable / containment identity
Origin and destination / board reference
Concealment stage / inspection notice
Penetration / fire compartment / interface refs
Photo / NCR / RFI / disposition refs
Required project input |  | Why it is needed
Approved electrical drawings, schedules and specifications |  | Identify design intent, routes, circuits, cable and containment requirements and revision.
Current coordination and fire-compartment details |  | Locate interfaces, penetrations, separation and required fire-stopping detail.
Project inspection and concealment schedule |  | Identify notice, witness and release roles before work becomes inaccessible.
Product approvals and installation instructions |  | Verify installed cable, containment, supports and protection against accepted submittals.
Electrical contractor work method and risk controls |  | Define qualified personnel, access controls and safe inspection arrangements.
Included scope | Visual and document checks of identified ordinary low-voltage rough-in work while accessible: route and circuit identity, support/protection, separation and interfaces, penetrations/fire-stopping coordination, enclosure condition and concealment evidence.
Excluded scope | Electrical design; conductor or protective-device selection/sizing; testing, commissioning, energisation or certification; high voltage, hazardous areas, PV/battery or specialist installations; and universal spacing, support interval, depth, separation or fire-rating values.
Use notice | Blank field record for ordinary building low-voltage electrical work only. Project documents and applicable state or territory requirements control. This record is neither a statutory certificate, electrical test certification, inspector approval nor authorisation to connect or energise. Do not perform electrical work or tests unless appropriately licensed/authorised. Actual results, dates, decisions and signatures remain blank until contemporaneous evidence is entered by the responsible person.
How to use
1 | Identify jurisdiction, exact installation/work boundary and current controlled drawing revision.
2 | Enter applicable project acceptance references, methods, limits, witness points and responsible roles from approved project documents; no defaults are supplied.
3 | Record actual observations/results only from contemporaneous work or issued reports, retaining units, report IDs and revisions.
4 | Maintain a dated, attributable event trail for defects, repair, retest and disposition; preserve earlier entries.
5 | Keep project release, statutory certificate, inspector sign-off or connection authorisation as separate evidence linked by reference.
Source title | Role and limits | URL | Locator
Queensland Electrical Safety Office, Guidelines for testing low voltage electrical installations (2026) | Queensland technical guidance; it does not set project criteria or authorise unqualified persons to test. | https://www.worksafe.qld.gov.au/__data/assets/pdf_file/0026/158525/guide-for-testing-low-voltage-electrical-installations.pdf | 2026 guide, visual inspection before mandatory tests and verification sections. Used for evidence categories and sequence context only.
WorkSafe Queensland, Electrical safety in the construction industry | Queensland jurisdictional guidance informing role and construction context. | https://www.worksafe.qld.gov.au/safety-and-prevention/hazards/electricity/industry-specific-electrical-hazards/electrical-safety-in-the-construction-industry | Construction electrical safety: electrical work by licensed/authorised persons; construction wiring inspection/testing by a qualified person before use.
WorkSafe Queensland, Issuing certificates of compliance | State-specific statutory certificate context. This record is expressly not that certificate. | https://www.worksafe.qld.gov.au/laws-and-compliance/electrical-safety-laws/issuing-certificates-of-compliance | Certificate of testing and compliance requirements for installation work and responsible issuer under Queensland rules.
Energy Safe Victoria, Electrical installation FAQ | Victoria-specific process example, subject to jurisdiction and work classification. | https://www.energysafe.vic.gov.au/industry-guidance/electrical/frequently-asked-questions/electrical-installation | Testing and inspection; prescribed work inspection before connection, including main switchboard example.
Energy Safe Victoria, Prescribed and non-prescribed work | Victoria-specific statutory boundary; not generalized to other jurisdictions. | https://www.energysafe.vic.gov.au/certificates-electrical-safety/obligations-and-guidelines/prescribed-and-non-prescribed-work | Prescribed installation work inspection, including consumer mains, main earthing and relevant main switchboard components.

## Issues and handover
Electrical Rough-In Inspection Record ¦ Issues and handover
Project | Location / area | Issue date | Open item reference | Person / role
Item ID / date | Affected location and issue | Immediate action / disposition | Recheck evidence / date | Responsible person / role
Electrical work evidence handover | Record evidence status | Select one status only
[ ] Evidence linked for assigned reviewer
[ ] Defect / required test / report remains open
[ ] Separate statutory, inspector, network or project decision required
Decision boundary | This field record preserves inspection and document references. It is not a statutory certificate, test certification, inspector sign-off, project release or authority to connect/energise.
Handover role | Installer / authorised electrical worker / scope and date
Handover role | Field recorder / role / evidence reference
Handover role | Electrical contractor responsible person / licence or authorisation ref
Handover role | Inspector / regulator / network approval reference where applicable
Handover role | Project reviewer / disposition reference
Handover role | Open defects / retest / as-built references
Signature note | Signatures record the named person’s stated role and entry only. They do not by themselves approve design, certify compliance, release a contractual control point or authorize the next activity.

## Event log
Electrical Rough-In Inspection Record event log
Use one row per defined area/circuit/check event. Keep project criteria separate from actual observations and reported results. Preserve failed and superseded entries; link every decision to its authorised role and separate evidence. This log does not certify work or authorise connection.
Project / contract |  |  | Element / pour / lot |  |  | Date / shift
Date / event | Area / board / circuit | Drawing / revision | Check / test category | Project method / criterion ref | Actual result / unit or observation | Report / photo / NCR ref | Action / retest / disposition | Role / reviewer / authority ref | Status / handover ref