## Field record
Check ID | Check, observation and method | Specific record field | Project criterion / source document and revision | Actual record / issue / evidence
FW-01 | Work package documents and design-check status What to observe: Identify element/boundary, current temporary-works drawings, design revision, erection sequence and required independent check/submission records. How to check: Compare work area with controlled document register; verify status and that check records apply to actual system/configuration. Acceptance basis: Use project temporary-works procedure, approved drawings, specification and contract points; cite design/check status without treating field inspection as design approval. Reference to confirm: Controlled temporary-works register, approved drawings, project procedure and required design/check records. | element / formwork zone
drawing / rev
design-check record ref
open query / response
Result / status (Pass / Fail / N/A / Pending)
Inspector name / role / date
Photo / certificate / report reference
Issue / disposition / recheck evidence and date
FW-02 | System components and visible condition What to observe: Observe form face/framing, proprietary components, ties/connectors and reused parts for damage, deformation, corrosion, omissions or unapproved mixed systems. How to check: Walk accessible faces and compare system identifiers/components with approved drawings, supplier details and inspection points. Acceptance basis: Use approved project system/component schedule; damaged/reused component criteria come from project designer/manufacturer. Reference to confirm: Approved system/component schedule, manufacturer instructions and project condition/disposition criteria. | system / component ID
location / condition
detail / drawing ref
photo / disposition ref
Result / status (Pass / Fail / N/A / Pending)
Inspector name / role / date
Photo / certificate / report reference
Issue / disposition / recheck evidence and date
FW-03 | Bearing, support and founding interface What to observe: Observe base plates, sole plates, bearers, props and actual ground/slab contact, including settlement, voids, disturbance or unplanned load transfer. How to check: Inspect support points against approved details and project ground/floor information; record location and movement signs. Acceptance basis: Use project design assumptions, approved support/founding detail and required ground/slab verification; no bearing capacity or prop load is set. Reference to confirm: Approved support/founding details, design assumptions and project ground/slab verification. | support ID / location
bearing detail ref
contact / movement
verification / direction ref
Result / status (Pass / Fail / N/A / Pending)
Inspector name / role / date
Photo / certificate / report reference
Issue / disposition / recheck evidence and date
FW-04 | Line, level, dimensions and formed profile What to observe: Check installed form surface/edges against element geometry and setting-out information, including openings/steps in this package. How to check: Measure project-designated points with identified instruments; record readings, grid/offset and drawing/detail. Acceptance basis: Use approved structural/formwork drawings and project tolerances; do not use generic dimensional limits. Reference to confirm: Approved structural and formwork drawings and project dimensional criteria. | grid / point
criterion / drawing ref
instrument / method
actual / unit / recheck
Result / status (Pass / Fail / N/A / Pending)
Inspector name / role / date
Photo / certificate / report reference
Issue / disposition / recheck evidence and date
FW-05 | Joints, sealing and concrete-loss paths What to observe: Inspect panel joints, corners, stop-ends, kickers, penetrations and closures for gaps, movement paths and sealing per approved detail/method. How to check: Visually inspect joints and compare materials/detail with temporary-works drawings and pour method; photograph suspected leakage paths. Acceptance basis: Use approved project joint/sealing detail and placement method; no generic gap limit or sealant prescription applies. Reference to confirm: Approved joint/sealing details and concrete placement method. | joint / location
detail / material ref
seal condition
repair / recheck ref
Result / status (Pass / Fail / N/A / Pending)
Inspector name / role / date
Photo / certificate / report reference
Issue / disposition / recheck evidence and date
FW-06 | Bracing, ties, connections and restraint fit What to observe: Observe braces, ties, wedges, pins, clamps and connections for presence, orientation/engagement and visible damage against approved arrangement. How to check: Inspect drawing-identified points; compare component and installation with system instructions/project erection details. Acceptance basis: Use approved temporary-works design and manufacturer/project details; do not infer spacing, torque, capacity or allowable deflection. Reference to confirm: Approved bracing/tie/connection details and applicable system installation instructions. | connection / location
system detail ref
engagement / defect
direction / recheck ref
Result / status (Pass / Fail / N/A / Pending)
Inspector name / role / date
Photo / certificate / report reference
Issue / disposition / recheck evidence and date
FW-07 | Cast-in openings and interface coordination What to observe: Check voids, block-outs, stop-ends or form interfaces shown on coordinated project drawings and within formwork package. How to check: Compare with current structural/coordination details; verify secure fixing and no unapproved cuts/alterations to system. Acceptance basis: Use approved coordinated drawings and temporary-works details; field-cut penetrations require approvals set by project design process. Reference to confirm: Approved coordination/opening drawings and temporary-works alteration details. | opening / grid
coordination drawing ref
position / dimensions
response / recheck ref
Result / status (Pass / Fail / N/A / Pending)
Inspector name / role / date
Photo / certificate / report reference
Issue / disposition / recheck evidence and date
FW-08 | Access, edge protection and work-stage safety interface What to observe: Observe access route, working platform, edge/opening protection and safe arrangement relevant to inspecting/placing concrete. How to check: Compare visible access/protection with project SWMS, work-at-height and temporary-works plans; refer hazards to site safety process. Acceptance basis: Apply site safety plan and jurisdictional WHS requirements; checklist does not certify a platform, edge protection or SWMS. Reference to confirm: Site SWMS, access/work-at-height plans and applicable jurisdictional WHS requirements. | zone / access point
SWMS / plan ref
hazard / reported role
correction evidence
Result / status (Pass / Fail / N/A / Pending)
Inspector name / role / date
Photo / certificate / report reference
Issue / disposition / recheck evidence and date
FW-09 | Placement-stage loads, access and change control What to observe: Confirm planned placement sequence, access and equipment are covered by current approved temporary-works/method documents; identify field changes. How to check: Review method with responsible site role and compare planned sequence/equipment/configuration to documented design assumptions. Acceptance basis: Use approved sequence and assumptions; no allowable load, pour rate, concrete pressure or vibration criterion is supplied. Reference to confirm: Approved placement method, temporary-works assumptions and written change review. | method revision
design assumption ref
equipment / sequence
change approval ref
Result / status (Pass / Fail / N/A / Pending)
Inspector name / role / date
Photo / certificate / report reference
Issue / disposition / recheck evidence and date

## Project setup
Cavoren ITP | Formwork Inspection Checklist
Field | Project entry | Reason / instructions | Source / locator
Project name / contract
Client / principal
Contractor / trade
Jurisdiction / building class
Room / element / zone / lot
Inspection date / time
Checklist issue / revision
Project / contractor
Element / formwork zone
Pour or lot reference
Inspection date
Temporary-works drawing / revision
Formwork system identifier
Required project input |  | Why it is needed
Element, formwork zone, pour/lot and system identifier |  | Makes the inspected assembly/configuration traceable.
Approved temporary-works drawings, system details and revision |  | Defines installed arrangement and inspection basis.
Design assumptions, support evidence and required independent check records |  | Allows checking that documents match visible conditions without recalculating capacity.
Structural/formwork geometry and project dimensional criteria |  | Provides project dimensions and tolerances for measurements.
Current pour method, access/SWMS and change-control procedure |  | Connects inspection to placement, loads, safe access and field-change escalation.
Included scope | Installed formwork and associated falsework for ordinary cast-in-place slabs, pad footings and strip footings, before loading/concrete placement against project temporary-works documents.
Excluded scope | Temporary-works design/capacity calculations, independent design certification, complex suspended falsework, bridges/highways special provisions, jump/slip/travelling forms, major lift design, prestressing, demolition/stripping/load release and whole-pour release.
Use notice | Blank field checklist for project adaptation. Use actual approved documents and project acceptance criteria. Record only observations made. This is not design approval, a temporary-works certificate, contractual Hold/Witness Point release, or permission to place, strip or load.
How to use
1 | Define assembly boundary and gather controlled drawings, system instructions, structural interfaces, pour method and safety plan.
2 | Inspect installed configuration and interfaces at work location; record component IDs and measurements against cited documents.
3 | Keep design/check evidence separate from observations; do not infer capacity visually.
4 | If system, support, loading, geometry or access differs from documents, identify change and refer under project change control.
5 | Transfer any release decision to assigned authority and contractual ITP; this checklist does not authorize stripping.
Source title | Role and limits | URL | Locator
Cavoren cast-in-place concrete baseline | Topic and sequence context only; not a project specification or independent technical authority. | https://itp.cavoren.net/templates/concrete/ | Original proposed concrete baseline rows CON-01 to CON-08
Queensland TMR MRTS70 Concrete, July 2022 | Topic guidance only for concrete/formwork interface. Queensland transport/infrastructure contract criteria are not universal building requirements. | https://www.tmr.qld.gov.au/_/media/busind/techstdpubs/specifications-and-drawings/specifications/2-bridges-and-structures/mrts70.pdf?extension=pdf&hash=BD4A48371C386F32622F6862572AA56A&rev=24517261eac44ddb86310c7980172050&sc_lang=en&size=1730809 | Sections 15.5–15.9 (formwork/falsework, reinforcement, placement/compaction, early loading).
Safe Work Australia, Guide to formwork, July 2014 | Safety interface guidance only. It does not replace temporary-works design, project acceptance criteria, jurisdiction-specific WHS advice or release. | https://www.safeworkaustralia.gov.au/system/files/documents/1703/guide-formwork.pdf | PDF pages 1–4: formwork/falsework definitions, Design, formwork drawings, system components, erection/use safety and access prompts.

## Issues and handover
Formwork Inspection Checklist ¦ Issues and handover
Project | Location / area | Issue date | Open item reference | Person / role
Item ID / date | Affected location and issue | Immediate action / disposition | Recheck evidence / date | Responsible person / role
Formwork inspection handover | Field inspection handover status | Select one status only
[ ] Field observations recorded
[ ] Action / recheck outstanding
[ ] Temporary-works review required
Decision boundary | This records the field inspection handover only. It is not design certification, authorization to pour, a Hold Point release, or permission to strip/load. Transfer the completed inspection and outstanding issues to the project-assigned temporary-works/project release process.
Handover role | Field inspector name / role / date
Handover role | Receiving temporary-works or project role / date
Handover role | Open design query, NCR or change approval reference
Field inspector | Role / record field | Entry / reference
Field inspector name/role/date
Formwork zone/system and inspected configuration
Observed condition, measurements and evidence refs
Design check record | Role / record field | Entry / reference
Temporary-works design and revision
Designer and independent checker roles/identities
Design assumptions and support evidence references
Written change reassessment/approval reference
Project release / handover | Role / record field | Entry / reference
Project/temporary-works release role assigned by contract
Decision scope and stage
Decision status and conditions
Date/time and ITP/control-point/notice reference
Role boundary | Field inspector records installed condition. Designer/checker owns design and required independent check; project role owns release. The checklist cannot certify capacity, alter design, release a Hold Point, or authorize placement, stripping or loading.
Signature note | Signatures record the named person’s stated role and entry only. They do not by themselves approve design, certify compliance, release a contractual control point or authorize the next activity.