## ITP document register
ITP document register
Index controlled ITP documents and revisions required by the project. Each row points to a source file. Record status and supersession only from the document-control process; an index entry does not approve the ITP.
Package / area | ITP ID / title | Revision / issue date | Document status / source | Owner / reviewer | Controlled file location | Superseded by / review reference

## Field record
Check ID | Check, observation and method | Specific record field | Project criterion / source document and revision | Actual record / issue / evidence
REG-01 | Register basis and document control What to observe: Identify the contract quality and document-control sources governing this register. How to check: Record approved quality plan and ITP revisions, register owner, numbering convention, document repository, status vocabulary and any contract handover schedule. Acceptance basis: The register basis is traceable to current project-controlled sources. A sample clause or external guide is not substituted for the actual contract. Reference to confirm: Executed contract and amendments, approved quality plan, document-control procedure and current ITP index. | Contract / package reference
Quality plan / revision
ITP list / revisions
Register owner / role
Document-control procedure
Handover schedule / revision
Workflow stage / action status (project-defined)
Entry by / role / date
Supporting record / evidence reference
Next action / linked issue or separate release reference
REG-02 | Requirement and checkpoint mapping What to observe: Link each required checkpoint to the source requirement, ITP and defined project record. How to check: Index the requirement clause or drawing detail, ITP item and record identifier. Enter Hold, Witness, Review or other checkpoint terms only where the project assigns them. Acceptance basis: The mapping uses the controlled project wording and revision. The register does not create acceptance criteria, notice periods, a checkpoint type or an authority. Reference to confirm: Current contract specifications, approved drawings, submittals and ITPs. | Requirement / clause / drawing detail
Source revision
ITP ID / item
Checkpoint type exactly as assigned
Project record ID
Required notice / source
Workflow stage / action status (project-defined)
Entry by / role / date
Supporting record / evidence reference
Next action / linked issue or separate release reference
REG-03 | Assigned people and planned notices What to observe: Record project-assigned inspection roles and actual notice obligations without implying the event occurred. How to check: Link named roles to the contract or ITP and record planned dates or notice details only when the project schedule provides them. Record sent notices in the event history with their real reference and timestamp. Acceptance basis: The planned requirement and actual notification evidence remain distinct. No witness attendance or notice compliance is inferred from an assigned role. Reference to confirm: Project ITP, communication procedure, contract notice clauses and actual notice records. | Assigned inspector / role
Client / verifier role if required
Project notice period / source
Planned event date / basis
Actual notice reference / date
Attendance / response evidence
Workflow stage / action status (project-defined)
Entry by / role / date
Supporting record / evidence reference
Next action / linked issue or separate release reference
REG-04 | Actual inspection and test records What to observe: Index an inspection or test only when its underlying project record exists. How to check: Record the actual record ID, date, location or lot, issuer, method and source acceptance reference. Link the signed or issued report, instrument output, material certificate or photo only where the project requires it. Acceptance basis: The register stores evidence references and actual status supplied by the source record. It does not calculate or assign Pass, Fail, N/A or test acceptance. Reference to confirm: Approved ITP, applicable project method and original inspection/test report or certificate. | Inspection / report ID and revision
Actual date / time / location
Issuer / role
Method and acceptance source
Actual result copied with source
Evidence file / controlled location
Workflow stage / action status (project-defined)
Entry by / role / date
Supporting record / evidence reference
Next action / linked issue or separate release reference
REG-05 | Material and supplier records What to observe: Index material and supplier records required by the project for the relevant work lot. How to check: Link certificates, delivery records, product data, approvals and batch/heat/serial identifiers to the actual location or asset where required. Confirm document identity and status in the controlled repository. Acceptance basis: Only records required by the project and actually supplied or issued are indexed. A listed certificate does not by itself approve design or prove installation conformity. Reference to confirm: Project specification, approved submittals, procurement/traceability process and source supplier records. | Product / material / supplier
Batch / heat / serial / lot
Required certificate / submittal
Actual document ID / revision
Mapped area / installed quantity
Review / status source
Workflow stage / action status (project-defined)
Entry by / role / date
Supporting record / evidence reference
Next action / linked issue or separate release reference
REG-06 | NCR, action and recheck links What to observe: Link a nonconformance and its later records without treating an NCR closeout as an inspection result or release. How to check: Record the NCR ID, affected lots, authorised disposition, actual action evidence, recheck record and separate open conditions from the source records. Acceptance basis: NCR status is copied from its authorised record. Any ITP checkpoint, concealment or contractual release remains a separate status and decision. Reference to confirm: Project NCR procedure, issued disposition, recheck record and contract/ITP release requirements. | NCR ID / revision
Affected lot / checkpoint
Disposition authority / reference
Action evidence / date
Recheck source / actual status
Separate release status / reference
Workflow stage / action status (project-defined)
Entry by / role / date
Supporting record / evidence reference
Next action / linked issue or separate release reference
REG-07 | Conformity record index What to observe: Index final records and source documents required by the actual contract handover schedule. How to check: Link issued as-executed information, O&M manuals, test reports, material records, notices, certifications and other applicable records to the project schedule and controlled file location. Acceptance basis: The register points to the source file and its actual revision/status. It is not a substitute for the original evidence or proof that every project-required document has been accepted. Reference to confirm: Executed contract handover requirements, controlled dossier index and source document register. | Handover item / contract source
Required document / owner
Actual file / record ID
Revision / issue date
Controlled repository path
Review / acceptance reference if required
Workflow stage / action status (project-defined)
Entry by / role / date
Supporting record / evidence reference
Next action / linked issue or separate release reference
REG-08 | Separate release and handover review What to observe: Record the actual project release and handover decisions in their designated records. How to check: Identify outstanding checkpoints and document conditions. Link the named authorised decision maker, decision, date, scope, conditions and separate record reference for any release or handover review. Acceptance basis: A populated register does not establish compliance, completion, formal release or accepted handover. Those statuses require their own project evidence and authority. Reference to confirm: Contract, approved ITP, hold-point/notice process, release instruction and handover review record. | Open checkpoint / issue
Required outstanding document
Release authority / source
Actual release decision / reference
Handover review / decision reference
Conditions / follow-up owner
Workflow stage / action status (project-defined)
Entry by / role / date
Supporting record / evidence reference
Next action / linked issue or separate release reference

## Project setup
Cavoren quality record | Construction ITP Inspection and Quality Records Register
Field | Project entry | Reason / instructions | Source / locator
Project name / contract
Client / principal
Contractor / trade
Jurisdiction / building class
Room / element / zone / lot
Inspection date / time
Checklist issue / revision
Project / contract / principal
Package / trade / contractor
Register owner / role
Register issue / revision / date
Contract quality plan / ITP source and revision
Record naming / document control procedure
Project handover or dossier index reference
Required project input |  | Why it is needed
Current contract, specification, approved drawings and ITPs |  | Use project-controlled sources to define the required checks, acceptance basis, notice rules, checkpoint type and release authority. This register supplies none of those requirements.
Project document numbering and retention rules |  | Confirm record IDs, revisions, status terms, file location, required metadata, retention period and dossier format from the contract and document control procedure.
Actual inspection, test and material evidence |  | Index source records that exist, including reports, certificates, photos or supplier records where required. An index row does not reproduce or verify its source document.
Issue, recheck and NCR references |  | Link unresolved findings and later evidence to the applicable NCR or corrective-action record. NCR closure does not itself close a separate ITP or contract release.
Separate release and handover requirements |  | Identify project-assigned release and handover roles, required decision records and outstanding conditions. Do not infer release or handover acceptance from a populated index.
Included scope | Cross-trade register structure for identifying controlled requirements, ITP checkpoints, responsible and notified roles, actual inspection or test record references, open issues, evidence and separately documented completion, release and handover status. Each row is an index entry, not a substitute for the underlying evidence.
Excluded scope | Creating project acceptance criteria, selecting standards or test methods, deciding whether an inspection passes, recording work that did not occur, approving a hold-point release, certifying compliance, or replacing the contract, approved ITP, test report, NCR, as-built drawing, certificate or O&M document.
Use notice | Blank register. Populate it from the current controlled project documents and the project records actually created. Every status, date, result, role and document reference remains blank until evidenced. NCR closure, inspection result, contractual release and dossier/handover completeness are distinct fields and decisions. A complete index does not establish that indexed work complies.
How to use
1 | Create the register from the current contract, approved quality plan, ITPs and document-control procedure. Record each source revision and its project owner.
2 | Use a stable project record identifier for each requirement or checkpoint and retain its link to the controlling clause, drawing, ITP and applicable location or lot.
3 | Record checkpoint type and notice arrangements exactly as assigned in project documents. Enter planned requirements separately from an actual inspection or test result.
4 | Add actual events only after they occur. Link the result, inspector, date, evidence file and any NCR or recheck to the underlying record. Leave unknown, future and incomplete events blank or use the project-defined pending term.
5 | Index source documents with their actual title, revision, date, author or issuer, status and controlled location. The index is a navigation aid; preserve each original report or evidence file.
6 | Track action status, inspection result, NCR closure, contractual release and handover completeness in their own fields. Use only the authority and status definitions established by the project.
7 | Reconcile the register against the contract handover schedule and project document-control process before a responsible project reviewer records completion.
Source title | Role and limits | URL | Locator
NSW Government, Quality management guidelines for construction | Official NSW Government construction procurement guidance. The page describes NSW Government project scope and gives examples of quality-plan, ITP, nonconformity, document-control, register and handover record interfaces. Its sample GC21 clauses are not universal requirements and apply only when adopted by a project's actual contract. The linked Appendix D ITP DOCX was not readable in the source check, so no claim about its detailed contents is made. | https://www.info.buy.nsw.gov.au/resources/construction/quality-management-guidelines-for-construction | Use the page headings “Scope and purpose” and “Contents of a quality management plan” for NSW Government context, quality-plan content and record management. Under the sample contract clauses, see the GC21 examples concerning quality records, conformity registers, nonconforming work and handover. These examples are NSW/GC21-specific and apply only when adopted by the project contract. Appendix D is linked on the page, but its DOCX body was not verified.

## Issues and handover
Construction ITP Inspection and Quality Records Register ¦ Issues and handover
Project | Location / area | Issue date | Open item reference | Person / role
Item ID / date | Affected location and issue | Immediate action / disposition | Recheck evidence / date | Responsible person / role
Register and dossier review | Register review status | Select one status only
[ ] Records being compiled
[ ] Project review or source record outstanding
[ ] Index reviewed under the project process
Decision boundary | Choose only the state evidenced by the project process. Index review does not establish compliance, approve an inspection result, close an NCR or make a contractual release decision.
Handover role | Register owner / role / revision
Handover role | Source record reviewer / reference
Handover role | NCR and action owner / status source
Handover role | Release authority / separate record
Handover role | Handover reviewer / decision and conditions
Signature note | Signatures record the named person’s stated role and entry only. They do not by themselves approve design, certify compliance, release a contractual control point or authorize the next activity.

## Event log
Actual inspection and record events
Add an entry only after the inspection, test, notice, record issue or review occurs. Link it to the controlling ITP and underlying record. A blank row is not a planned or completed event.
Project / contract |  |  | Element / pour / lot |  |  |  | Date / shift
Date / time | ITP ID / revision / checkpoint | Location / lot | Event type / source | Inspector / issuer / role | Actual result / status source | Report / evidence ID | Issue / release / handover link