## ITP
piping-plumbing-itp-template ¦ Inspection and Test Plan
[Fill: project name] ¦ Building Plumbing ITP — Water, Sanitary and Stormwater (Editable Baseline) — free editable baseline ¦ [Fill: Australian state/territory] ¦ Rev 00 ¦ 2026-10-06 ¦ For review Contractor: [Fill: contractor] Client: [Fill: client] Scope: Original reusable baseline for conventional building cold/hot water, sanitary plumbing/drainage and stormwater where each is selected. Rows identify conditional services separately. Excludes gas, process/high-pressure pipework, fire services, HVAC/refrigerant, pools, onsite wastewater and industrial systems. Test regimes must be confirmed per jurisdiction, actual project-adopted standards and system; no default pressure/test duration is supplied. This is a free, editable, proposed baseline and is not tailored to a project, approved by a client, or evidence of completed inspection. Before use, complete the scope questions and bracketed fields, confirm every criterion and control against current project documents, and remove non-applicable rows. Exclusions: Confirm exclusions for this project; use the scope notes above.
ID | Stage | Inspection / test | Method | Acceptance requirement | Reference | Frequency | Responsible role | Point | Approval / witness party | Notice / release | Record | Remarks
PL01 | Scope and service classification | Proposed: baseline — Identify each system/medium, boundaries and excluded work. | Proposed: baseline — Review plans, scope, schedules and design notes; classify water, sanitary, stormwater and heated-water systems separately. | Proposed: baseline — Only specified systems [Fill: Included plumbing services] are included; process, gas, high-pressure, fire, HVAC/refrigerant, pool and on-site wastewater systems are excluded unless individually scoped. | Guidance only; see Source Register: NCC22-V3, ABCB-PCA-INTRO | Proposed: Once before work and when scope changes. | Proposed: licensed plumbing contractor/design reviewer. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Plumbing scope and system register | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
PL02 | Regulatory basis and approvals | Proposed: baseline — Confirm jurisdiction, applicable NCC Volume Three edition/state variations, licensing and inspection/notification pathway. | Proposed: baseline — Review regulatory authority guidance, approvals, project specification and adopted document register. | Proposed: baseline — Current applicable jurisdiction, approved pathway, inspection/notification roles and adopted editions are recorded; conflicts raised. | Guidance only; see Source Register: NCC22-V3, ABCB-PCA-INTRO | Proposed: Before work; update on regulatory/approved revision. | Proposed: Plumbing contractor and builder/design reviewer. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Plumbing regulatory and approvals register | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
PL03 | Material and product approval | Proposed: baseline — Check pipe/fitting material, class/type, joint system, potable water suitability and product certification where applicable. | Proposed: baseline — Inspect labels/certificates and compare with approved submittal/specification and applicable WaterMark requirements. | Proposed: baseline — Products match approved schedule [Fill: Pipe/fitting/product schedule] and required approvals/evidence for their intended service; drinking-water contact suitability is documented where required. | Guidance only; see Source Register: NCC22-V3, NCC22-REFDOCS | Proposed: Each delivery/product type and substitution. | Proposed: licensed plumbing contractor submits; reviewer approves. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Plumbing products register | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
PL04 | Delivery and storage | Proposed: baseline — Inspect received materials for identity, damage, cleanliness, contamination and storage protection. | Proposed: baseline — Visual inspection and trace labels/batches against product submittal; maintain caps/protection as required. | Proposed: baseline — Correct approved items are traceable, undamaged and kept clean/protected per manufacturer instructions [Fill: Pipe/fitting/product schedule]. | Guidance only; see Source Register: CQA-ITP | Proposed: Each delivery/batch. | Proposed: plumbing contractor. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Plumbing delivery and traceability log | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
PL05 | Set-out and service coordination | Proposed: baseline — Check service route, levels, fixture/equipment connections, penetrations and clashes. | Proposed: baseline — Compare marked-out installation to coordinated drawings and surveyed levels; resolve clashes before fixing/covering. | Proposed: baseline — Routes, invert/connection levels and service points match approved drawings [Fill: Approved plumbing drawings]; unresolved clashes have approved resolution. | Guidance only; see Source Register: NCC22-V3 | Proposed: Each zone/floor before installation. | Proposed: plumbing contractor; builder coordinates. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Plumbing set-out and coordination check | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
PL06 | Trench, bedding and support | Proposed: baseline — For buried runs, check trench condition, bedding, support, depth/cover and protection; for above-ground, check supports and movement provisions. | Proposed: baseline — Inspect before laying and before cover; measure against approved details and the relevant adopted standard/project criteria. | Proposed: baseline — Bedding/support, depth, cover, spacing and movement provisions meet approved detail [Fill: Approved plumbing drawings] and criteria [Fill: Specification and adopted standards]; no values assumed. | Guidance only; see Source Register: NCC22-V3, NCC22-REFDOCS | Proposed: Each run/section before pipe placement or concealment. | Proposed: licensed plumbing contractor. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Trench and pipe support checklist | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
PL07 | Pipework installation and identification | Proposed: baseline — Inspect pipe type/diameter, route, gradient where relevant, jointing, supports, isolation/access and identification. | Proposed: baseline — Visual and measured checks against isometrics, schedule, manufacturer jointing instructions and adopted standard. | Proposed: baseline — Installed pipework, gradient, joints, access and identification match approved documents [Fill: Approved plumbing drawings]/[Fill: Specification and adopted standards]; system is clearly identified by service. | Guidance only; see Source Register: NCC22-V3, NCC22-REFDOCS | Proposed: Each service run before concealment. | Proposed: Licensed plumbing contractor. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Pipe installation checklist | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
PL08 | Jointing and workmanship | Proposed: baseline — Check joint preparation, assembly, welding/brazing/solvent process only for the specified material/system. | Proposed: baseline — Observe installer qualification where specified; check process parameters and joint records required by product/project instructions. | Proposed: baseline — Joint type and workmanship follow approved method [Fill: Pipe/fitting/product schedule] and manufacturer/project criteria; required qualification/evidence is current. | Guidance only; see Source Register: CQA-ITP | Proposed: Each joint batch/lot and visual check along completed run. | Proposed: Licensed plumbing contractor; qualified specialist if project requires. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Jointing and workmanship record | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
PL09 | Valves, fixtures and backflow interfaces | Proposed: baseline — Verify valve type/location/access, fixture connections, backflow device and cross-connection protections if in scope. | Proposed: baseline — Compare to approved schedules and NCC/project hazard assessment; record device identification and certificates where required. | Proposed: baseline — Devices and interfaces match approved design [Fill: Approved plumbing drawings] and applicable project/jurisdictional requirements; missing hazard assessment is referred for resolution. | Guidance only; see Source Register: NCC22-V3, NCC22-REFDOCS | Proposed: Each device/fixture or assembly. | Proposed: Licensed plumbing contractor; authorised tester for device tests if required. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Valve, fixture and backflow register | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
PL10 | Sanitary drainage alignment and falls | Proposed: baseline — Inspect sanitary drain route, grade, connections, access openings and cleanouts before backfill. | Proposed: baseline — Check against approved drainage plan and levels; use survey/measurement method specified by project. | Proposed: baseline — Alignment, gradient, invert and access match approved design [Fill: Approved plumbing drawings] and adopted criteria [Fill: Specification and adopted standards]; record actual levels where required. | Guidance only; see Source Register: NCC22-V3, WA-BULLETIN-133 | Proposed: Each drain run before testing/backfill. | Proposed: Licensed plumber/drainer. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Sanitary drainage pre-cover checklist | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
PL11 | Sanitary pipe test before backfill | Proposed: baseline — For sanitary plumbing/drainage, perform only the applicable jurisdiction/project test before concealment. | Proposed: baseline — Licensed plumber/drainer confirms adopted standard edition, system boundaries, test medium, pressure/head and duration; record results. | Proposed: baseline — Test meets confirmed project/jurisdiction criteria [Fill: Sanitary test method and criteria]; defects repaired and section retested before backfill. WA bulletin illustrates local methods, not national default criteria. | Guidance only; see Source Register: WA-BULLETIN-133, NCC22-REFDOCS | Proposed: Each defined test section before backfill/cover. | Proposed: Licensed plumber/drainer; authority/client witness only where required. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Sanitary pipe test record | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
PL12 | Water service pressure/leak test | Proposed: baseline — Test water services using the method and criteria approved for the project and jurisdiction. | Proposed: baseline — Licensed plumber confirms isolated section, test medium, pressure/duration and acceptance source; record actual readings, instrument and observations. | Proposed: baseline — No leakage or pressure change beyond confirmed applicable criterion [Fill: Water-service test method and criteria]; no preset national pressure/duration is assumed. | Guidance only; see Source Register: NCC22-V3, NCC22-REFDOCS | Proposed: Each defined water service section before concealment/commissioning. | Proposed: Licensed plumbing contractor. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Water service pressure test record | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
PL13 | Stormwater drainage (conditional) | Proposed: baseline — Where included, check stormwater pipe, pits, inlets, gradients, connections and discharge points. | Proposed: baseline — Inspect route/levels and compare to approved stormwater plan, civil interface and applicable adopted requirements. | Proposed: baseline — Installed system and discharge path match approved drawings [Fill: Approved plumbing drawings] and project criteria [Fill: Specification and adopted standards]; no sanitary test rule applied by assumption. | Guidance only; see Source Register: NCC22-V3, NCC22-REFDOCS | Proposed: Each run/pit/outfall before cover and at completion. | Proposed: plumbing contractor/civil contractor per scope. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Stormwater installation checklist | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
PL14 | Heated water service (conditional) | Proposed: baseline — Where included, check heater/system connections, relief/tempering components, discharge and access. | Proposed: baseline — Inspect against approved design, equipment instructions and adopted heated-water requirements. | Proposed: baseline — Equipment, safety components, connection/discharge and settings meet approved schedule [Fill: Approved plumbing drawings]/[Fill: Specification and adopted standards]; record settings only from approved source. | Guidance only; see Source Register: NCC22-V3, NCC22-REFDOCS | Proposed: Each heater/system before commissioning. | Proposed: Licensed plumbing contractor; electrical trade interface separate. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Heated water installation checklist | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
PL15 | Flushing, cleaning and disinfection (conditional) | Proposed: baseline — Where required for drinking water, confirm flushing, disinfection and any specified water quality evidence. | Proposed: baseline — Follow project-approved procedure and applicable authority/manufacturer requirements; use competent authorised person. | Proposed: baseline — Required flushing/disinfection steps and any specified sample results meet project/jurisdiction criteria [Fill: Flushing/disinfection requirements]; no unsupported universal chlorination value. | Guidance only; see Source Register: NCC22-V3 | Proposed: Each system/zone where required before use. | Proposed: Licensed plumbing contractor; laboratory/person as required. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Water service flushing/disinfection record | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
PL16 | Pre-cover inspection and backfill | Proposed: baseline — Walk down installed services and confirm testing/photographs/authority inspections before covering. | Proposed: baseline — Check inspection checklist, test evidence, utility/authority notices, service marking and approved backfill requirements. | Proposed: baseline — All required pre-cover checks are complete; identified defects are closed and required authority release is documented [Fill: Concealment/backfill release]. | Guidance only; see Source Register: WA-BULLETIN-133, CQA-ITP | Proposed: Each trench/shaft/ceiling area before concealment. | Proposed: Licensed plumber/drainer; builder coordinates; authority as required. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Pre-cover and backfill release checklist | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
PL17 | Commissioning and operational checks | Proposed: baseline — Verify specified flow, operation, fixture discharge, leaks and system interfaces. | Proposed: baseline — Commission by licensed plumbing practitioner under approved procedure; record measured results and exceptions by system. | Proposed: baseline — Specified operational criteria in [Fill: Specification and adopted standards] are satisfied; defects are corrected and retested; no generic flow/pressure figures assumed. | Guidance only; see Source Register: NCC22-V3, ABCB-PCA-INTRO | Proposed: Each system/zone at commissioning. | Proposed: Licensed plumbing contractor; client/operator witness if required. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Plumbing commissioning record | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
PL18 | Defects and retest | Proposed: baseline — Record leaks, blockages, incorrect levels, joint failures and corrective work. | Proposed: baseline — Identify location/system, defect, repair method, retest evidence and closure. | Proposed: baseline — Defects are corrected against approved method and failed tests repeated successfully before cover/use. | Guidance only; see Source Register: CQA-ITP | Proposed: Each defect/retest. | Proposed: Licensed plumbing contractor; reviewer per project. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Plumbing defect and retest register | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
PL19 | As-built and handover | Proposed: baseline — Verify certificates, inspection notices, test reports, product evidence, as-builts and operation/maintenance information. | Proposed: baseline — Review contract/regulator handover index and match records to service IDs/locations. | Proposed: baseline — Required certificates and records are complete for included systems and issued by properly authorised persons; as-builts reflect installed route. | Guidance only; see Source Register: NCC22-V3, CQA-ITP | Proposed: Once per package and after approved changes. | Proposed: Licensed plumbing contractor submits; builder compiles. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Plumbing handover register | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
Point key: H = Proposed Hold Point - use only if assigned in the contract ¦ W = Proposed Witness Point - use only if assigned in the contract ¦ R = Proposed Review ¦ S = Proposed Surveillance ¦ TBC = To be confirmed ¦ N/A = Not applicable. External H/W rights and release rules must come from the project contract and approved process.

## Record Forms
Blank Inspection Record Forms
[Fill: project name] ¦ piping-plumbing-itp-template ¦ Record actual observations during the work. No results or signatures are pre-filled.
ITP ID / Stage | Inspection / method / acceptance | Location / lot | Date and result | Evidence / record ref. | Performed by / signature | Reviewed by / signature
PL01 ¦ Scope and service classification | Proposed: baseline — Identify each system/medium, boundaries and excluded work. Method: Proposed: baseline — Review plans, scope, schedules and design notes; classify water, sanitary, stormwater and heated-water systems separately. Accept when: Proposed: baseline — Only specified systems [Fill: Included plumbing services] are included; process, gas, high-pressure, fire, HVAC/refrigerant, pool and on-site wastewater systems are excluded unless individually scoped. Record: Plumbing scope and system register |  | Date: __________ Actual result/observation: __________ Evidence/photo/report reference: __________ Result / disposition: __________ Corrective action / retest ref.: __________
PL02 ¦ Regulatory basis and approvals | Proposed: baseline — Confirm jurisdiction, applicable NCC Volume Three edition/state variations, licensing and inspection/notification pathway. Method: Proposed: baseline — Review regulatory authority guidance, approvals, project specification and adopted document register. Accept when: Proposed: baseline — Current applicable jurisdiction, approved pathway, inspection/notification roles and adopted editions are recorded; conflicts raised. Record: Plumbing regulatory and approvals register |  | Date: __________ Actual result/observation: __________ Evidence/photo/report reference: __________ Result / disposition: __________ Corrective action / retest ref.: __________
PL03 ¦ Material and product approval | Proposed: baseline — Check pipe/fitting material, class/type, joint system, potable water suitability and product certification where applicable. Method: Proposed: baseline — Inspect labels/certificates and compare with approved submittal/specification and applicable WaterMark requirements. Accept when: Proposed: baseline — Products match approved schedule [Fill: Pipe/fitting/product schedule] and required approvals/evidence for their intended service; drinking-water contact suitability is documented where required. Record: Plumbing products register |  | Date: __________ Actual result/observation: __________ Evidence/photo/report reference: __________ Result / disposition: __________ Corrective action / retest ref.: __________
PL04 ¦ Delivery and storage | Proposed: baseline — Inspect received materials for identity, damage, cleanliness, contamination and storage protection. Method: Proposed: baseline — Visual inspection and trace labels/batches against product submittal; maintain caps/protection as required. Accept when: Proposed: baseline — Correct approved items are traceable, undamaged and kept clean/protected per manufacturer instructions [Fill: Pipe/fitting/product schedule]. Record: Plumbing delivery and traceability log |  | Date: __________ Actual result/observation: __________ Evidence/photo/report reference: __________ Result / disposition: __________ Corrective action / retest ref.: __________
PL05 ¦ Set-out and service coordination | Proposed: baseline — Check service route, levels, fixture/equipment connections, penetrations and clashes. Method: Proposed: baseline — Compare marked-out installation to coordinated drawings and surveyed levels; resolve clashes before fixing/covering. Accept when: Proposed: baseline — Routes, invert/connection levels and service points match approved drawings [Fill: Approved plumbing drawings]; unresolved clashes have approved resolution. Record: Plumbing set-out and coordination check |  | Date: __________ Actual result/observation: __________ Evidence/photo/report reference: __________ Result / disposition: __________ Corrective action / retest ref.: __________
PL06 ¦ Trench, bedding and support | Proposed: baseline — For buried runs, check trench condition, bedding, support, depth/cover and protection; for above-ground, check supports and movement provisions. Method: Proposed: baseline — Inspect before laying and before cover; measure against approved details and the relevant adopted standard/project criteria. Accept when: Proposed: baseline — Bedding/support, depth, cover, spacing and movement provisions meet approved detail [Fill: Approved plumbing drawings] and criteria [Fill: Specification and adopted standards]; no values assumed. Record: Trench and pipe support checklist |  | Date: __________ Actual result/observation: __________ Evidence/photo/report reference: __________ Result / disposition: __________ Corrective action / retest ref.: __________
PL07 ¦ Pipework installation and identification | Proposed: baseline — Inspect pipe type/diameter, route, gradient where relevant, jointing, supports, isolation/access and identification. Method: Proposed: baseline — Visual and measured checks against isometrics, schedule, manufacturer jointing instructions and adopted standard. Accept when: Proposed: baseline — Installed pipework, gradient, joints, access and identification match approved documents [Fill: Approved plumbing drawings]/[Fill: Specification and adopted standards]; system is clearly identified by service. Record: Pipe installation checklist |  | Date: __________ Actual result/observation: __________ Evidence/photo/report reference: __________ Result / disposition: __________ Corrective action / retest ref.: __________
PL08 ¦ Jointing and workmanship | Proposed: baseline — Check joint preparation, assembly, welding/brazing/solvent process only for the specified material/system. Method: Proposed: baseline — Observe installer qualification where specified; check process parameters and joint records required by product/project instructions. Accept when: Proposed: baseline — Joint type and workmanship follow approved method [Fill: Pipe/fitting/product schedule] and manufacturer/project criteria; required qualification/evidence is current. Record: Jointing and workmanship record |  | Date: __________ Actual result/observation: __________ Evidence/photo/report reference: __________ Result / disposition: __________ Corrective action / retest ref.: __________
PL09 ¦ Valves, fixtures and backflow interfaces | Proposed: baseline — Verify valve type/location/access, fixture connections, backflow device and cross-connection protections if in scope. Method: Proposed: baseline — Compare to approved schedules and NCC/project hazard assessment; record device identification and certificates where required. Accept when: Proposed: baseline — Devices and interfaces match approved design [Fill: Approved plumbing drawings] and applicable project/jurisdictional requirements; missing hazard assessment is referred for resolution. Record: Valve, fixture and backflow register |  | Date: __________ Actual result/observation: __________ Evidence/photo/report reference: __________ Result / disposition: __________ Corrective action / retest ref.: __________
PL10 ¦ Sanitary drainage alignment and falls | Proposed: baseline — Inspect sanitary drain route, grade, connections, access openings and cleanouts before backfill. Method: Proposed: baseline — Check against approved drainage plan and levels; use survey/measurement method specified by project. Accept when: Proposed: baseline — Alignment, gradient, invert and access match approved design [Fill: Approved plumbing drawings] and adopted criteria [Fill: Specification and adopted standards]; record actual levels where required. Record: Sanitary drainage pre-cover checklist |  | Date: __________ Actual result/observation: __________ Evidence/photo/report reference: __________ Result / disposition: __________ Corrective action / retest ref.: __________
PL11 ¦ Sanitary pipe test before backfill | Proposed: baseline — For sanitary plumbing/drainage, perform only the applicable jurisdiction/project test before concealment. Method: Proposed: baseline — Licensed plumber/drainer confirms adopted standard edition, system boundaries, test medium, pressure/head and duration; record results. Accept when: Proposed: baseline — Test meets confirmed project/jurisdiction criteria [Fill: Sanitary test method and criteria]; defects repaired and section retested before backfill. WA bulletin illustrates local methods, not national default criteria. Record: Sanitary pipe test record |  | Date: __________ System/section ID: __________ Hydrostatic/air/vacuum/other: __________ Test medium: __________ Head/pressure applied: __________ Unit: __________ Stabilisation time: __________ Test duration: __________ Start reading/time: __________ End reading/time: __________ Leak/pressure change observed: __________ Instrument ID/calibration: __________ Pass/fail/exception: __________ Repair/retest reference: __________ Result / disposition: __________ Corrective action / retest ref.: __________
PL12 ¦ Water service pressure/leak test | Proposed: baseline — Test water services using the method and criteria approved for the project and jurisdiction. Method: Proposed: baseline — Licensed plumber confirms isolated section, test medium, pressure/duration and acceptance source; record actual readings, instrument and observations. Accept when: Proposed: baseline — No leakage or pressure change beyond confirmed applicable criterion [Fill: Water-service test method and criteria]; no preset national pressure/duration is assumed. Record: Water service pressure test record |  | Date: __________ System/section ID: __________ Test method/reference: __________ Test medium: __________ Test pressure: __________ Unit: __________ Duration: __________ Start reading/time: __________ End reading/time: __________ Leak observation: __________ Instrument ID/calibration: __________ Pass/fail/exception: __________ Repair/retest reference: __________ Result / disposition: __________ Corrective action / retest ref.: __________
PL13 ¦ Stormwater drainage (conditional) | Proposed: baseline — Where included, check stormwater pipe, pits, inlets, gradients, connections and discharge points. Method: Proposed: baseline — Inspect route/levels and compare to approved stormwater plan, civil interface and applicable adopted requirements. Accept when: Proposed: baseline — Installed system and discharge path match approved drawings [Fill: Approved plumbing drawings] and project criteria [Fill: Specification and adopted standards]; no sanitary test rule applied by assumption. Record: Stormwater installation checklist |  | Date: __________ Actual result/observation: __________ Evidence/photo/report reference: __________ Result / disposition: __________ Corrective action / retest ref.: __________
PL14 ¦ Heated water service (conditional) | Proposed: baseline — Where included, check heater/system connections, relief/tempering components, discharge and access. Method: Proposed: baseline — Inspect against approved design, equipment instructions and adopted heated-water requirements. Accept when: Proposed: baseline — Equipment, safety components, connection/discharge and settings meet approved schedule [Fill: Approved plumbing drawings]/[Fill: Specification and adopted standards]; record settings only from approved source. Record: Heated water installation checklist |  | Date: __________ Heater make/model: __________ Serial number: __________ Recorded setting: __________ Unit: __________ Discharge check/reference: __________ Commissioning record: __________ Result / disposition: __________ Corrective action / retest ref.: __________
PL15 ¦ Flushing, cleaning and disinfection (conditional) | Proposed: baseline — Where required for drinking water, confirm flushing, disinfection and any specified water quality evidence. Method: Proposed: baseline — Follow project-approved procedure and applicable authority/manufacturer requirements; use competent authorised person. Accept when: Proposed: baseline — Required flushing/disinfection steps and any specified sample results meet project/jurisdiction criteria [Fill: Flushing/disinfection requirements]; no unsupported universal chlorination value. Record: Water service flushing/disinfection record |  | Date: __________ System/zone: __________ Procedure/reference: __________ Date/time: __________ Water source: __________ Sample ID: __________ Laboratory: __________ Result: __________ Criterion source/location: __________ Result / disposition: __________ Corrective action / retest ref.: __________
PL16 ¦ Pre-cover inspection and backfill | Proposed: baseline — Walk down installed services and confirm testing/photographs/authority inspections before covering. Method: Proposed: baseline — Check inspection checklist, test evidence, utility/authority notices, service marking and approved backfill requirements. Accept when: Proposed: baseline — All required pre-cover checks are complete; identified defects are closed and required authority release is documented [Fill: Concealment/backfill release]. Record: Pre-cover and backfill release checklist |  | Date: __________ Actual result/observation: __________ Evidence/photo/report reference: __________ Result / disposition: __________ Corrective action / retest ref.: __________
PL17 ¦ Commissioning and operational checks | Proposed: baseline — Verify specified flow, operation, fixture discharge, leaks and system interfaces. Method: Proposed: baseline — Commission by licensed plumbing practitioner under approved procedure; record measured results and exceptions by system. Accept when: Proposed: baseline — Specified operational criteria in [Fill: Specification and adopted standards] are satisfied; defects are corrected and retested; no generic flow/pressure figures assumed. Record: Plumbing commissioning record |  | Date: __________ Actual result/observation: __________ Evidence/photo/report reference: __________ Result / disposition: __________ Corrective action / retest ref.: __________
PL18 ¦ Defects and retest | Proposed: baseline — Record leaks, blockages, incorrect levels, joint failures and corrective work. Method: Proposed: baseline — Identify location/system, defect, repair method, retest evidence and closure. Accept when: Proposed: baseline — Defects are corrected against approved method and failed tests repeated successfully before cover/use. Record: Plumbing defect and retest register |  | Date: __________ Actual result/observation: __________ Evidence/photo/report reference: __________ Result / disposition: __________ Corrective action / retest ref.: __________
PL19 ¦ As-built and handover | Proposed: baseline — Verify certificates, inspection notices, test reports, product evidence, as-builts and operation/maintenance information. Method: Proposed: baseline — Review contract/regulator handover index and match records to service IDs/locations. Accept when: Proposed: baseline — Required certificates and records are complete for included systems and issued by properly authorised persons; as-builts reflect installed route. Record: Plumbing handover register |  | Date: __________ Actual result/observation: __________ Evidence/photo/report reference: __________ Result / disposition: __________ Corrective action / retest ref.: __________

## Source Register
Source Register
Source ID | Title | Revision / check | Type | Path / URL
NCC22-V3 | ABCB, NCC 2022 Volume Three (Plumbing Code of Australia) | See linked source; verify current edition and project adoption | guidance | https://ncc.abcb.gov.au/editions/ncc-2022/adopted/volume-three
NCC22-REFDOCS | ABCB, NCC 2022 Volume Three referenced documents | See linked source; verify current edition and project adoption | guidance | https://ncc.abcb.gov.au/editions/ncc-2022/adopted/volume-three/2-referenced-documents/referenced-documents
WA-BULLETIN-133 | WA DMIRS, Industry Bulletin 133: Sanitary plumbing and sanitary drainage installation testing | See linked source; verify current edition and project adoption | guidance | https://www.wa.gov.au/system/files/2024-10/industry_bulletin_133_-_sanitary_plumbing_and_sanitary_drainage_installation.pdf
ABCB-PCA-INTRO | ABCB, NCC Tutor lesson: Using Volume Three | See linked source; verify current edition and project adoption | guidance | https://ncc.abcb.gov.au/resources/videos/ncc-tutor-lesson-using-volume-three
CQA-ITP | Construction Quality Association, Guide: How to create an ITP | See linked source; verify current edition and project adoption | guidance | https://www.cqa.org.au/post/guide-how-to-create-an-inspection-and-test-plan-itp

## Confirmations
Open Confirmations
Issue ID | Priority | ITP rows | Open item | Action needed
CONF-001 | confirmation | PL01 | PL01: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-002 | confirmation | PL02 | PL02: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-003 | confirmation | PL03 | PL03: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-004 | confirmation | PL04 | PL04: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-005 | confirmation | PL05 | PL05: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-006 | confirmation | PL06 | PL06: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-007 | confirmation | PL07 | PL07: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-008 | confirmation | PL08 | PL08: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-009 | confirmation | PL09 | PL09: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-010 | confirmation | PL10 | PL10: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-011 | confirmation | PL11 | PL11: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-012 | confirmation | PL12 | PL12: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-013 | confirmation | PL13 | PL13: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-014 | confirmation | PL14 | PL14: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-015 | confirmation | PL15 | PL15: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-016 | confirmation | PL16 | PL16: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-017 | confirmation | PL17 | PL17: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-018 | confirmation | PL18 | PL18: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-019 | confirmation | PL19 | PL19: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.