## Field record
Check ID | Check, observation and method | Specific record field | Project criterion / source document and revision | Actual record / issue / evidence
RE-01 | Inspection package and reinforcement documents What to observe: Identify element, pour/lot boundaries, current structural drawings, bar schedule, revisions and project inspection/check requirements. How to check: Review the controlled document register against the element and schedule marks at the workface; note superseded or conflicting copies. Acceptance basis: Use current approved project drawings, bar schedule, specification and ITP; record unresolved conflict rather than choosing a revision. Reference to confirm: Controlled document register, approved structural drawings, bar schedule, reinforcement specification and project ITP. | element / grid
drawing / rev
bar schedule / rev
open item ref
Result / status (Pass / Fail / N/A / Pending)
Inspector name / role / date
Photo / certificate / report reference
Issue / disposition / recheck evidence and date
RE-02 | Delivery identity and traceability What to observe: Inspect labels/tags, bundle or mesh marks and delivery documents for identity to scheduled bar marks, product description and source traceability required by the job. How to check: Compare delivered bundles/mesh with schedule and dockets/certificates; link identity to storage location and element allocation. Acceptance basis: Apply only project procurement/specification traceability requirements and scheduled marks; do not impose TMR registration unless adopted by contract. Reference to confirm: Approved bar schedule, material submittal, delivery docket and project traceability requirements. | delivery docket
bundle / bar mark
certificate ref
allocated location
Result / status (Pass / Fail / N/A / Pending)
Inspector name / role / date
Photo / certificate / report reference
Issue / disposition / recheck evidence and date
RE-03 | Storage and visible steel condition What to observe: Observe stacking/separation, ground contact, physical damage, bends/kinks and visible contamination relevant to the specified product. How to check: Walk stock before fixing; inspect representative bundles and suspect bars; photograph defects and identify affected marks. Acceptance basis: Compare with project specification and approved material submittal; seek direction where condition may affect specified use. Reference to confirm: Project reinforcement specification, approved material submittal and written condition disposition. | bar mark / bundle
storage location
condition / photo ref
disposition ref
Result / status (Pass / Fail / N/A / Pending)
Inspector name / role / date
Photo / certificate / report reference
Issue / disposition / recheck evidence and date
RE-04 | Cut, bend and bar-mark conformity What to observe: Compare installed cut/bent shapes, schedule marks and orientation with approved bending/bar schedule, including any project-controlled site re-bending. How to check: Trace selected bars to bending schedule and inspect shape/orientation; review authorization and method for permitted field adjustment. Acceptance basis: Use current approved schedule and project-approved fabrication/adjustment procedure; no generic bend radius, length or tolerance is supplied. Reference to confirm: Approved bar bending schedule and project-approved fabrication or field-adjustment procedure. | bar mark / location
schedule shape / rev
observed shape
approval / disposition ref
Result / status (Pass / Fail / N/A / Pending)
Inspector name / role / date
Photo / certificate / report reference
Issue / disposition / recheck evidence and date
RE-05 | Bar arrangement, spacing and layer position What to observe: Observe installed bar marks, direction, layer, orientation and relative spacing against structural details, including congestion zones. How to check: Check identified grids/sections using project measurement method; record actual readings where required by drawings/specification. Acceptance basis: Use actual structural drawing, bar schedule and project tolerance; no universal spacing or tolerance applies. Reference to confirm: Approved structural drawings, bar schedule and project dimensional criteria. | grid / section
bar marks / layer
criterion / drawing ref
actual measurement
Result / status (Pass / Fail / N/A / Pending)
Inspector name / role / date
Photo / certificate / report reference
Issue / disposition / recheck evidence and date
RE-06 | Laps, anchorage, couplers and termination details What to observe: Inspect shown splice locations/types, lap/anchorage arrangement, bar ends and coupler identity/engagement evidence specified for the element. How to check: Compare critical locations with structural details; check product and installation records for specified mechanical splices. Acceptance basis: Follow exact project drawings, adopted specification/standard and approved coupler submittal; do not infer lap lengths, embedment or coupler acceptance class. Reference to confirm: Structural splice/anchorage details, adopted project specification and approved coupler instructions. | splice / location
detail / drawing ref
product / batch
installation / disposition ref
Result / status (Pass / Fail / N/A / Pending)
Inspector name / role / date
Photo / certificate / report reference
Issue / disposition / recheck evidence and date
RE-07 | Supports, spacers and specified cover What to observe: Observe chair/spacer product and placement, support contact/stability and reinforcement position relative to formed faces or substrate. How to check: Inspect support type/locations; check project-identified cover points with suitable verified measuring method when required. Acceptance basis: Use project cover schedule/details, accepted products and tolerances; record actual values where project calls for measurement. Reference to confirm: Project cover schedule, support/spacer details and approved products. | support / location
cover criterion / ref
actual cover / unit / method
recheck evidence
Result / status (Pass / Fail / N/A / Pending)
Inspector name / role / date
Photo / certificate / report reference
Issue / disposition / recheck evidence and date
RE-08 | Fixing, restraint and placement stability What to observe: Observe ties/fixings, cage rigidity, support stability and displacement risk from planned worker access and documented placing method. How to check: Review approved placing/access method; inspect congested, edge, opening and support zones; record project-required movement checks. Acceptance basis: Use project-approved fixing details and construction/placement method; do not infer universal tie frequency or load resistance. Reference to confirm: Approved fixing details and concrete placement/access method. | zone / bar IDs
fixing observed
placing method ref
direction / recheck ref
Result / status (Pass / Fail / N/A / Pending)
Inspector name / role / date
Photo / certificate / report reference
Issue / disposition / recheck evidence and date
RE-09 | Surface, projection and reinforcement exceptions What to observe: Observe contamination/coating or loose material that may affect specified performance, projecting bars at interfaces, and outstanding substitutions/NCRs. How to check: Walk steel zone before concealment; cross-check substitution/NCR register and prior-pour interfaces; record condition and closeout reference. Acceptance basis: Use project specification and written designer/project disposition; no blanket rust rejection threshold or cleaning rule is imposed. Reference to confirm: Project specification, approved substitutions and written NCR/designer dispositions. | zone / interface
condition observed
NCR / substitution ref
action / closeout ref
Result / status (Pass / Fail / N/A / Pending)
Inspector name / role / date
Photo / certificate / report reference
Issue / disposition / recheck evidence and date

## Project setup
Cavoren ITP | Reinforcement Inspection Checklist
Field | Project entry | Reason / instructions | Source / locator
Project name / contract
Client / principal
Contractor / trade
Jurisdiction / building class
Room / element / zone / lot
Inspection date / time
Checklist issue / revision
Project / contractor
Element / grid / inspection zone
Pour or lot reference
Inspection date
Structural drawing / revision
Bar schedule / revision
Required project input |  | Why it is needed
Element, grid and pour/lot IDs |  | Defines the physical steel package inspected and links results to the pour record.
Current structural drawings and bar schedule, including revisions |  | Provides actual marks, layout, details and dimensions.
Project reinforcement specification and adopted standard edition |  | Supplies contractual product, tolerance, records and installation criteria.
Approved steel/coupler submittals and delivery traceability records |  | Links installed marks/products to evidence.
Project inspection, substitution and NCR procedures |  | Defines assigned roles, control points and closeout process.
Included scope | Steel reinforcement installed in cast-in-place reinforced slabs, pad footings and strip footings, from document/bar-mark check through pre-concealment inspection.
Excluded scope | Precast manufacture, post-tensioning/prestressing, piles, shotcrete, bridge/highway special provisions, welding/NDT acceptance, structural design/rebar design verification, concrete delivery/testing/placement, and whole-pour release.
Use notice | Blank field checklist for project adaptation. Use actual approved documents and project acceptance criteria. Record only observations made. This is not design approval, a temporary-works certificate, contractual Hold/Witness Point release, or permission to place, strip or load.
How to use
1 | Confirm physical scope, controlled documents, measurement method, required records and assigned roles.
2 | Inspect a defined zone/lot; cite criterion and actual document revision for each check.
3 | Record actual measurements only where required; attach traceability and photo evidence by reference.
4 | For deviations, identify affected steel, prevent concealment where required, obtain written disposition and record recheck.
5 | Keep field observations separate from designer approval and project release.
Source title | Role and limits | URL | Locator
Cavoren cast-in-place concrete baseline | Topic and sequence context only; not a project specification or independent technical authority. | https://itp.cavoren.net/templates/concrete/ | Original proposed concrete baseline rows CON-01 to CON-08
Queensland TMR Ancillary MRTS71 Reinforcing Steel / ATS 5310, July 2025 | Topic guidance from a Queensland transport/infrastructure specification only. Do not import its values, registrations, frequencies, roles or hold points into general building work. | https://www.tmr.qld.gov.au/_/media/busind/techstdpubs/specifications-and-drawings/specifications/2-bridges-and-structures/mrts71.pdf?extension=pdf&hash=436D56549EF2693B1E5CC9DAD5DCF1D6&rev=c09d0ebf1e8149bfbab395d06076d9d1&sc_lang=en&size=695385 | Clauses 1.1–1.4; 4.1; 5.1–5.19; 6.1–6.9; 7.1–7.8; 8.1–8.5; 9.1–9.9; Sections 10–12; Appendix A. TMR listing says ancillary harmonised specifications are information only and not for use in contracts.
Queensland TMR MRTS70 Concrete, July 2022 | Topic guidance only for concrete/formwork interface. Queensland transport/infrastructure contract criteria are not universal building requirements. | https://www.tmr.qld.gov.au/_/media/busind/techstdpubs/specifications-and-drawings/specifications/2-bridges-and-structures/mrts70.pdf?extension=pdf&hash=BD4A48371C386F32622F6862572AA56A&rev=24517261eac44ddb86310c7980172050&sc_lang=en&size=1730809 | Sections 15.5–15.9 (formwork/falsework, reinforcement, placement/compaction, early loading).

## Issues and handover
Reinforcement Inspection Checklist ¦ Issues and handover
Project | Location / area | Issue date | Open item reference | Person / role
Item ID / date | Affected location and issue | Immediate action / disposition | Recheck evidence / date | Responsible person / role
Reinforcement inspection handover | Inspection record status | Select one status only
[ ] Inspection record complete
[ ] Action / recheck outstanding
[ ] Design or project disposition required
Decision boundary | This status records the steel inspection handover only. It does not mean ready to pour, approve reinforcement design, release a contractual control point, or authorize placement. Carry open items into the project ITP/pre-pour process.
Handover role | Field inspector name / role / date
Handover role | Receiving project role / date
Handover role | Open NCR, RFI or disposition reference
Field inspector | Role / record field | Entry / reference
Field inspector name/role/date
Inspection lot, element and boundaries
Observation and evidence references
Design check record | Role / record field | Entry / reference
Design document and revision
Designer/checker identity and project-assigned role
Design response/calculation/RFI reference
Project release / handover | Role / record field | Entry / reference
Release decision-maker role assigned by project/contract
Decision status and conditions
Basis: inspection/NCR references and control-point clause
Date/time and notice/release record reference
Role boundary | Inspector records field observations; design author/checker and project release authority remain separate records/roles. This signature does not certify design, approve a substitution, release a Hold Point or authorize placement.
Signature note | Signatures record the named person’s stated role and entry only. They do not by themselves approve design, certify compliance, release a contractual control point or authorize the next activity.