## Start here
Structural Steel Erection ITP Template
Project-specific baseline for site receipt, support interfaces, erection readiness, member placement, connections, geometry evidence and handover. It does not design lifting operations, temporary works, structural stability or determine tolerances, fastener values, weld acceptance or contractual release rights.
Status | Free editable proposed baseline. Not project-approved and not evidence that work was inspected.
Project fields | Complete project, state, parties, document number/revision and scope in your controlled copy.
Technical criteria | Replace every [Enter ...] prompt with the exact contract/drawing/specification/procedure reference and project condition. Confirm adopted standard editions and resolve conflicts.
Frequency / lot | These rows contain proposed activity triggers only. Set the actual lot/sample basis and frequency from project requirements.
Roles and control points | Confirm performing/reviewing roles, contractual H/W rights, notice, evidence and release. No external control point is assumed.
Conditional activities | Remove out-of-scope work or mark it not applicable with a reason; include only processes actually specified.
Records | Use the matching blank Records sheet. Enter actual inspection date, measured result and signature only when the work is performed.
Evidence | Keep original material certificates, weld/NDT/coating/survey reports and written dispositions; index them rather than replacing them with a tick.
Scope boundary | Project-specific baseline for site receipt, support interfaces, erection readiness, member placement, connections, geometry evidence and handover. It does not design lifting operations, temporary works, structural stability or determine tolerances, fastener values, weld acceptance or contractual release rights.
Project source prompts | • Approved structural and steelwork drawings / revisions: Identify contract drawing register, structural sheets, steel schedules, connection details and controlled revisions. • Specified construction category and design basis: Enter the category and exact source/decision; do not select a category in this template. • Fabrication, subcontractor and handover boundary: Identify who details, processes, welds, inspects, coats, transports, erects and supplies records. • Approved erection sequence / temporary stability documents: Use approved project erection and temporary works documents. This ITP does not design lifts, bracing or temporary works. • Performing, reviewing, witness and release roles: Keep contractor checks distinct from client/consultant contractual rights; source H/W notice and release arrangements. • Steel grade, product and certification requirements: Use project specification and adopted material standards/editions; preserve source and any exceptions. • Project record, submission and closeout requirements: Identify required registers, dossier index, report format and handover records. • Anchor/holding-down bolt and base interface requirements: Identify concrete interface records, surveyed positions, approved details and assigned discrepancy decision-maker. • Project geometry / survey tolerances and evidence: Cite actual drawing or specification items and survey method; no generic tolerances are supplied. • Structural fastener system and verification requirements: Identify specified assemblies, supply references, installation method and any verification evidence. • Site welding scope and project welding regime: Identify actual joints, approved procedure, required personnel and inspection/NDT evidence if included. • Weld category, WPS, personnel evidence and acceptance: Identify only the contract-specified welding regime, required approvals and evidence. • Specified NDT method, extent, timing and acceptance: Copy only from the governing project documents; if absent, identify the exact gap. • Specified grout / baseplate interface scope: Confirm included activities, approved product/method, substrate conditions and acceptance documents.

## ITP
steel-erection ¦ Proposed Inspection and Test Plan
Document number: [Enter] Revision: [Enter] Date: [Enter] Project: [Enter] State: [Enter] Contractor: [Enter] Client: [Enter] Project-specific baseline for site receipt, support interfaces, erection readiness, member placement, connections, geometry evidence and handover. It does not design lifting operations, temporary works, structural stability or determine tolerances, fastener values, weld acceptance or contractual release rights.
ID | Stage | Inspection / test | Method | Project acceptance condition | Reference / locator | Trigger / frequency | Performing / reviewing role | Point | Approval / witness party | Notice / release evidence | Record | Remarks / applicability
ERE-01 | Erection package and workfront release inputs | Confirm erection scope, received member schedule, interface boundaries and approved sequence documents are identified for the workfront. | Review contract scope, erection drawings/revisions, member list, approved sequence/temporary stability documents and project inspection/control requirements before site assembly. | The workfront and member/connection references map to controlled approved documents; required technical approvals and assigned decision roles are identifiable before the relevant operation. | Topic guidance only; see Source Register. Enter the actual project document, revision and locator. | Proposed: At the identified activity / item / lot before the next step that would obscure or change the evidence; confirm project-defined coverage and timing. | Proposed: Assigned fabricator / erector quality role performs and records; project-assigned reviewer acts only within documented authority. | TBC | Proposed: [Enter project-assigned reviewing / release authority] | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external control point is assigned. | Erection workfront and document register | Proposed baseline. Confirm applicability and replace with controlled project requirement. Include only when this activity is in the contracted package.
ERE-02 | Delivery receipt and member identity | Check delivered member marks, packing identity, traceability handover and visible transport condition before distribution to the workfront. | Compare delivery docket and packing list with member marks and fabrication dossier; inspect for visible damage or identity gaps and link exceptions to the affected item. | The received member and evidence map to the dispatch records and project material register; damage, missing records or untraceable items are identified and dispositioned before use. | Topic guidance only; see Source Register. Enter the actual project document, revision and locator. | Proposed: At the identified activity / item / lot before the next step that would obscure or change the evidence; confirm project-defined coverage and timing. | Proposed: Assigned fabricator / erector quality role performs and records; project-assigned reviewer acts only within documented authority. | TBC | Proposed: [Enter project-assigned reviewing / release authority] | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external control point is assigned. | Site steel receiving and discrepancy register | Proposed baseline. Confirm applicability and replace with controlled project requirement. Include only when this activity is in the contracted package.
ERE-03 | Base and anchor interface before steel placement | Verify the assigned interface evidence for support locations and anchors before steelwork is placed or the interface becomes inaccessible. | Compare the concrete/anchor handover and survey record with the approved steel drawings and project-defined interface criteria; record point/location references and unresolved deviations. | The inspected support and anchor evidence is traceable to the drawing and assigned interface acceptance source; unresolved deviations have written direction from the project-designated decision role. | Topic guidance only; see Source Register. Enter the actual project document, revision and locator. | Proposed: At the identified activity / item / lot before the next step that would obscure or change the evidence; confirm project-defined coverage and timing. | Proposed: Assigned fabricator / erector quality role performs and records; project-assigned reviewer acts only within documented authority. | TBC | Proposed: [Enter project-assigned reviewing / release authority] | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external control point is assigned. | Base / anchor interface and survey record | Proposed baseline. Confirm applicability and replace with controlled project requirement. Include only when this activity is in the contracted package.
ERE-04 | Pre-erection temporary stability and readiness documents | Confirm the approved project erection and temporary stability documentation relevant to the next operation is available to the assigned team. | Check controlled sequence, temporary works/bracing details and any required engineered approvals or release documents; verify revisions and workfront applicability. This check does not design or validate a lift. | The applicable approved documents and responsible roles are identified for the workfront before the operation; missing or conflicting requirements are referred through the project process. | Topic guidance only; see Source Register. Enter the actual project document, revision and locator. | Proposed: At the identified activity / item / lot before the next step that would obscure or change the evidence; confirm project-defined coverage and timing. | Proposed: Assigned fabricator / erector quality role performs and records; project-assigned reviewer acts only within documented authority. | TBC | Proposed: [Enter project-assigned reviewing / release authority] | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external control point is assigned. | Erection readiness and briefing reference | Proposed baseline. Confirm applicability and replace with controlled project requirement. Include only when this activity is in the contracted package.
ERE-05 | Member placement, orientation and temporary restraint | Inspect installed member identity, location/orientation and documented temporary restraint state against the approved erection information. | Identify member and grid/location; compare orientation and connection interface with the erection drawing; record observed restraint/bracing evidence against the project sequence. Do not infer structural stability from visual appearance. | Member identity, position and required temporary restraint evidence correspond to the current approved erection documents; any difference or incomplete restraint is escalated to the assigned technical authority. | Topic guidance only; see Source Register. Enter the actual project document, revision and locator. | Proposed: At the identified activity / item / lot before the next step that would obscure or change the evidence; confirm project-defined coverage and timing. | Proposed: Assigned fabricator / erector quality role performs and records; project-assigned reviewer acts only within documented authority. | TBC | Proposed: [Enter project-assigned reviewing / release authority] | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external control point is assigned. | Member placement and temporary restraint record | Proposed baseline. Confirm applicability and replace with controlled project requirement. Include only when this activity is in the contracted package.
ERE-06 | Bolted connection assembly and specified verification | Trace each identified bolted connection to the supplied assembly and project-specified installation/verification evidence. | Identify the connection and fastener lot; compare assembly/installation records with approved connection detail and nominated procedure; record only measurements, tool checks or verification required by project documents. | The connection record identifies its project fastener source, installation procedure and required verification evidence; any missing evidence or deviation has a recorded project disposition and recheck. | Topic guidance only; see Source Register. Enter the actual project document, revision and locator. | Proposed: At the identified activity / item / lot before the next step that would obscure or change the evidence; confirm project-defined coverage and timing. | Proposed: Assigned fabricator / erector quality role performs and records; project-assigned reviewer acts only within documented authority. | TBC | Proposed: [Enter project-assigned reviewing / release authority] | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external control point is assigned. | Bolted connection installation and verification log | Proposed baseline. Confirm applicability and replace with controlled project requirement. Include only when this activity is in the contracted package.
ERE-07 | Site welded connections and inspection evidence | Where site welding is included, preserve a separate trace from connection identity to approved site procedure, production records and specified inspection reports. | Locate weld by connection/member marks; verify the controlled site WPS and required personnel/process records; connect visual/NDT evidence and repair records to the same weld ID. | The site weld has traceable approved procedure and project-required inspection evidence; required repairs/retests and technical dispositions remain linked to the original weld and connection. | Topic guidance only; see Source Register. Enter the actual project document, revision and locator. | Proposed: At the identified activity / item / lot before the next step that would obscure or change the evidence; confirm project-defined coverage and timing. | Proposed: Assigned fabricator / erector quality role performs and records; project-assigned reviewer acts only within documented authority. | TBC | Proposed: [Enter project-assigned reviewing / release authority] | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external control point is assigned. | Site weld map and inspection / NDT index | Proposed baseline. Confirm applicability and replace with controlled project requirement. Conditional: include only if site welding is in the package.
ERE-08 | Geometry, connection completion and handover | Record final project-specified survey/connection evidence and compile unresolved items before handing the frame to follow-on trades. | Compare measured locations and completed connection evidence with identified acceptance sources; reconcile open NCRs, grout/baseplate records where included, as-built changes and required dossier items. | The final record links actual observations and reports to member/grid/connection identifiers and project criteria; unresolved items and required releases remain visible for the assigned decision-maker and follow-on trade. | Topic guidance only; see Source Register. Enter the actual project document, revision and locator. | Proposed: At the identified activity / item / lot before the next step that would obscure or change the evidence; confirm project-defined coverage and timing. | Proposed: Assigned fabricator / erector quality role performs and records; project-assigned reviewer acts only within documented authority. | TBC | Proposed: [Enter project-assigned reviewing / release authority] | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external control point is assigned. | Steelwork completion, survey and handover register | Proposed baseline. Confirm applicability and replace with controlled project requirement. Include only when this activity is in the contracted package.

## Records
Blank Inspection Record Prompts
Complete during actual work. These files contain no prefilled inspection results, dates, names, approvals or signatures. Keep original third-party reports.
ITP ID / event | Record field | Actual entry / observation | Evidence / report ref. | Disposition / action ref. | Performed by / date | Reviewed / decision ref.
ERE-01 ¦ Erection package and workfront release inputs | Building / grid / workfront / lot
ERE-01 | Erection drawing / revision
ERE-01 | Approved sequence / temporary stability doc ref.
ERE-01 | Trade / designer / erector interface
ERE-01 | Open decision / release record ref.
ERE-01 | Date / lot / result / status |  | Original report / photo / attachment ref. | NCR / correction / recheck ref. | Actual performer and date | Assigned review / decision ref.
ERE-02 ¦ Delivery receipt and member identity | Delivery / packing list ref.
ERE-02 | Member / piece mark
ERE-02 | Dossier / certificate / traceability ref.
ERE-02 | Observed transport / storage condition
ERE-02 | Damage / missing evidence / disposition ref.
ERE-02 | Date / lot / result / status |  | Original report / photo / attachment ref. | NCR / correction / recheck ref. | Actual performer and date | Assigned review / decision ref.
ERE-03 ¦ Base and anchor interface before steel placement | Grid / baseplate / support mark
ERE-03 | Anchor group / identification
ERE-03 | Drawing / survey / concrete handover ref.
ERE-03 | Actual position / condition / unit
ERE-03 | Deviation / designer disposition ref.
ERE-03 | Date / lot / result / status |  | Original report / photo / attachment ref. | NCR / correction / recheck ref. | Actual performer and date | Assigned review / decision ref.
ERE-04 ¦ Pre-erection temporary stability and readiness documents | Planned operation / workfront
ERE-04 | Sequence / revision
ERE-04 | Temporary stability document / approval ref.
ERE-04 | Briefing / interface evidence ref.
ERE-04 | Unresolved conflict / referral ref.
ERE-04 | Date / lot / result / status |  | Original report / photo / attachment ref. | NCR / correction / recheck ref. | Actual performer and date | Assigned review / decision ref.
ERE-05 ¦ Member placement, orientation and temporary restraint | Member mark
ERE-05 | Grid / level / connection locator
ERE-05 | Erection drawing / revision
ERE-05 | Temporary restraint / brace ref. and observed state
ERE-05 | Deviation / technical direction ref.
ERE-05 | Date / lot / result / status |  | Original report / photo / attachment ref. | NCR / correction / recheck ref. | Actual performer and date | Assigned review / decision ref.
ERE-06 ¦ Bolted connection assembly and specified verification | Connection / grid / member marks
ERE-06 | Fastener assembly / lot / certificate ref.
ERE-06 | Approved installation procedure ref.
ERE-06 | Actual specified verification / unit / tool ref.
ERE-06 | Deviation / recheck / disposition ref.
ERE-06 | Date / lot / result / status |  | Original report / photo / attachment ref. | NCR / correction / recheck ref. | Actual performer and date | Assigned review / decision ref.
ERE-07 ¦ Site welded connections and inspection evidence | Weld ID / connection / location
ERE-07 | Site WPS / revision
ERE-07 | Production / operator evidence ref.
ERE-07 | Visual / NDT report and result ref.
ERE-07 | Repair / recheck / disposition ref.
ERE-07 | Date / lot / result / status |  | Original report / photo / attachment ref. | NCR / correction / recheck ref. | Actual performer and date | Assigned review / decision ref.
ERE-08 ¦ Geometry, connection completion and handover | Building / grid / level / member IDs
ERE-08 | As-built / survey report and actual value / unit
ERE-08 | Connection completion evidence ref.
ERE-08 | Grout / base interface report ref., if applicable
ERE-08 | NCR / release / handover outstanding item ref.
ERE-08 | Date / lot / result / status |  | Original report / photo / attachment ref. | NCR / correction / recheck ref. | Actual performer and date | Assigned review / decision ref.

## Source Register
Topic Guidance Source Register
Source ID | Title | Locator / accessed date | Use and limitation
ASI-FAB-ERECT | Australian Steel Institute, Fabrication and Erection | Accessed 2026-10-07; sections Steel distribution (product packaging/marking/traceability), Steel detailing, The fabrication process, Erection of steel structures. URL: https://steel.org.au/what-we-do/focus-areas/fabrication-and-erection/ | Industry process overview supporting distinction between shop fabrication and site assembly, interface handoffs, marking/traceability, bolting or site welding, and alignment. It supplies no universal technical acceptance values, frequencies or contract hold points.
ASI-TRACE | Australian Steel Institute, Traceability | Accessed 2026-10-07; sections on steel supply chain, material identification through distribution and processing, component traceability and records. URL: https://www.steel.org.au/what-we-do/focus-areas/traceability/ | Industry guidance for preserving a positive link between physical product, markings and compliance documents as steel moves through the supply chain. Not a project specification or universal traceability class.
TMR-MRTS78 | Queensland Department of Transport and Main Roads, MRTS78 Fabrication of Structural Steelwork, November 2020; TMR Amendment Register, May 2026 | MRTS78 Sections 1, 6–12; active official PDF accessed 2026-10-07. TMR Amendment Register, May 2026, MRTS78 Suite entry records later amendment topics including traceability, weld/process details, fastener scope transfer to MRTS278 and reordered control points: https://www.tmr.qld.gov.au/-/media/busind/techstdpubs/Specifications-and-drawings/Specifications/amendmentregister.pdf?hash=03180BD61BBB010F98A0432974939A51&sc_lang=en. URL: https://www.tmr.qld.gov.au/-/media/busind/techstdpubs/Specifications-and-drawings/Specifications/2-Bridges-and-Structures/MRTS78.pdf?la=en | Queensland transport/bridge specification example only. Its project-specific scope, registered supplier requirements, numeric criteria and Hold/Witness points do not apply to ordinary building projects by default. Confirm the contract-adopted edition and amendment suite before use.
HUTCHIES-STEEL | Hutchinson Builders, Safety & Quality Planning downloads (Structural Steel ITP and Report examples) | Accessed 2026-10-07; publicly listed structural steel ITP/report examples inspected as broad sequence and record concepts. URL: https://subbies.hutchies.com.au/resources/videos/safety-and-quality-planning | Industry example supporting separate shop/site work and traceable record concepts only. Original documents are not reproduced; blank example criteria do not set universal acceptance values or rates.