## Start here
Structural Steel Fabrication ITP Template
Project-specific baseline for workshop processing, assembly, welding and inspection interfaces, subcontract coating, fabrication records and dispatch to site. It does not certify design, provide a WPS, determine weld/NDT acceptance values, select coatings or create inspection release rights.
Status | Free editable proposed baseline. Not project-approved and not evidence that work was inspected.
Project fields | Complete project, state, parties, document number/revision and scope in your controlled copy.
Technical criteria | Replace every [Enter ...] prompt with the exact contract/drawing/specification/procedure reference and project condition. Confirm adopted standard editions and resolve conflicts.
Frequency / lot | These rows contain proposed activity triggers only. Set the actual lot/sample basis and frequency from project requirements.
Roles and control points | Confirm performing/reviewing roles, contractual H/W rights, notice, evidence and release. No external control point is assumed.
Conditional activities | Remove out-of-scope work or mark it not applicable with a reason; include only processes actually specified.
Records | Use the matching blank Records sheet. Enter actual inspection date, measured result and signature only when the work is performed.
Evidence | Keep original material certificates, weld/NDT/coating/survey reports and written dispositions; index them rather than replacing them with a tick.
Scope boundary | Project-specific baseline for workshop processing, assembly, welding and inspection interfaces, subcontract coating, fabrication records and dispatch to site. It does not certify design, provide a WPS, determine weld/NDT acceptance values, select coatings or create inspection release rights.
Project source prompts | • Approved structural and steelwork drawings / revisions: Identify contract drawing register, structural sheets, steel schedules, connection details and controlled revisions. • Specified construction category and design basis: Enter the category and exact source/decision; do not select a category in this template. • Fabrication, subcontractor and handover boundary: Identify who details, processes, welds, inspects, coats, transports, erects and supplies records. • Performing, reviewing, witness and release roles: Keep contractor checks distinct from client/consultant contractual rights; source H/W notice and release arrangements. • Project record, submission and closeout requirements: Identify required registers, dossier index, report format and handover records. • Steel grade, product and certification requirements: Use project specification and adopted material standards/editions; preserve source and any exceptions. • Weld category, WPS, personnel evidence and acceptance: Identify only the contract-specified welding regime, required approvals and evidence. • Specified NDT method, extent, timing and acceptance: Copy only from the governing project documents; if absent, identify the exact gap. • Project geometry / survey tolerances and evidence: Cite actual drawing or specification items and survey method; no generic tolerances are supplied. • Specified coating system, preparation, inspection and repair: Identify applicable paint/galvanizing system and project source; do not assume system or thickness.

## ITP
steel-fabrication ¦ Proposed Inspection and Test Plan
Document number: [Enter] Revision: [Enter] Date: [Enter] Project: [Enter] State: [Enter] Contractor: [Enter] Client: [Enter] Project-specific baseline for workshop processing, assembly, welding and inspection interfaces, subcontract coating, fabrication records and dispatch to site. It does not certify design, provide a WPS, determine weld/NDT acceptance values, select coatings or create inspection release rights.
ID | Stage | Inspection / test | Method | Project acceptance condition | Reference / locator | Trigger / frequency | Performing / reviewing role | Point | Approval / witness party | Notice / release evidence | Record | Remarks / applicability
FBR-01 | Package definition and submittal readiness | Confirm the fabrication lot, downstream erection interfaces and required submissions are defined before steel is released for production. | Compare contract scope, drawing register, steel schedule, submittal register and supplier/subcontract interfaces; flag unresolved revisions or responsibility gaps. | The identified lot and interfaces map to the current controlled drawings and specified category; required submissions and unresolved decisions are visible before work proceeds. | Topic guidance only; see Source Register. Enter the actual project document, revision and locator. | Proposed: At the identified activity / item / lot before the next step that would obscure or change the evidence; confirm project-defined coverage and timing. | Proposed: Assigned fabricator / erector quality role performs and records; project-assigned reviewer acts only within documented authority. | TBC | Proposed: [Enter project-assigned reviewing / release authority] | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external control point is assigned. | Fabrication package and submittal register | Proposed baseline. Confirm applicability and replace with controlled project requirement. Include only when this activity is in the contracted package.
FBR-02 | Incoming steel and certificate traceability | Verify received steel identity and preserve the link from each project lot or member to its supplied compliance documents. | Compare purchase/delivery documentation, physical marks or controlled transfer marks, member/heat references and certificates against the project material schedule; document breaks before processing. | The identified product agrees with the specified material record and its compliance documentation remains traceable through the project's required identification level; gaps are segregated and referred for written disposition. | Topic guidance only; see Source Register. Enter the actual project document, revision and locator. | Proposed: At the identified activity / item / lot before the next step that would obscure or change the evidence; confirm project-defined coverage and timing. | Proposed: Assigned fabricator / erector quality role performs and records; project-assigned reviewer acts only within documented authority. | TBC | Proposed: [Enter project-assigned reviewing / release authority] | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external control point is assigned. | Incoming material and traceability register | Proposed baseline. Confirm applicability and replace with controlled project requirement. Include only when this activity is in the contracted package.
FBR-03 | Detailing and approved shop information | Check shop details used for manufacture against the controlled design information and record resolved design interfaces. | Review shop drawing, member list, connection/bolt details and revision status against contract drawings and approved design responses; record specific discrepancy references. | Released shop information identifies the member and connection being made and has the review/approval status required by the contract; unresolved design changes are not silently incorporated. | Topic guidance only; see Source Register. Enter the actual project document, revision and locator. | Proposed: At the identified activity / item / lot before the next step that would obscure or change the evidence; confirm project-defined coverage and timing. | Proposed: Assigned fabricator / erector quality role performs and records; project-assigned reviewer acts only within documented authority. | TBC | Proposed: [Enter project-assigned reviewing / release authority] | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external control point is assigned. | Shop drawing review and change register | Proposed baseline. Confirm applicability and replace with controlled project requirement. Include only when this activity is in the contracted package.
FBR-04 | Cutting, drilling and edge preparation | Inspect processed components against their identified drawings and fabrication details before assembly obscures the features. | Identify the member mark; compare cut, hole and edge-preparation features with the cited drawing/detail and approved fabrication information; note the actual inspection evidence and discrepancy location. | The inspected member and relevant features correspond to the controlled details and specified preparation; any deviation has a traceable approved disposition before incorporation. | Topic guidance only; see Source Register. Enter the actual project document, revision and locator. | Proposed: At the identified activity / item / lot before the next step that would obscure or change the evidence; confirm project-defined coverage and timing. | Proposed: Assigned fabricator / erector quality role performs and records; project-assigned reviewer acts only within documented authority. | TBC | Proposed: [Enter project-assigned reviewing / release authority] | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external control point is assigned. | Fabrication processing and dimensional record | Proposed baseline. Confirm applicability and replace with controlled project requirement. Include only when this activity is in the contracted package.
FBR-05 | Joint fit-up and assembly before welding | Verify the identified joint preparation and fit-up against its weld detail before welding changes access to the joint. | Locate the joint on the weld map and compare preparation, alignment, cleanliness, backing and fit-up features that the approved WPS and project detail require; record the observed feature, not a generic pass tick. | Joint identity, preparation and fit-up match the cited approved detail and applicable WPS requirements; unresolved departures are held for assigned disposition before welding. | Topic guidance only; see Source Register. Enter the actual project document, revision and locator. | Proposed: At the identified activity / item / lot before the next step that would obscure or change the evidence; confirm project-defined coverage and timing. | Proposed: Assigned fabricator / erector quality role performs and records; project-assigned reviewer acts only within documented authority. | TBC | Proposed: [Enter project-assigned reviewing / release authority] | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external control point is assigned. | Joint fit-up and weld map record | Proposed baseline. Confirm applicability and replace with controlled project requirement. Include only when this activity is in the contracted package.
FBR-06 | Welding process and weld identity | Maintain a traceable record connecting each performed weld to its joint, applicable procedure and production evidence. | Review the weld map and production record for the actual joint ID, procedure reference, responsible welder/operator evidence required by the project, date/shift, consumable/control records where specified, and any repair link. | Every recorded weld can be traced to its identified joint and applicable approved process evidence; required records are present and discrepancies or repairs remain linked to the original weld identity. | Topic guidance only; see Source Register. Enter the actual project document, revision and locator. | Proposed: At the identified activity / item / lot before the next step that would obscure or change the evidence; confirm project-defined coverage and timing. | Proposed: Assigned fabricator / erector quality role performs and records; project-assigned reviewer acts only within documented authority. | TBC | Proposed: [Enter project-assigned reviewing / release authority] | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external control point is assigned. | Weld production and repair register | Proposed baseline. Confirm applicability and replace with controlled project requirement. Include only when this activity is in the contracted package.
FBR-07 | Completed weld inspection and specified NDT | Record visual inspection and only project-specified NDT against the identified weld and acceptance source. | Identify the weld on the weld map; compare observable weld features with the cited criteria; link any NDT request, report, method, extent and result to that same joint. Preserve the original report. | The inspection record and any required report identify the weld, method and controlling acceptance reference; required evidence is complete and nonconformances have an assigned disposition and recheck trail. | Topic guidance only; see Source Register. Enter the actual project document, revision and locator. | Proposed: At the identified activity / item / lot before the next step that would obscure or change the evidence; confirm project-defined coverage and timing. | Proposed: Assigned fabricator / erector quality role performs and records; project-assigned reviewer acts only within documented authority. | TBC | Proposed: [Enter project-assigned reviewing / release authority] | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external control point is assigned. | Weld inspection and NDT report index | Proposed baseline. Confirm applicability and replace with controlled project requirement. Include only when this activity is in the contracted package.
FBR-08 | Trial assembly / fabrication geometry | Where required by the project, verify assembly interfaces and measured geometry against identified drawings before disassembly or shipment. | Record assembly marks and measurement locations; compare actual measured features with the project-nominated drawing dimensions/tolerances and identify instrument/report references. | The assembly, measurement location and actual observations are traceable to the controlled acceptance source; results outside or without a source are referred for project disposition. | Topic guidance only; see Source Register. Enter the actual project document, revision and locator. | Proposed: At the identified activity / item / lot before the next step that would obscure or change the evidence; confirm project-defined coverage and timing. | Proposed: Assigned fabricator / erector quality role performs and records; project-assigned reviewer acts only within documented authority. | TBC | Proposed: [Enter project-assigned reviewing / release authority] | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external control point is assigned. | Trial assembly and dimensional survey record | Proposed baseline. Confirm applicability and replace with controlled project requirement. Conditional: include where trial assembly or a defined dimensional verification is required by the project.
FBR-09 | Surface preparation, coating and repair interface | Verify specified surface treatment evidence and retain identification through subcontract processing and return to the fabricator. | Compare the coating work order and member marks with specified system documents; review preparation/application/environmental readings and repair records only where required by the project; link subcontract report to each lot/member. | The delivered coating evidence identifies the specified system, inspected lot/member and source criteria; incomplete, damaged or discrepant areas have traceable project disposition and repair evidence. | Topic guidance only; see Source Register. Enter the actual project document, revision and locator. | Proposed: At the identified activity / item / lot before the next step that would obscure or change the evidence; confirm project-defined coverage and timing. | Proposed: Assigned fabricator / erector quality role performs and records; project-assigned reviewer acts only within documented authority. | TBC | Proposed: [Enter project-assigned reviewing / release authority] | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external control point is assigned. | Surface treatment and coating traceability record | Proposed baseline. Confirm applicability and replace with controlled project requirement. Include only when this activity is in the contracted package.
FBR-10 | Fabrication dossier and dispatch release interface | Compile the required manufacturing evidence and maintain the link from shop lot/member marks to packing and receiving records. | Reconcile material certificates, traceability, shop drawing revisions, weld map and inspection reports, coating evidence, NCR dispositions and member/packing list against project dossier requirements. | The required dossier index identifies the supplied member/lot and controlled documents; open exceptions and delivery/erection handover items are clearly listed for assigned project review. | Topic guidance only; see Source Register. Enter the actual project document, revision and locator. | Proposed: At the identified activity / item / lot before the next step that would obscure or change the evidence; confirm project-defined coverage and timing. | Proposed: Assigned fabricator / erector quality role performs and records; project-assigned reviewer acts only within documented authority. | TBC | Proposed: [Enter project-assigned reviewing / release authority] | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external control point is assigned. | Fabrication dossier index and dispatch register | Proposed baseline. Confirm applicability and replace with controlled project requirement. Include only when this activity is in the contracted package.

## Records
Blank Inspection Record Prompts
Complete during actual work. These files contain no prefilled inspection results, dates, names, approvals or signatures. Keep original third-party reports.
ITP ID / event | Record field | Actual entry / observation | Evidence / report ref. | Disposition / action ref. | Performed by / date | Reviewed / decision ref.
FBR-01 ¦ Package definition and submittal readiness | Package / lot reference
FBR-01 | Drawing and revision
FBR-01 | Detailer / processor / coater / erector interface
FBR-01 | Open decision / action reference
FBR-01 | Date / lot / result / status |  | Original report / photo / attachment ref. | NCR / correction / recheck ref. | Actual performer and date | Assigned review / decision ref.
FBR-02 ¦ Incoming steel and certificate traceability | Member / piece mark
FBR-02 | Heat / batch / source ID
FBR-02 | Specified material designation
FBR-02 | Certificate and source document ref.
FBR-02 | Traceability gap / disposition ref.
FBR-02 | Date / lot / result / status |  | Original report / photo / attachment ref. | NCR / correction / recheck ref. | Actual performer and date | Assigned review / decision ref.
FBR-03 ¦ Detailing and approved shop information | Member / assembly mark
FBR-03 | Shop drawing / revision / detail
FBR-03 | Design drawing / revision / detail
FBR-03 | RFI / design response / approval ref.
FBR-03 | Date / lot / result / status |  | Original report / photo / attachment ref. | NCR / correction / recheck ref. | Actual performer and date | Assigned review / decision ref.
FBR-04 ¦ Cutting, drilling and edge preparation | Member mark
FBR-04 | Cut / hole / edge feature and drawing locator
FBR-04 | Observed dimension / condition and unit
FBR-04 | Measurement method / tool ref.
FBR-04 | Deviation / disposition ref.
FBR-04 | Date / lot / result / status |  | Original report / photo / attachment ref. | NCR / correction / recheck ref. | Actual performer and date | Assigned review / decision ref.
FBR-05 ¦ Joint fit-up and assembly before welding | Weld ID / member and joint locator
FBR-05 | Weld map / drawing revision
FBR-05 | WPS reference / revision
FBR-05 | Observed fit-up feature / condition
FBR-05 | Deviation / disposition ref.
FBR-05 | Date / lot / result / status |  | Original report / photo / attachment ref. | NCR / correction / recheck ref. | Actual performer and date | Assigned review / decision ref.
FBR-06 ¦ Welding process and weld identity | Weld ID / member / location
FBR-06 | WPS / revision
FBR-06 | Welder / operator evidence ref.
FBR-06 | Date / production record ref.
FBR-06 | Repair / reinspection ref.
FBR-06 | Date / lot / result / status |  | Original report / photo / attachment ref. | NCR / correction / recheck ref. | Actual performer and date | Assigned review / decision ref.
FBR-07 ¦ Completed weld inspection and specified NDT | Weld ID / member / location
FBR-07 | Acceptance source / clause
FBR-07 | Visual observation / disposition
FBR-07 | NDT method / report / result ref.
FBR-07 | NCR / repair / recheck ref.
FBR-07 | Date / lot / result / status |  | Original report / photo / attachment ref. | NCR / correction / recheck ref. | Actual performer and date | Assigned review / decision ref.
FBR-08 ¦ Trial assembly / fabrication geometry | Assembly / member marks
FBR-08 | Measurement point / drawing locator
FBR-08 | Observed dimension / unit
FBR-08 | Drawing / tolerance source
FBR-08 | Survey / instrument / report ref.
FBR-08 | Date / lot / result / status |  | Original report / photo / attachment ref. | NCR / correction / recheck ref. | Actual performer and date | Assigned review / decision ref.
FBR-09 ¦ Surface preparation, coating and repair interface | Member / lot mark
FBR-09 | Specified coating system / source
FBR-09 | Subcontractor / process record ref.
FBR-09 | Observed inspection / reading / unit if specified
FBR-09 | Damage / repair / reinspection ref.
FBR-09 | Date / lot / result / status |  | Original report / photo / attachment ref. | NCR / correction / recheck ref. | Actual performer and date | Assigned review / decision ref.
FBR-10 ¦ Fabrication dossier and dispatch release interface | Fabrication lot / packing list
FBR-10 | Member marks / quantity basis
FBR-10 | Dossier index / revision
FBR-10 | Open NCR / concession / missing evidence ref.
FBR-10 | Transport / receiving interface ref.
FBR-10 | Date / lot / result / status |  | Original report / photo / attachment ref. | NCR / correction / recheck ref. | Actual performer and date | Assigned review / decision ref.

## Source Register
Topic Guidance Source Register
Source ID | Title | Locator / accessed date | Use and limitation
ASI-FAB-ERECT | Australian Steel Institute, Fabrication and Erection | Accessed 2026-10-07; sections Steel distribution (product packaging/marking/traceability), Steel detailing, The fabrication process, Erection of steel structures. URL: https://steel.org.au/what-we-do/focus-areas/fabrication-and-erection/ | Industry process overview supporting distinction between shop fabrication and site assembly, interface handoffs, marking/traceability, bolting or site welding, and alignment. It supplies no universal technical acceptance values, frequencies or contract hold points.
ASI-TRACE | Australian Steel Institute, Traceability | Accessed 2026-10-07; sections on steel supply chain, material identification through distribution and processing, component traceability and records. URL: https://www.steel.org.au/what-we-do/focus-areas/traceability/ | Industry guidance for preserving a positive link between physical product, markings and compliance documents as steel moves through the supply chain. Not a project specification or universal traceability class.
TMR-MRTS78 | Queensland Department of Transport and Main Roads, MRTS78 Fabrication of Structural Steelwork, November 2020; TMR Amendment Register, May 2026 | MRTS78 Sections 1, 6–12; active official PDF accessed 2026-10-07. TMR Amendment Register, May 2026, MRTS78 Suite entry records later amendment topics including traceability, weld/process details, fastener scope transfer to MRTS278 and reordered control points: https://www.tmr.qld.gov.au/-/media/busind/techstdpubs/Specifications-and-drawings/Specifications/amendmentregister.pdf?hash=03180BD61BBB010F98A0432974939A51&sc_lang=en. URL: https://www.tmr.qld.gov.au/-/media/busind/techstdpubs/Specifications-and-drawings/Specifications/2-Bridges-and-Structures/MRTS78.pdf?la=en | Queensland transport/bridge specification example only. Its project-specific scope, registered supplier requirements, numeric criteria and Hold/Witness points do not apply to ordinary building projects by default. Confirm the contract-adopted edition and amendment suite before use.
HUTCHIES-STEEL | Hutchinson Builders, Safety & Quality Planning downloads (Structural Steel ITP and Report examples) | Accessed 2026-10-07; publicly listed structural steel ITP/report examples inspected as broad sequence and record concepts. URL: https://subbies.hutchies.com.au/resources/videos/safety-and-quality-planning | Industry example supporting separate shop/site work and traceable record concepts only. Original documents are not reproduced; blank example criteria do not set universal acceptance values or rates.