## ITP
structural-steel-itp-template ¦ Inspection and Test Plan
[Fill: project name] ¦ Structural steel fabrication and erection inspection and test plan template — free editable baseline ¦ [Fill: Australian state/territory] ¦ Rev 00 ¦ 2026-10-06 ¦ For review Contractor: [Fill: contractor] Client: [Fill: client] Scope: Reusable baseline for structural steelwork from material receipt and workshop fabrication through coating, delivery and site erection. Separate shop and site lots/roles where different. Excludes design certification, crane/lift engineering, fireproofing and specialist coatings unless included. This is a free, editable, proposed baseline and is not tailored to a project, approved by a client, or evidence of completed inspection. Before use, complete the scope questions and bracketed fields, confirm every criterion and control against current project documents, and remove non-applicable rows. Exclusions: Confirm exclusions for this project; use the scope notes above.
ID | Stage | Inspection / test | Method | Acceptance requirement | Reference | Frequency | Responsible role | Point | Approval / witness party | Notice / release | Record | Remarks
STE-01 | Planning and submittals | Proposed: baseline — Confirm package boundaries, design documents, construction category, inspection/testing plan and fabrication/erection interfaces. | Proposed: baseline — Review approved drawings, specification, annexures and submittal register. | Proposed: baseline — Current approved [Fill: Approved drawings and revisions], [Fill: Construction category], [Fill: Steel Criteria], [Fill: Approved weld procedure, acceptance and sampling criteria], [Fill: Specified NDT method, extent and acceptance criteria] and [Fill: Project coating system, preparation and inspection criteria] requirements are identified; resolve inconsistencies before fabrication. | Guidance only; see Source Register: NSW-QMG, TMR-MRTS78, HUTCHIES-SUITE | Proposed: Before procurement / fabrication. | Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Steelwork submittal and document register | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
STE-02 | Material certificates and traceability | Proposed: baseline — Verify section, plate, bolt and consumable identity and link supplied steel to certificates/heat or batch evidence. | Proposed: baseline — Check markings, tags, delivery dockets and certificates against material register and approved grade schedule. | Proposed: baseline — Material type/grade matches [Fill: Material grades / certification criteria] and each item/lot is traceable to required certification; quarantine unidentified or discrepant material. | Guidance only; see Source Register: NSW-QMG, TMR-MRTS78, HUTCHIES-SUITE | Proposed: Each delivery and before traceability is lost through cutting/blasting. | Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Steel material register and certificates | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
STE-03 | Material condition and storage | Proposed: baseline — Inspect received steel and consumables for damage, corrosion, distortion, contamination and protected storage. | Proposed: baseline — Visual inspection on receipt and before use; check storage requirements for consumables. | Proposed: baseline — Condition remains suitable for specified fabrication/coating; damage or consumable storage excursions are recorded and dispositioned. | Guidance only; see Source Register: NSW-QMG, TMR-MRTS78 | Proposed: Every delivery and before use. | Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Incoming steel inspection | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
STE-04 | Fabrication set-out and cutting | Proposed: baseline — Check member identity, cut lengths, hole positions, edge preparation and fabrication dimensions. | Proposed: baseline — Measure against shop/approved drawings and fabrication schedule before assembly or welding. | Proposed: baseline — Dimensions and preparation match [Fill: Fabrication dimensions / tolerances]; revisions and approved deviations are traceable. | Guidance only; see Source Register: NSW-QMG, TMR-MRTS78, HUTCHIES-SUITE | Proposed: Each member or defined fabrication lot before assembly. | Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Fabrication dimensional checklist | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
STE-05 | Welding documentation readiness | Proposed: baseline — Verify approved welding procedures, weld map, consumables and personnel qualifications required by project. | Proposed: baseline — Review WPS, procedure qualification evidence, welder qualifications/continuity and consumable records against weld schedule. | Proposed: baseline — Applicable WPS and qualifications cover the specified joint/material/process under [Fill: Weld procedure/qualification requirements]; missing or mismatched coverage is resolved before welding. | Guidance only; see Source Register: NSW-QMG, TMR-MRTS78, HUTCHIES-SUITE | Proposed: Before first weld and when material, process, joint or personnel scope changes. | Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Welding document and qualification register | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
STE-06 | Fit-up and joint preparation | Proposed: baseline — Inspect joint preparation, root gap, alignment, cleanliness, backing and fit-up before welding. | Proposed: baseline — Visual and dimensional checks against approved joint detail and applicable WPS. | Proposed: baseline — Fit-up satisfies [Fill: Joint fit-up acceptance] and WPS; defects, unapproved tacks or mismatch are corrected before welding. | Guidance only; see Source Register: NSW-QMG, TMR-MRTS78, HUTCHIES-SUITE | Proposed: Each joint category / weld lot before welding, at specified rate. | Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Weld fit-up inspection | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
STE-07 | Welding process controls | Proposed: baseline — Check weld execution records include joint identity, WPS, welder, date and any specified environmental/process controls. | Proposed: baseline — Observe/record welding and review production logs against approved WPS and project requirements. | Proposed: baseline — Work is performed within the applicable approved WPS and [Fill: Welding process variables / controls]; interruptions, repairs and deviations are traceable. | Guidance only; see Source Register: NSW-QMG, TMR-MRTS78, HUTCHIES-SUITE | Proposed: During each welding shift / project-defined lot. | Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Welding production log | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
STE-08 | Completed weld visual inspection | Proposed: baseline — Inspect completed welds for profile, visible defects, size and completion against weld map and acceptance criteria. | Proposed: baseline — Visual inspection by project-designated competent inspector; use measuring gauges where required. | Proposed: baseline — Weld identification and visual acceptance match [Fill: Visual acceptance and sampling]; repairs are recorded and reinspected. | Guidance only; see Source Register: NSW-QMG, TMR-MRTS78, HUTCHIES-SUITE | Proposed: Each weld or sampling rate defined in project requirements. | Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Weld visual inspection register | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
STE-09 | Specified NDT | Proposed: baseline — Arrange and review only the NDT methods, extent and acceptance specified for the welds. | Proposed: baseline — Match NDT request/report to joint IDs and weld map; verify method, operator, equipment and report disposition as required. | Proposed: baseline — Reports cover [Fill: NDT method, extent and criteria] and report acceptance against the adopted project criteria; untested, rejected or repair-required welds are tracked to closure. | Guidance only; see Source Register: NSW-QMG, TMR-MRTS78, HUTCHIES-SUITE | Proposed: At specified welds/lots and before concealment or coating as required. | Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | NDT request and report register | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
STE-10 | Bolt and fastener receipt | Proposed: baseline — Check bolt assemblies, grade, lot identity, coating/condition and required certificates. | Proposed: baseline — Review packaging marks, certificates and delivery register against connection schedule and installation specification. | Proposed: baseline — Fasteners match [Fill: Bolt system / certificate criteria] and remain identifiable by lot; mixed, damaged or undocumented items are isolated pending disposition. | Guidance only; see Source Register: NSW-QMG, TMR-MRTS78, HUTCHIES-SUITE | Proposed: Each delivery / lot before installation. | Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Fastener register and certificates | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
STE-11 | Bolt installation and verification | Proposed: baseline — Inspect connection assembly, fit, washer/nut arrangement and the project-specified installation/verification evidence. | Proposed: baseline — Observe installation method and examine calibrated tool records or verification tests only where required by project. | Proposed: baseline — Installation and verification satisfy [Fill: Bolt installation / verification criteria]; record connection/member IDs, method and any retightening or replacement. | Guidance only; see Source Register: NSW-QMG, TMR-MRTS78, HUTCHIES-SUITE | Proposed: Each connection group at the project-defined stage and rate. | Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Bolt installation and verification log | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
STE-12 | Protective coating surface preparation | Proposed: baseline — Check substrate preparation, cleanliness, profile and environmental conditions before coating. | Proposed: baseline — Inspect surface against specified coating system and record preparation method/environment; verify traceability before blasting/galvanizing where required. | Proposed: baseline — Surface preparation and conditions meet [Fill: Preparation class / environmental limits] and supplier instructions; contamination or unsuitable conditions are corrected before application. | Guidance only; see Source Register: NSW-QMG, TMR-MRTS78, HUTCHIES-SUITE | Proposed: Each coating lot / shift and before coating. | Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Coating surface-preparation report | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
STE-13 | Coating application and thickness | Proposed: baseline — Inspect applied coating system, coverage, dry film thickness or galvanizing checks as specified. | Proposed: baseline — Review batch records and use specified inspection method/instrument; record calibration and measurement locations. | Proposed: baseline — System, coats, measured values and acceptance comply with [Fill: System, thickness and acceptance]; repair/recoat and reinspection are documented. | Guidance only; see Source Register: NSW-QMG, TMR-MRTS78, HUTCHIES-SUITE | Proposed: Each defined coating lot at specified stages. | Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Coating application and inspection report | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
STE-14 | Fabrication release and delivery | Proposed: baseline — Compile material, dimensional, weld, NDT and coating records; inspect member markings and transport condition. | Proposed: baseline — Review manufacturing data book against member register; inspect before dispatch and again on receipt. | Proposed: baseline — Required manufacturing records are complete; member marks match erection drawings; transport damage is dispositioned before erection. | Guidance only; see Source Register: NSW-QMG, TMR-MRTS78, HUTCHIES-SUITE | Proposed: Each dispatch and receipt lot. | Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Fabrication release and delivery inspection | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
STE-15 | Erection and temporary stability | Proposed: baseline — Check erection sequence, lifting/temporary bracing, member orientation, plumb/level and connection completion against approved erection documents. | Proposed: baseline — Observe erection and survey critical geometry against approved drawings and temporary works/erection method. | Proposed: baseline — Erection follows approved method and [Fill: Erection geometry and release criteria]; temporary stability and connections are confirmed before removing temporary supports. | Guidance only; see Source Register: NSW-QMG, TMR-MRTS78, HUTCHIES-SUITE | Proposed: Each erection sequence / level / frame before releasing temporary supports. | Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Erection inspection and survey record | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
STE-16 | Grout, final connections and closeout | Proposed: baseline — Inspect specified baseplate grout and final connection completion; close out defects and as-built records. | Proposed: baseline — Check grout product, preparation/application records where required; verify final bolt/weld completion, survey and NCR closure. | Proposed: baseline — Grout and connections match approved details and [Fill: Grout / connection / closeout requirements]; outstanding deviations have written design/client disposition before package completion. | Guidance only; see Source Register: NSW-QMG, TMR-MRTS78, HUTCHIES-SUITE | Proposed: At completion and before concealment/load transfer where applicable. | Proposed: [Fill: Person/role proposed to perform this check] performs and records; [Fill: Person/role proposed to review or release this check] reviews where the project assigns review. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Steelwork completion checklist and record pack | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
Point key: H = Proposed Hold Point - use only if assigned in the contract ¦ W = Proposed Witness Point - use only if assigned in the contract ¦ R = Proposed Review ¦ S = Proposed Surveillance ¦ TBC = To be confirmed ¦ N/A = Not applicable. External H/W rights and release rules must come from the project contract and approved process.

## Record Forms
Blank Inspection Record Forms
[Fill: project name] ¦ structural-steel-itp-template ¦ Record actual observations during the work. No results or signatures are pre-filled.
ITP ID / Stage | Inspection / method / acceptance | Location / lot | Date and result | Evidence / record ref. | Performed by / signature | Reviewed by / signature
STE-01 ¦ Planning and submittals | Proposed: baseline — Confirm package boundaries, design documents, construction category, inspection/testing plan and fabrication/erection interfaces. Method: Proposed: baseline — Review approved drawings, specification, annexures and submittal register. Accept when: Proposed: baseline — Current approved [Fill: Approved drawings and revisions], [Fill: Construction category], [Fill: Steel Criteria], [Fill: Approved weld procedure, acceptance and sampling criteria], [Fill: Specified NDT method, extent and acceptance criteria] and [Fill: Project coating system, preparation and inspection criteria] requirements are identified; resolve inconsistencies before fabrication. Record: Steelwork submittal and document register |  | Date: __________ Document title / number: __________ Revision / issue date: __________ Conflict / unresolved interface: __________ Submittal register reference: __________ Result / disposition: __________ Corrective action / retest ref.: __________
STE-02 ¦ Material certificates and traceability | Proposed: baseline — Verify section, plate, bolt and consumable identity and link supplied steel to certificates/heat or batch evidence. Method: Proposed: baseline — Check markings, tags, delivery dockets and certificates against material register and approved grade schedule. Accept when: Proposed: baseline — Material type/grade matches [Fill: Material grades / certification criteria] and each item/lot is traceable to required certification; quarantine unidentified or discrepant material. Record: Steel material register and certificates |  | Date: __________ Member / heat ID: __________ Specified grade: __________ Section / plate size (mm): __________ Certificate reference: __________ Result / disposition: __________ Corrective action / retest ref.: __________
STE-03 ¦ Material condition and storage | Proposed: baseline — Inspect received steel and consumables for damage, corrosion, distortion, contamination and protected storage. Method: Proposed: baseline — Visual inspection on receipt and before use; check storage requirements for consumables. Accept when: Proposed: baseline — Condition remains suitable for specified fabrication/coating; damage or consumable storage excursions are recorded and dispositioned. Record: Incoming steel inspection |  | Date: __________ Item / member: __________ Condition / damage: __________ Disposition ref: __________ Result / disposition: __________ Corrective action / retest ref.: __________
STE-04 ¦ Fabrication set-out and cutting | Proposed: baseline — Check member identity, cut lengths, hole positions, edge preparation and fabrication dimensions. Method: Proposed: baseline — Measure against shop/approved drawings and fabrication schedule before assembly or welding. Accept when: Proposed: baseline — Dimensions and preparation match [Fill: Fabrication dimensions / tolerances]; revisions and approved deviations are traceable. Record: Fabrication dimensional checklist |  | Date: __________ Member mark: __________ Length (mm): __________ Hole / feature position (mm): __________ Edge prep / detail: __________ Result / disposition: __________ Corrective action / retest ref.: __________
STE-05 ¦ Welding documentation readiness | Proposed: baseline — Verify approved welding procedures, weld map, consumables and personnel qualifications required by project. Method: Proposed: baseline — Review WPS, procedure qualification evidence, welder qualifications/continuity and consumable records against weld schedule. Accept when: Proposed: baseline — Applicable WPS and qualifications cover the specified joint/material/process under [Fill: Weld procedure/qualification requirements]; missing or mismatched coverage is resolved before welding. Record: Welding document and qualification register |  | Date: __________ WPS ID/revision: __________ Welder ID: __________ Qualification record ref: __________ Consumable batch: __________ Result / disposition: __________ Corrective action / retest ref.: __________
STE-06 ¦ Fit-up and joint preparation | Proposed: baseline — Inspect joint preparation, root gap, alignment, cleanliness, backing and fit-up before welding. Method: Proposed: baseline — Visual and dimensional checks against approved joint detail and applicable WPS. Accept when: Proposed: baseline — Fit-up satisfies [Fill: Joint fit-up acceptance] and WPS; defects, unapproved tacks or mismatch are corrected before welding. Record: Weld fit-up inspection |  | Date: __________ Joint ID: __________ Root gap (mm): __________ Mismatch / alignment (mm): __________ WPS ID: __________ Result / disposition: __________ Corrective action / retest ref.: __________
STE-07 ¦ Welding process controls | Proposed: baseline — Check weld execution records include joint identity, WPS, welder, date and any specified environmental/process controls. Method: Proposed: baseline — Observe/record welding and review production logs against approved WPS and project requirements. Accept when: Proposed: baseline — Work is performed within the applicable approved WPS and [Fill: Welding process variables / controls]; interruptions, repairs and deviations are traceable. Record: Welding production log |  | Date: __________ Joint ID: __________ WPS ID: __________ Welder ID: __________ Weld date: __________ Repair cycle ref: __________ Result / disposition: __________ Corrective action / retest ref.: __________
STE-08 ¦ Completed weld visual inspection | Proposed: baseline — Inspect completed welds for profile, visible defects, size and completion against weld map and acceptance criteria. Method: Proposed: baseline — Visual inspection by project-designated competent inspector; use measuring gauges where required. Accept when: Proposed: baseline — Weld identification and visual acceptance match [Fill: Visual acceptance and sampling]; repairs are recorded and reinspected. Record: Weld visual inspection register |  | Date: __________ Joint ID: __________ Measured weld size (mm): __________ Visual result: __________ Repair / reinspection ref: __________ Result / disposition: __________ Corrective action / retest ref.: __________
STE-09 ¦ Specified NDT | Proposed: baseline — Arrange and review only the NDT methods, extent and acceptance specified for the welds. Method: Proposed: baseline — Match NDT request/report to joint IDs and weld map; verify method, operator, equipment and report disposition as required. Accept when: Proposed: baseline — Reports cover [Fill: NDT method, extent and criteria] and report acceptance against the adopted project criteria; untested, rejected or repair-required welds are tracked to closure. Record: NDT request and report register |  | Date: __________ Joint ID: __________ NDT method: __________ Extent / coverage: __________ Report ref: __________ Result / disposition: __________ Result / disposition: __________ Corrective action / retest ref.: __________
STE-10 ¦ Bolt and fastener receipt | Proposed: baseline — Check bolt assemblies, grade, lot identity, coating/condition and required certificates. Method: Proposed: baseline — Review packaging marks, certificates and delivery register against connection schedule and installation specification. Accept when: Proposed: baseline — Fasteners match [Fill: Bolt system / certificate criteria] and remain identifiable by lot; mixed, damaged or undocumented items are isolated pending disposition. Record: Fastener register and certificates |  | Date: __________ Lot / batch: __________ Nominal diameter (mm): __________ Specified grade: __________ Certificate ref: __________ Result / disposition: __________ Corrective action / retest ref.: __________
STE-11 ¦ Bolt installation and verification | Proposed: baseline — Inspect connection assembly, fit, washer/nut arrangement and the project-specified installation/verification evidence. Method: Proposed: baseline — Observe installation method and examine calibrated tool records or verification tests only where required by project. Accept when: Proposed: baseline — Installation and verification satisfy [Fill: Bolt installation / verification criteria]; record connection/member IDs, method and any retightening or replacement. Record: Bolt installation and verification log |  | Date: __________ Connection ID: __________ Bolt lot: __________ Installation method: __________ Verification reading/result: __________ Tool ID / calibration: __________ Result / disposition: __________ Corrective action / retest ref.: __________
STE-12 ¦ Protective coating surface preparation | Proposed: baseline — Check substrate preparation, cleanliness, profile and environmental conditions before coating. Method: Proposed: baseline — Inspect surface against specified coating system and record preparation method/environment; verify traceability before blasting/galvanizing where required. Accept when: Proposed: baseline — Surface preparation and conditions meet [Fill: Preparation class / environmental limits] and supplier instructions; contamination or unsuitable conditions are corrected before application. Record: Coating surface-preparation report |  | Date: __________ Member / lot: __________ Specified / observed prep grade: __________ Profile result: __________ Conditions / dew point if required: __________ Result / disposition: __________ Corrective action / retest ref.: __________
STE-13 ¦ Coating application and thickness | Proposed: baseline — Inspect applied coating system, coverage, dry film thickness or galvanizing checks as specified. Method: Proposed: baseline — Review batch records and use specified inspection method/instrument; record calibration and measurement locations. Accept when: Proposed: baseline — System, coats, measured values and acceptance comply with [Fill: System, thickness and acceptance]; repair/recoat and reinspection are documented. Record: Coating application and inspection report |  | Date: __________ Member / location: __________ Coat / system: __________ Measured thickness (µm): __________ Instrument ID: __________ Repair / recheck ref: __________ Result / disposition: __________ Corrective action / retest ref.: __________
STE-14 ¦ Fabrication release and delivery | Proposed: baseline — Compile material, dimensional, weld, NDT and coating records; inspect member markings and transport condition. Method: Proposed: baseline — Review manufacturing data book against member register; inspect before dispatch and again on receipt. Accept when: Proposed: baseline — Required manufacturing records are complete; member marks match erection drawings; transport damage is dispositioned before erection. Record: Fabrication release and delivery inspection |  | Date: __________ Member mark: __________ Dispatch docket: __________ Damage / disposition: __________ Dossier ref: __________ Result / disposition: __________ Corrective action / retest ref.: __________
STE-15 ¦ Erection and temporary stability | Proposed: baseline — Check erection sequence, lifting/temporary bracing, member orientation, plumb/level and connection completion against approved erection documents. Method: Proposed: baseline — Observe erection and survey critical geometry against approved drawings and temporary works/erection method. Accept when: Proposed: baseline — Erection follows approved method and [Fill: Erection geometry and release criteria]; temporary stability and connections are confirmed before removing temporary supports. Record: Erection inspection and survey record |  | Date: __________ Grid / level: __________ Member mark: __________ Plumb / alignment (mm): __________ Survey ref: __________ Result / disposition: __________ Corrective action / retest ref.: __________
STE-16 ¦ Grout, final connections and closeout | Proposed: baseline — Inspect specified baseplate grout and final connection completion; close out defects and as-built records. Method: Proposed: baseline — Check grout product, preparation/application records where required; verify final bolt/weld completion, survey and NCR closure. Accept when: Proposed: baseline — Grout and connections match approved details and [Fill: Grout / connection / closeout requirements]; outstanding deviations have written design/client disposition before package completion. Record: Steelwork completion checklist and record pack |  | Date: __________ Baseplate / location: __________ Grout batch: __________ Release evidence: __________ NCR / disposition ref: __________ Result / disposition: __________ Corrective action / retest ref.: __________

## Source Register
Source Register
Source ID | Title | Revision / check | Type | Path / URL
NSW-QMG | NSW Government Quality Management Guidelines for Construction, Appendix D (ITP guidance) | See linked source; verify current edition and project adoption | guidance | https://www.info.buy.nsw.gov.au/resources/construction/quality-management-guidelines-for-construction
TMR-MRTS78 | Queensland TMR MRTS78 Fabrication of Structural Steelwork (November 2020) | See linked source; verify current edition and project adoption | guidance | https://www.tmr.qld.gov.au/_/media/busind/techstdpubs/specifications-and-drawings/specifications/2-bridges-and-structures/mrts78.pdf?extension=pdf&hash=50EAAB111B231F1443975ABF3F281175&rev=13c320fd75b648a5b31908b182c84091&sc_lang=en&size=1765061
HUTCHIES-SUITE | Hutchinson Builders, Construction ITPs and Reports suite (downloadable Word examples) | See linked source; verify current edition and project adoption | guidance | https://subbies.hutchies.com.au/resources/videos/safety-and-quality-planning

## Confirmations
Open Confirmations
Issue ID | Priority | ITP rows | Open item | Action needed
CONF-001 | confirmation | STE-01 | STE-01: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-002 | confirmation | STE-02 | STE-02: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-003 | confirmation | STE-03 | STE-03: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-004 | confirmation | STE-04 | STE-04: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-005 | confirmation | STE-05 | STE-05: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-006 | confirmation | STE-06 | STE-06: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-007 | confirmation | STE-07 | STE-07: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-008 | confirmation | STE-08 | STE-08: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-009 | confirmation | STE-09 | STE-09: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-010 | confirmation | STE-10 | STE-10: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-011 | confirmation | STE-11 | STE-11: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-012 | confirmation | STE-12 | STE-12: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-013 | confirmation | STE-13 | STE-13: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-014 | confirmation | STE-14 | STE-14: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-015 | confirmation | STE-15 | STE-15: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-016 | confirmation | STE-16 | STE-16: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.