## Start here
Switchboard Installation ITP Template
Ordinary building low-voltage switchboard installation from approved design/submittal through verification and handover readiness. Covers only the identified project package and approved drawings. Excludes high voltage, hazardous areas, generation/storage/PV, fire alarm, security, communications/data, specialist controls and utility/network-owned works unless separately identified and supported by project-specific scope. No live-work guide is provided. Electrical work and tests belong to appropriately licensed/authorised personnel under applicable jurisdictional law; project values, legal Hold/Witness points and release authority are not supplied.
Status | Free editable proposed baseline. It is not project-approved and is not evidence that work was inspected.
Project fields | Complete the project, jurisdiction, parties, document number/revision and scope in the controlled project copy.
Technical criteria | Replace every [Enter ...] prompt with the exact contract, approved drawing, specification or procedure reference and project condition. Confirm adopted editions and resolve conflicts.
Frequency and lot | These rows show proposed activity triggers only. Set the actual lot, sampling basis and frequency from project requirements.
Roles and control points | Confirm performing/reviewing roles, contractual or regulatory H/W rights, notice, evidence and release authority. No external control point is assigned.
Conditional work | Remove out-of-scope work or mark it not applicable with a reason. Include only processes required for this project.
Records | Use the matching blank Records sheet. Enter actual inspection date, observation, result and signature only when work is performed.
Evidence | Retain original certificates, test reports, survey records, photographs and written dispositions; index them rather than replacing them with a tick.
Scope boundary | Ordinary building low-voltage switchboard installation from approved design/submittal through verification and handover readiness. Covers only the identified project package and approved drawings. Excludes high voltage, hazardous areas, generation/storage/PV, fire alarm, security, communications/data, specialist controls and utility/network-owned works unless separately identified and supported by project-specific scope. No live-work guide is provided. Electrical work and tests belong to appropriately licensed/authorised personnel under applicable jurisdictional law; project values, legal Hold/Witness points and release authority are not supplied.
Project source prompts | Jurisdiction and regulator basis: Identify state/territory, electrical safety regulator, applicable licence classes, adopted requirements and notification/certificate rules; confirm current law. Approved electrical drawings and revisions: Identify controlled layouts, single-line diagrams, schedules, details and approved changes. Project specification and adopted standards: List exact project requirements, edition/revision and clauses from controlled sources; do not assume an edition. Electrical work scope and boundaries: Identify included circuits, equipment, work areas, package limits, interfaces and exclusions. Approved equipment and product evidence: Identify approved switchboards, protective devices, cables, accessories and required product evidence. Licensed roles, reviews and release authority: Identify licensed electrical contractor/worker, designer, inspector, network operator and contractual review/release roles; do not infer authority. Project verification and test criteria: Enter applicable test methods, acceptance criteria, coverage and record from current jurisdiction/project sources; no values supplied. Isolation and alternate supply arrangements: Identify all supply sources, isolation/lockout coordination and approved work controls; this baseline contains no live-work procedure. Certificates, test records and handover: Identify jurisdictional certificates, test schedules, as-builts, board schedules and dossier requirements. Network connection / energisation interface: Identify who requests inspection/connection, network owner prerequisites and separate supply-authorisation decision.

## ITP
Switchboard Installation ITP Template ¦ Proposed Inspection and Test Plan
Document number: [Enter] Revision: [Enter] Date: [Enter] Project: [Enter] Jurisdiction: [Enter] Contractor: [Enter] Ordinary building low-voltage switchboard installation from approved design/submittal through verification and handover readiness. Covers only the identified project package and approved drawings. Excludes high voltage, hazardous areas, generation/storage/PV, fire alarm, security, communications/data, specialist controls and utility/network-owned works unless separately identified and supported by project-specific scope. No live-work guide is provided. Electrical work and tests belong to appropriately licensed/authorised personnel under applicable jurisdictional law; project values, legal Hold/Witness points and release authority are not supplied.
ITP field | Proposed plan entry
SWB-01 | SWB-01 ¦ Board design, rating and interface release
Inspection / test | Confirm board scope, location, single-line diagram, supply boundary and approved technical submittals.
Method | Review approved board schedule, drawings, supply/network interface, fault-level/design inputs and assigned designer decisions; do not calculate or select ratings in this baseline.
Project acceptance condition | Board identity, design basis, project interfaces and required approvals are traceable to current controlled documents before procurement or installation. Project source: [Enter Approved electrical drawings and revisions]; [Enter Project specification and adopted standards]; [Enter Jurisdiction and regulator basis]. Supporting controlled inputs: [Enter Approved equipment and product evidence]; [Enter Network connection / energisation interface].
Reference / locator | Enter actual controlled project document, revision and locator; see Source Register for topic guidance.
Trigger / frequency | Proposed: Check the identified circuit, board or work lot before concealment or the next activity removes access; project coverage and timing must be confirmed.
Performing / reviewing role | Proposed: Assigned appropriately licensed electrical contractor/worker performs and records electrical work and tests within their authority. Other review roles act only within documented jurisdictional or contractual authority. Project role basis: [Enter Licensed roles, reviews and release authority]
Control point / external party | Proposed: Contractor check only. Confirm any statutory inspection, contractual Hold/Witness point, notice and release authority from jurisdiction and contract; none is assigned by this template. Project basis: [Enter Licensed roles, reviews and release authority]; [Enter Jurisdiction and regulator basis]
Notice / release evidence | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external release authority is assigned.
Record | Switchboard design and interface register
Applicability / remarks | Include when this activity is in the contracted work package. Baseline topic only. Resolve project criteria from the controlling source and preserve document/revision/clause or drawing/sheet/item locator; do not enter guessed values, inspection rates, legal H/W points or signatures.
SWB-02 | SWB-02 ¦ Receipt, identity and condition
Inspection / test | Inspect delivered switchboard and components against approved equipment schedule and supplier documents.
Method | Match board ID, assembly configuration, device schedule and certificates to approved submittal; inspect transport condition and record discrepancies for disposition.
Project acceptance condition | Delivered assembly and evidence match approved schedule; damage or substitutions are accepted by assigned authority before installation. Project source: [Enter Approved electrical drawings and revisions]; [Enter Project specification and adopted standards]; [Enter Jurisdiction and regulator basis]. Supporting controlled inputs: [Enter Approved equipment and product evidence].
Reference / locator | Enter actual controlled project document, revision and locator; see Source Register for topic guidance.
Trigger / frequency | Proposed: Check the identified circuit, board or work lot before concealment or the next activity removes access; project coverage and timing must be confirmed.
Performing / reviewing role | Proposed: Assigned appropriately licensed electrical contractor/worker performs and records electrical work and tests within their authority. Other review roles act only within documented jurisdictional or contractual authority. Project role basis: [Enter Licensed roles, reviews and release authority]
Control point / external party | Proposed: Contractor check only. Confirm any statutory inspection, contractual Hold/Witness point, notice and release authority from jurisdiction and contract; none is assigned by this template. Project basis: [Enter Licensed roles, reviews and release authority]; [Enter Jurisdiction and regulator basis]
Notice / release evidence | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external release authority is assigned.
Record | Receipt, identity and condition inspection record
Applicability / remarks | Include when this activity is in the contracted work package. Baseline topic only. Resolve project criteria from the controlling source and preserve document/revision/clause or drawing/sheet/item locator; do not enter guessed values, inspection rates, legal H/W points or signatures.
SWB-03 | SWB-03 ¦ Room, plinth and mounting readiness
Inspection / test | Inspect switchboard location, mounting surface, access and service entries before positioning.
Method | Compare room/location, support/plinth, access and entry points with approved drawings and coordination requirements; record unresolved builder/service interfaces.
Project acceptance condition | Installation location and support/interface arrangements satisfy approved project documents and manufacturer requirements; no generic clearance values are supplied. Project source: [Enter Approved electrical drawings and revisions]; [Enter Project specification and adopted standards]; [Enter Jurisdiction and regulator basis]. Supporting controlled inputs: [Enter Approved equipment and product evidence].
Reference / locator | Enter actual controlled project document, revision and locator; see Source Register for topic guidance.
Trigger / frequency | Proposed: Check the identified circuit, board or work lot before concealment or the next activity removes access; project coverage and timing must be confirmed.
Performing / reviewing role | Proposed: Assigned appropriately licensed electrical contractor/worker performs and records electrical work and tests within their authority. Other review roles act only within documented jurisdictional or contractual authority. Project role basis: [Enter Licensed roles, reviews and release authority]
Control point / external party | Proposed: Contractor check only. Confirm any statutory inspection, contractual Hold/Witness point, notice and release authority from jurisdiction and contract; none is assigned by this template. Project basis: [Enter Licensed roles, reviews and release authority]; [Enter Jurisdiction and regulator basis]
Notice / release evidence | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external release authority is assigned.
Record | Room, plinth and mounting readiness inspection record
Applicability / remarks | Include when this activity is in the contracted work package. Baseline topic only. Resolve project criteria from the controlling source and preserve document/revision/clause or drawing/sheet/item locator; do not enter guessed values, inspection rates, legal H/W points or signatures.
SWB-04 | SWB-04 ¦ Placement, enclosure and cable entries
Inspection / test | Inspect installed board alignment, anchorage, enclosure integrity, entry treatment and identification before termination.
Method | Use approved installation instructions and drawings; inspect visible condition, board identity, entries, covers and labels; record deviations before energisation planning.
Project acceptance condition | Assembly is installed to approved instructions/documents, remains intact and identifiable, and deviations are dispositioned. Project source: [Enter Approved electrical drawings and revisions]; [Enter Project specification and adopted standards]; [Enter Jurisdiction and regulator basis]. Supporting controlled inputs: [Enter Approved equipment and product evidence]; [Enter Network connection / energisation interface].
Reference / locator | Enter actual controlled project document, revision and locator; see Source Register for topic guidance.
Trigger / frequency | Proposed: Check the identified circuit, board or work lot before concealment or the next activity removes access; project coverage and timing must be confirmed.
Performing / reviewing role | Proposed: Assigned appropriately licensed electrical contractor/worker performs and records electrical work and tests within their authority. Other review roles act only within documented jurisdictional or contractual authority. Project role basis: [Enter Licensed roles, reviews and release authority]
Control point / external party | Proposed: Contractor check only. Confirm any statutory inspection, contractual Hold/Witness point, notice and release authority from jurisdiction and contract; none is assigned by this template. Project basis: [Enter Licensed roles, reviews and release authority]; [Enter Jurisdiction and regulator basis]
Notice / release evidence | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external release authority is assigned.
Record | Placement, enclosure and cable entries inspection record
Applicability / remarks | Include when this activity is in the contracted work package. Baseline topic only. Resolve project criteria from the controlling source and preserve document/revision/clause or drawing/sheet/item locator; do not enter guessed values, inspection rates, legal H/W points or signatures.
SWB-05 | SWB-05 ¦ Incoming/outgoing connections and earthing
Inspection / test | Check documented completion of identified incoming/outgoing terminations, protective conductors and bonding interfaces.
Method | Assigned electrical worker verifies against approved single-line, schedules, connection details and supplier instructions; record circuit/device identity and required torque/tool evidence only if specified.
Project acceptance condition | Connections and earthing/bonding are complete to controlling sources; no torque, conductor size or setting is inferred by this template. Project source: [Enter Approved electrical drawings and revisions]; [Enter Project specification and adopted standards]; [Enter Jurisdiction and regulator basis]. Supporting controlled inputs: [Enter Approved equipment and product evidence]; [Enter Network connection / energisation interface].
Reference / locator | Enter actual controlled project document, revision and locator; see Source Register for topic guidance.
Trigger / frequency | Proposed: Check the identified circuit, board or work lot before concealment or the next activity removes access; project coverage and timing must be confirmed.
Performing / reviewing role | Proposed: Assigned appropriately licensed electrical contractor/worker performs and records electrical work and tests within their authority. Other review roles act only within documented jurisdictional or contractual authority. Project role basis: [Enter Licensed roles, reviews and release authority]
Control point / external party | Proposed: Contractor check only. Confirm any statutory inspection, contractual Hold/Witness point, notice and release authority from jurisdiction and contract; none is assigned by this template. Project basis: [Enter Licensed roles, reviews and release authority]; [Enter Jurisdiction and regulator basis]
Notice / release evidence | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external release authority is assigned.
Record | Incoming/outgoing connections and earthing inspection record
Applicability / remarks | Include when this activity is in the contracted work package. Baseline topic only. Resolve project criteria from the controlling source and preserve document/revision/clause or drawing/sheet/item locator; do not enter guessed values, inspection rates, legal H/W points or signatures.
SWB-06 | SWB-06 ¦ Protection devices and settings
Inspection / test | Verify protective device identity, labels and settings documentation against approved design/schedules before functional verification.
Method | Compare installed device references and recorded settings to approved coordination/design documents; any change is referred to responsible designer and recorded.
Project acceptance condition | Installed devices and settings evidence match approved design documents; no protective setting or performance threshold is supplied. Project source: [Enter Approved electrical drawings and revisions]; [Enter Project specification and adopted standards]; [Enter Jurisdiction and regulator basis]. Supporting controlled inputs: [Enter Approved equipment and product evidence]; [Enter Project verification and test criteria].
Reference / locator | Enter actual controlled project document, revision and locator; see Source Register for topic guidance.
Trigger / frequency | Proposed: Check the identified circuit, board or work lot before concealment or the next activity removes access; project coverage and timing must be confirmed.
Performing / reviewing role | Proposed: Assigned appropriately licensed electrical contractor/worker performs and records electrical work and tests within their authority. Other review roles act only within documented jurisdictional or contractual authority. Project role basis: [Enter Licensed roles, reviews and release authority]
Control point / external party | Proposed: Contractor check only. Confirm any statutory inspection, contractual Hold/Witness point, notice and release authority from jurisdiction and contract; none is assigned by this template. Project basis: [Enter Licensed roles, reviews and release authority]; [Enter Jurisdiction and regulator basis]
Notice / release evidence | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external release authority is assigned.
Record | Protection devices and settings inspection record
Applicability / remarks | Include when this activity is in the contracted work package. Baseline topic only. Resolve project criteria from the controlling source and preserve document/revision/clause or drawing/sheet/item locator; do not enter guessed values, inspection rates, legal H/W points or signatures.
SWB-07 | SWB-07 ¦ Verification, functional checks and test evidence
Inspection / test | Review required switchboard tests and functional/sequence evidence for identified board and circuits.
Method | Assigned licensed electrical worker performs required verification under applicable sources; record scope, method, device IDs, instruments and actual results. This is not an instruction for live testing.
Project acceptance condition | Required examination and test evidence meets jurisdictional and project acceptance sources; defects, exclusions and retests are traceable. Project source: [Enter Approved electrical drawings and revisions]; [Enter Project specification and adopted standards]; [Enter Jurisdiction and regulator basis]. Supporting controlled inputs: [Enter Approved equipment and product evidence]; [Enter Project verification and test criteria].
Reference / locator | Enter actual controlled project document, revision and locator; see Source Register for topic guidance.
Trigger / frequency | Proposed: Check the identified circuit, board or work lot before concealment or the next activity removes access; project coverage and timing must be confirmed.
Performing / reviewing role | Proposed: Assigned appropriately licensed electrical contractor/worker performs and records electrical work and tests within their authority. Other review roles act only within documented jurisdictional or contractual authority. Project role basis: [Enter Licensed roles, reviews and release authority]
Control point / external party | Proposed: Contractor check only. Confirm any statutory inspection, contractual Hold/Witness point, notice and release authority from jurisdiction and contract; none is assigned by this template. Project basis: [Enter Licensed roles, reviews and release authority]; [Enter Jurisdiction and regulator basis]
Notice / release evidence | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external release authority is assigned.
Record | Verification, functional checks and test evidence inspection record
Applicability / remarks | Include when this activity is in the contracted work package. Baseline topic only. Resolve project criteria from the controlling source and preserve document/revision/clause or drawing/sheet/item locator; do not enter guessed values, inspection rates, legal H/W points or signatures.
SWB-08 | SWB-08 ¦ Pre-energisation readiness and network interface
Inspection / test | Confirm installation test/certificate package and outstanding defects are ready for the distinct energisation and supply-connection process.
Method | Review test record, certificate, approved as-builts, outstanding-work register, isolation/source plan and network operator/retailer prerequisites; identify who controls each release.
Project acceptance condition | Contractor completion and required certificates are documented; contractual acceptance, statutory inspection and network/supply connection approvals are separately obtained from their authorised parties. This check does not authorise energisation. Project source: [Enter Approved electrical drawings and revisions]; [Enter Project specification and adopted standards]; [Enter Jurisdiction and regulator basis]. Supporting controlled inputs: [Enter Approved equipment and product evidence]; [Enter Project verification and test criteria]; [Enter Network connection / energisation interface].
Reference / locator | Enter actual controlled project document, revision and locator; see Source Register for topic guidance.
Trigger / frequency | Proposed: Check the identified circuit, board or work lot before concealment or the next activity removes access; project coverage and timing must be confirmed.
Performing / reviewing role | Proposed: Assigned appropriately licensed electrical contractor/worker performs and records electrical work and tests within their authority. Other review roles act only within documented jurisdictional or contractual authority. Project role basis: [Enter Licensed roles, reviews and release authority]
Control point / external party | Proposed: Contractor check only. Confirm any statutory inspection, contractual Hold/Witness point, notice and release authority from jurisdiction and contract; none is assigned by this template. Project basis: [Enter Licensed roles, reviews and release authority]; [Enter Jurisdiction and regulator basis]
Notice / release evidence | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external release authority is assigned.
Record | Switchboard pre-energisation readiness and connection interface record
Applicability / remarks | Include when this activity is in the contracted work package. Baseline topic only. Resolve project criteria from the controlling source and preserve document/revision/clause or drawing/sheet/item locator; do not enter guessed values, inspection rates, legal H/W points or signatures.

## Records
Blank Inspection Record Prompts
Complete during actual work. Actual result, date, names, approvals and signatures are intentionally blank. Retain original third-party reports.
ITP ID / event | Record field | Actual entry / observation | Evidence / report ref. | Disposition / action ref. | Performed by / date | Reviewed / decision ref.
SWB-01 | Board ID / supply boundary
SWB-01 | Single-line / equipment schedule revision
SWB-01 | Design rating / setting approval reference
SWB-01 | Manufacturer / assembly evidence reference
SWB-01 | Supply / metering interface owner
SWB-01 | Unresolved design decision
SWB-01 | Date / location / lot / result / status |  | Original report / photo / attachment reference | NCR / correction / recheck reference | Actual performer and date | Assigned review / decision reference
SWB-02 | Board ID / serial / supplier
SWB-02 | Assembly / device schedule revision
SWB-02 | Approved submittal / supplier evidence
SWB-02 | Transport condition / photo reference
SWB-02 | Discrepancy / authorised disposition
SWB-02 | Date / location / lot / result / status |  | Original report / photo / attachment reference | NCR / correction / recheck reference | Actual performer and date | Assigned review / decision reference
SWB-03 | Board / room / location
SWB-03 | Plinth / mounting detail revision
SWB-03 | Access / entry criteria source
SWB-03 | Actual observed or measured condition / unit
SWB-03 | Builder interface / outstanding item
SWB-03 | Date / location / lot / result / status |  | Original report / photo / attachment reference | NCR / correction / recheck reference | Actual performer and date | Assigned review / decision reference
SWB-04 | Board ID / installed location
SWB-04 | Mounting / anchorage detail
SWB-04 | Enclosure / entry treatment evidence
SWB-04 | Labels / covers / visible condition
SWB-04 | Deviation / correction / recheck reference
SWB-04 | Date / location / lot / result / status |  | Original report / photo / attachment reference | NCR / correction / recheck reference | Actual performer and date | Assigned review / decision reference
SWB-05 | Board / terminal / circuit ID
SWB-05 | Cable / conductor identification
SWB-05 | Connection / bonding detail revision
SWB-05 | Supplier torque / tool evidence if required
SWB-05 | Observed completion / defect
SWB-05 | Separate verification evidence reference
SWB-05 | Date / location / lot / result / status |  | Original report / photo / attachment reference | NCR / correction / recheck reference | Actual performer and date | Assigned review / decision reference
SWB-06 | Board / device / circuit identity
SWB-06 | Approved protection study / schedule revision
SWB-06 | Specified setting / unit / source locator
SWB-06 | Actual recorded setting / unit / evidence
SWB-06 | Label / device match
SWB-06 | Design change / authorised decision reference
SWB-06 | Date / location / lot / result / status |  | Original report / photo / attachment reference | NCR / correction / recheck reference | Actual performer and date | Assigned review / decision reference
SWB-07 | Board / circuit / function
SWB-07 | Verification scope and exclusions
SWB-07 | Approved method / criterion / source
SWB-07 | Instrument / original report reference
SWB-07 | Actual result / unit
SWB-07 | Failure / correction / retest link
SWB-07 | Licensed verification role / evidence
SWB-07 | Date / location / lot / result / status |  | Original report / photo / attachment reference | NCR / correction / recheck reference | Actual performer and date | Assigned review / decision reference
SWB-08 | Board / installation boundary
SWB-08 | Verification report / unresolved defects
SWB-08 | Jurisdiction certificate / issuer
SWB-08 | Required independent inspection evidence
SWB-08 | Contractual review / disposition reference
SWB-08 | Network / metering / connection prerequisite
SWB-08 | Source / isolation plan reference
SWB-08 | Actual connection decision / authorised party reference
SWB-08 | Date / location / lot / result / status |  | Original report / photo / attachment reference | NCR / correction / recheck reference | Actual performer and date | Assigned review / decision reference

## Source Register
Topic Guidance Source Register
Source ID | Title | Locator and URL | Use and limitation
QLD-TEST-LV | WorkSafe Queensland Electrical Safety Office, Testing | Accessed 7 October 2026; sections Who can test electrical equipment; What is energised electrical work; When is testing a form of energised electrical work; de-energised and isolated testing; requirements for energised testing. https://www.worksafe.qld.gov.au/safety-and-prevention/hazards/electricity/testing | Queensland-specific regulator guidance supports licensed testing and distinction between de-energised/isolated testing and energised work, including testing for dead. Use only as topic guidance; confirm current law and licensing in the project jurisdiction. No live-work procedure or numeric test criteria reproduced.
QLD-ESO-GUIDES | WorkSafe Queensland Electrical Safety Office, Electrical Safety Office technical guides | Accessed 7 October 2026; sections Guide to testing low voltage electrical installations, Guide to working on electrical installations with connections to alternate supplies, Guide to isolation and lockout procedures, Guide to service and submain polarity testing. https://www.worksafe.qld.gov.au/eso-technical-guides | Queensland regulator topic guidance for installation verification, alternate supplies and isolation/lockout. Apply only after confirming jurisdiction and current issue; it does not supply project acceptance values or project H/W points.
QLD-CERT | WorkSafe Queensland Electrical Safety Office, Issuing certificates of compliance | Accessed 7 October 2026; Requirements of certificates and FAQ: issuer, when certificate required, tested installation details, recipient, retention and signature. https://www.worksafe.qld.gov.au/laws-and-compliance/electrical-safety-laws/issuing-certificates-of-compliance | Queensland-specific example of electrical contractor certification following installation work. Do not generalise certificate name, trigger, retention or signatory rules nationally; identify applicable jurisdictional certificates from the regulator.
NSW-SIR-2026 | NSW Government, NSW Service and Installation Rules, April 2026 | Official PDF accessed 7 October 2026; sections for service and installation requirements, inspection/testing, certificates and supply connection (specific clause locator to be confirmed against applicable network rules). https://www.energy.nsw.gov.au/sites/default/files/2026-05/Service-and-Installation-Rules-NSW-April-2026.pdf | NSW-specific service/network interface reference only. Use to prompt separate network-owner connection and service requirements; not a national installation criterion or approval by this template.
SA-OTR-VERIFY | South Australia Office of the Technical Regulator, Electrical trades and testing/verification resources | Accessed 7 October 2026; Testing and verification section and linked Visual Inspection and Verification Form / Schedule of Test Results. The public form groups checks under general, consumers mains, switchboards, wiring systems, electrical equipment and earthing. https://www.energymining.sa.gov.au/industry/regulatory-services/office-of-the-technical-regulator/electrical-trades | Public example of inspection and test-record structure and separate compliance/reconnection interface. South Australia only; do not import its legal steps into another jurisdiction or use its form as project acceptance criteria.
VIC-DEFECTS | Energy Safe Victoria, Electrical installation defects | Accessed 7 October 2026; updated defect list and Top 10 Prescribed Inspections General defects, including switchboard, visual inspection and wiring-system topics. https://www.energysafe.vic.gov.au/certificates-electrical-safety/electrical-installation-defects | Victoria-specific public defect taxonomy supporting practical inspection topics and location-specific defect records. It is not a substitute for the adopted project standard or inspection by an authorised inspector.
VIC-POWER-INSPECTION | Energy Safe Victoria, Ensuring power is off until inspection FAQ | Accessed 7 October 2026; FAQ on keeping power off until inspection, including prescribed work and switchboard replacement context. https://www.energysafe.vic.gov.au/industry-guidance/electrical/frequently-asked-questions/ensuring-power-until-inspection | Victoria-specific illustration that inspection timing and restoration-of-supply requirements can be jurisdictional and work-type dependent. Do not generalise its rules nationally; confirm the actual local pathway and responsible party.