## Start here
Utility Trench Bedding, Surround and Backfill Inspection and Test Plan Template
Reusable baseline for ordinary utility trench earthworks from clearance and formation through bedding, pre-cover inspection, surround, backfill, specified earthworks verification and handover. Excludes structural trench support design, deep excavation engineering, pipe-system pressure/leak testing, commissioning, disinfection and utility-owner operational acceptance.
Status | Free editable proposed baseline. It is not project-approved and is not evidence that work was inspected.
Project fields | Complete the project, jurisdiction, parties, document number/revision and scope in the controlled project copy.
Technical criteria | Replace every [Enter ...] prompt with the exact contract, approved drawing, specification or procedure reference and project condition. Confirm adopted editions and resolve conflicts.
Frequency and lot | These rows show proposed activity triggers only. Set the actual lot, sampling basis and frequency from project requirements.
Roles and control points | Confirm performing/reviewing roles, contractual or regulatory H/W rights, notice, evidence and release authority. No external control point is assigned.
Conditional work | Remove out-of-scope work or mark it not applicable with a reason. Include only processes required for this project.
Records | Use the matching blank Records sheet. Enter actual inspection date, observation, result and signature only when work is performed.
Evidence | Retain original certificates, test reports, survey records, photographs and written dispositions; index them rather than replacing them with a tick.
Scope boundary | Reusable baseline for ordinary utility trench earthworks from clearance and formation through bedding, pre-cover inspection, surround, backfill, specified earthworks verification and handover. Excludes structural trench support design, deep excavation engineering, pipe-system pressure/leak testing, commissioning, disinfection and utility-owner operational acceptance.
Project source prompts | Project jurisdiction / authority context: State or territory and any authority or contract scope that governs the work. Approved civil / services drawings and revisions: Identify controlled plans, sections, set-out details, levels and applicable drawing items. Project earthworks specification and adopted standards: Identify contract clauses, adopted editions, annexures and precedence. Geotechnical design basis and disposition roles: Identify the report, design zones and who provides any specified founding or changed-ground disposition. Material source, classification and use schedule: Identify approved source, permitted use and project material criteria; do not infer a class. Project testing, lotting and reporting plan: Enter nominated methods, test locations, lot definition, rate, acceptance and laboratory role. Survey control, geometry and closeout requirements: Identify control, design geometry, tolerances, as-built format and responsible survey role. Service clearance and permit process: Identify current service information, locating, protection and permit requirements. Service and work-package interfaces: Identify exact trench, building, pavement or service boundaries and owner handover/testing responsibilities. Performing, reviewing and contractual release roles: Identify assigned roles, notice period, evidence, and contractual Hold/Witness or release conditions. Project records and handover requirements: Identify required registers, reports, photos, dispositions and handover submission.

## ITP
Utility Trench Bedding, Surround and Backfill Inspection and Test Plan Template ¦ Proposed Inspection and Test Plan
Document number: [Enter] Revision: [Enter] Date: [Enter] Project: [Enter] Jurisdiction: [Enter] Contractor: [Enter] Reusable baseline for ordinary utility trench earthworks from clearance and formation through bedding, pre-cover inspection, surround, backfill, specified earthworks verification and handover. Excludes structural trench support design, deep excavation engineering, pipe-system pressure/leak testing, commissioning, disinfection and utility-owner operational acceptance.
ITP field | Proposed plan entry
UTB-01 | UTB-01 ¦ Trench package, service information and approvals
Inspection / test | Confirm pipe/service identity, route, trench zones, interfaces, bedding/surround/backfill requirements and project test/handover basis.
Method | Review approved service drawings, specifications, utility owner information, installation instructions and project responsibilities; identify commissioning/testing as an interface only.
Project acceptance condition | Current controlled documents define the included trench extent, service system and zone-specific requirements; unknown technical criteria and interfaces are logged for project decision. [Enter Approved civil / services drawings and revisions] [Enter Project earthworks specification and adopted standards] [Enter Service and work-package interfaces] [Enter Performing, reviewing and contractual release roles]
Reference / locator | Enter actual controlled project document, revision and locator; see Source Register for topic guidance.
Trigger / frequency | Before excavation and when route, service system or controlled documents change.
Performing / reviewing role | Proposed: assigned earthworks supervisor / quality role performs and records; project-assigned reviewer acts only within documented authority. Confirm project roles: [Enter Performing, reviewing and contractual release roles].
Control point / external party | Proposed internal readiness check. Confirm any contractual Hold/Witness point, notice, evidence and release authority from project documents; none is assigned by this baseline.
Notice / release evidence | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external release authority is assigned.
Record | Utility trench work-front register
Applicability / remarks | Ordinary utility trench earthworks and pipe-zone backfill only; excludes structural trench support design and service-system testing/commissioning. Proposed baseline. Confirm project applicability and replace each prompt with controlled project sources; no external control point is assigned.
UTB-02 | UTB-02 ¦ Service locating, excavation permit and work-front clearance
Inspection / test | Verify applicable utility searches, locating marks, permits and protection arrangements at the planned trench section.
Method | Review current plans and permit/clearance records; check field marks and service owner instructions are identifiable at the trench location.
Project acceptance condition | Clearance and permits required by the project are current for this section; discrepancies or unknown services are referred before affected excavation proceeds. [Enter Service clearance and permit process] [Enter Approved civil / services drawings and revisions]
Reference / locator | Enter actual controlled project document, revision and locator; see Source Register for topic guidance.
Trigger / frequency | Before each trench section is opened and after route/condition changes.
Performing / reviewing role | Proposed: assigned earthworks supervisor / quality role performs and records; project-assigned reviewer acts only within documented authority. Confirm project roles: [Enter Performing, reviewing and contractual release roles].
Control point / external party | Proposed internal readiness check. Confirm any contractual Hold/Witness point, notice, evidence and release authority from project documents; none is assigned by this baseline.
Notice / release evidence | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external release authority is assigned.
Record | Trench clearance and permit record
Applicability / remarks | Includes service information and excavation clearance only; this record does not design temporary support. Proposed baseline. Confirm project applicability and replace each prompt with controlled project sources; no external control point is assigned.
UTB-03 | UTB-03 ¦ Trench excavation, bottom condition and water
Inspection / test | Inspect the excavated section and bedding formation against the documented profile and record encountered ground/water.
Method | Compare location, alignment, depth/profile evidence and bottom condition with approved service drawings and specified geotechnical/installation criteria; refer deviations.
Project acceptance condition | Dimensions and bottom condition match the project source; water, instability, obstruction or unsuitable founding receives written disposition before bedding or pipe placement. [Enter Approved civil / services drawings and revisions] [Enter Geotechnical design basis and disposition roles] [Enter Project earthworks specification and adopted standards]
Reference / locator | Enter actual controlled project document, revision and locator; see Source Register for topic guidance.
Trigger / frequency | Each section before bedding; recheck after disturbance, water ingress or changed ground.
Performing / reviewing role | Proposed: assigned earthworks supervisor / quality role performs and records; project-assigned reviewer acts only within documented authority. Confirm project roles: [Enter Performing, reviewing and contractual release roles].
Control point / external party | Proposed internal readiness check. Confirm any contractual Hold/Witness point, notice, evidence and release authority from project documents; none is assigned by this baseline.
Notice / release evidence | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external release authority is assigned.
Record | Trench excavation and formation record
Applicability / remarks | Include only for work shown in this package scope. Proposed baseline. Confirm project applicability and replace each prompt with controlled project sources; no external control point is assigned.
UTB-04 | UTB-04 ¦ Bedding and foundation material approval
Inspection / test | Verify bedding material identity and source against the project-specified pipe-zone material requirements.
Method | Review source/delivery documentation and compare material description or required test evidence with the approved material schedule and pipe-system documents.
Project acceptance condition | Material is traceable to the project-approved bedding requirement and intended service/zone; unsuitable or unidentified delivery is held for project disposition. [Enter Material source, classification and use schedule] [Enter Project earthworks specification and adopted standards] [Enter Service and work-package interfaces]
Reference / locator | Enter actual controlled project document, revision and locator; see Source Register for topic guidance.
Trigger / frequency | Before first use of each source/material and for each delivery group as project criteria require.
Performing / reviewing role | Proposed: assigned earthworks supervisor / quality role performs and records; project-assigned reviewer acts only within documented authority. Confirm project roles: [Enter Performing, reviewing and contractual release roles].
Control point / external party | Proposed internal readiness check. Confirm any contractual Hold/Witness point, notice, evidence and release authority from project documents; none is assigned by this baseline.
Notice / release evidence | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external release authority is assigned.
Record | Bedding material receipt record
Applicability / remarks | Include only for work shown in this package scope. Proposed baseline. Confirm project applicability and replace each prompt with controlled project sources; no external control point is assigned.
UTB-05 | UTB-05 ¦ Bedding placement, grade and bearing interface
Inspection / test | Check bedding placement and prepared support/grade before the service component is installed.
Method | Observe preparation, material placement and grade evidence; compare with the identified drawing, specification and manufacturer/project installation detail.
Project acceptance condition | Support, grade and contact arrangement meet the specific project and system documents; dimensions or tolerances are entered only from those documents. [Enter Approved civil / services drawings and revisions] [Enter Project earthworks specification and adopted standards] [Enter Service and work-package interfaces]
Reference / locator | Enter actual controlled project document, revision and locator; see Source Register for topic guidance.
Trigger / frequency | Each trench section before pipe or service installation; recheck any disturbed section.
Performing / reviewing role | Proposed: assigned earthworks supervisor / quality role performs and records; project-assigned reviewer acts only within documented authority. Confirm project roles: [Enter Performing, reviewing and contractual release roles].
Control point / external party | Proposed internal readiness check. Confirm any contractual Hold/Witness point, notice, evidence and release authority from project documents; none is assigned by this baseline.
Notice / release evidence | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external release authority is assigned.
Record | Bedding pre-installation inspection
Applicability / remarks | Include only for work shown in this package scope. Proposed baseline. Confirm project applicability and replace each prompt with controlled project sources; no external control point is assigned.
UTB-06 | UTB-06 ¦ Installed service position and pre-cover inspection
Inspection / test | Record visible service identity, alignment, joints/supports and required pre-cover evidence at the open trench interface.
Method | Inspect against approved service drawings and installation documents; capture required photographs, survey or specialist inspection references before surround conceals the installation.
Project acceptance condition | Installed work and required evidence match the cited project/system requirements; defects or missing inspection evidence remain open before concealment. System commissioning and pressure/leak testing are outside this package. [Enter Approved civil / services drawings and revisions] [Enter Project earthworks specification and adopted standards] [Enter Service and work-package interfaces] [Enter Project records and handover requirements]
Reference / locator | Enter actual controlled project document, revision and locator; see Source Register for topic guidance.
Trigger / frequency | Each defined section before surround or other concealment.
Performing / reviewing role | Proposed: assigned earthworks supervisor / quality role performs and records; project-assigned reviewer acts only within documented authority. Confirm project roles: [Enter Performing, reviewing and contractual release roles].
Control point / external party | Proposed internal readiness check. Confirm any contractual Hold/Witness point, notice, evidence and release authority from project documents; none is assigned by this baseline.
Notice / release evidence | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external release authority is assigned.
Record | Open-trench pre-cover record
Applicability / remarks | Include only for work shown in this package scope. Proposed baseline. Confirm project applicability and replace each prompt with controlled project sources; no external control point is assigned.
UTB-07 | UTB-07 ¦ Haunch and surround placement
Inspection / test | Inspect selected surround material, placement and support around the service before general backfill.
Method | Compare zone material/dimensions and placement sequence with the project detail and installation requirements; observe for displacement or damage.
Project acceptance condition | Surround material, extent and placement follow the project-defined pipe-zone detail; service remains in required position and any disturbance is corrected and re-inspected. [Enter Approved civil / services drawings and revisions] [Enter Material source, classification and use schedule] [Enter Project earthworks specification and adopted standards] [Enter Service and work-package interfaces]
Reference / locator | Enter actual controlled project document, revision and locator; see Source Register for topic guidance.
Trigger / frequency | Each section before advancing above the specified surround zone.
Performing / reviewing role | Proposed: assigned earthworks supervisor / quality role performs and records; project-assigned reviewer acts only within documented authority. Confirm project roles: [Enter Performing, reviewing and contractual release roles].
Control point / external party | Proposed internal readiness check. Confirm any contractual Hold/Witness point, notice, evidence and release authority from project documents; none is assigned by this baseline.
Notice / release evidence | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external release authority is assigned.
Record | Service surround inspection
Applicability / remarks | Include only for work shown in this package scope. Proposed baseline. Confirm project applicability and replace each prompt with controlled project sources; no external control point is assigned.
UTB-08 | UTB-08 ¦ Backfill above pipe zone and reinstatement build-up
Inspection / test | Check accepted backfill material, staged placement and protection of the installed service through the remaining trench depth.
Method | Trace delivered material to project use requirements; observe the documented placement method and specified verification stages; coordinate interfaces for surface reinstatement.
Project acceptance condition | Backfill material and sequence match project drawings/specification; specified verification is completed at the stated project trigger; any damage, settlement or open test is recorded and referred. [Enter Material source, classification and use schedule] [Enter Project earthworks specification and adopted standards] [Enter Project testing, lotting and reporting plan] [Enter Service and work-package interfaces]
Reference / locator | Enter actual controlled project document, revision and locator; see Source Register for topic guidance.
Trigger / frequency | Each defined backfill stage before it is covered by the next stage; use project lot/test basis.
Performing / reviewing role | Proposed: assigned earthworks supervisor / quality role performs and records; project-assigned reviewer acts only within documented authority. Confirm project roles: [Enter Performing, reviewing and contractual release roles].
Control point / external party | Proposed internal readiness check. Confirm any contractual Hold/Witness point, notice, evidence and release authority from project documents; none is assigned by this baseline.
Notice / release evidence | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external release authority is assigned.
Record | Trench backfill stage log
Applicability / remarks | Include only for work shown in this package scope. Proposed baseline. Confirm project applicability and replace each prompt with controlled project sources; no external control point is assigned.
UTB-09 | UTB-09 ¦ Trench testing, defects, survey and handover
Inspection / test | Close the trench section by reconciling specified earthworks tests, final location/level evidence, reinstatement and records.
Method | Review test reports and lot coverage against the project plan; verify survey/as-built files, defect/disposition register and handover index for the same section.
Project acceptance condition | Specified earthworks/backfill evidence and location records are complete to project requirements; outstanding failures or interfaces have written disposition before closeout. Pipe-system commissioning or operational acceptance is by the separately assigned package. [Enter Project testing, lotting and reporting plan] [Enter Survey control, geometry and closeout requirements] [Enter Project records and handover requirements] [Enter Performing, reviewing and contractual release roles]
Reference / locator | Enter actual controlled project document, revision and locator; see Source Register for topic guidance.
Trigger / frequency | At section completion before package handover and before records are closed.
Performing / reviewing role | Proposed: assigned earthworks supervisor / quality role performs and records; project-assigned reviewer acts only within documented authority. Confirm project roles: [Enter Performing, reviewing and contractual release roles].
Control point / external party | Proposed internal readiness check. Confirm any contractual Hold/Witness point, notice, evidence and release authority from project documents; none is assigned by this baseline.
Notice / release evidence | Proposed: Confirm project notice recipient, evidence, timing and release authority; no external release authority is assigned.
Record | Trench section closeout register
Applicability / remarks | Include only for work shown in this package scope. Proposed baseline. Confirm project applicability and replace each prompt with controlled project sources; no external control point is assigned.

## Records
Blank Inspection Record Prompts
Complete during actual work. Actual result, date, names, approvals and signatures are intentionally blank. Retain original third-party reports.
ITP ID / event | Record field | Actual entry / observation | Evidence / report ref. | Disposition / action ref. | Performed by / date | Reviewed / decision ref.
UTB-01 | Service / system / line ID
UTB-01 | Route / drawing locator
UTB-01 | Spec / drawing revisions
UTB-01 | Open interface decision ref.
UTB-01 | Date / location / lot / result / status |  | Original report / photo / attachment reference | NCR / correction / recheck reference | Actual performer and date | Assigned review / decision reference
UTB-02 | Section / chainage
UTB-02 | Service owner / located service
UTB-02 | Permit / clearance ref.
UTB-02 | Field mark / photo ref.
UTB-02 | Date / location / lot / result / status |  | Original report / photo / attachment reference | NCR / correction / recheck reference | Actual performer and date | Assigned review / decision reference
UTB-03 | Section / location
UTB-03 | Drawing / profile locator
UTB-03 | Bottom / water observation
UTB-03 | Instruction / reinspection ref.
UTB-03 | Date / location / lot / result / status |  | Original report / photo / attachment reference | NCR / correction / recheck reference | Actual performer and date | Assigned review / decision reference
UTB-04 | Docket / delivery ID
UTB-04 | Material description / source
UTB-04 | Service / trench zone
UTB-04 | Approval / report ref.
UTB-04 | Date / location / lot / result / status |  | Original report / photo / attachment reference | NCR / correction / recheck reference | Actual performer and date | Assigned review / decision reference
UTB-05 | Section / location
UTB-05 | Observed grade / method / unit
UTB-05 | Drawing / installation detail locator
UTB-05 | Support / contact observation
UTB-05 | Date / location / lot / result / status |  | Original report / photo / attachment reference | NCR / correction / recheck reference | Actual performer and date | Assigned review / decision reference
UTB-06 | Line / component ID
UTB-06 | Section / location
UTB-06 | Inspection / survey / photo ref.
UTB-06 | Defect / disposition ref.
UTB-06 | Date / location / lot / result / status |  | Original report / photo / attachment reference | NCR / correction / recheck reference | Actual performer and date | Assigned review / decision reference
UTB-07 | Section / line ID
UTB-07 | Zone limits / drawing locator
UTB-07 | Surround material / delivery ref.
UTB-07 | Observed position / survey ref.
UTB-07 | Date / location / lot / result / status |  | Original report / photo / attachment reference | NCR / correction / recheck reference | Actual performer and date | Assigned review / decision reference
UTB-08 | Section / lift or stage
UTB-08 | Material / source ID
UTB-08 | Specified test / report ref.
UTB-08 | Surface reinstatement interface
UTB-08 | Date / location / lot / result / status |  | Original report / photo / attachment reference | NCR / correction / recheck reference | Actual performer and date | Assigned review / decision reference
UTB-09 | Section / line ID
UTB-09 | Test method / report / lot refs.
UTB-09 | As-built location / level ref.
UTB-09 | Defect / disposition / interface ref.
UTB-09 | Handover index / recipient ref.
UTB-09 | Date / location / lot / result / status |  | Original report / photo / attachment reference | NCR / correction / recheck reference | Actual performer and date | Assigned review / decision reference

## Source Register
Topic Guidance Source Register
Source ID | Title | Locator and URL | Use and limitation
TMR-MRTS04 | Queensland Department of Transport and Main Roads, MRTS04 General Earthworks (March 2025) | Inspected official PDF and local searchable extract industry-library/text/tmr-mrts04.txt. Topic locators: 1.1-1.2 scope (printed specification pp. 1-2); 5.2-5.6 procedures, testing/lotting (printed pp. 15-19); 6 geometry (printed pp. 19-20); 8 topsoil (printed pp. 22-24); 9 unsuitable material (printed pp. 25-26); 13 excavation (printed pp. 34-38); 14 Earth Fill (printed pp. 38-47); 15 Compaction (printed pp. 48-53); 19 Backfill (printed pp. 67-74). https://www.tmr.qld.gov.au/-/media/busind/techstdpubs/Specifications-and-drawings/Specifications/3-Roadworks-Drainage-Culverts-and-Geotechnical/MRTS04.pdf | Inspected topic example for Queensland road and bridge earthworks only. Supports identification of process topics, documentary controls, materials, geometry, excavation, fill, compaction, backfill and the fact that lot/test rules are specified. Its technical values, tests, frequencies, lot sizes, control points and roles are not defaults; use only if the project contract adopts this edition and applicable annexures.
HUTCHIES-GROUNDWORKS | Hutchinson Builders, Safety & Quality Planning: 010 Groundworks ITP and Report (EXAMPLE) | Official downloads page lists 010 Groundworks ITP and 010 Groundworks Report; both DOCX files downloaded and text-extracted 2026-10-07 from the linked Toolbox files. ITP table rows 3-11 cover bulk set-out, fill source, excavation, fill operations, bottom/surface preparation, compaction/soil-strength records and final inspection; rows 12-25 cover detailed earthworks, trench/pit bottoms, bedding/blinding, backfill, regulatory records and closeout. Matching report table rows 2-4 capture lot/location/open-close/comments/signature; rows 8-32 carry process, specification, acceptance, pass/fail, CAR, initials and date. https://subbies.hutchies.com.au/resources/videos/safety-and-quality-planning | Builder example marked EXAMPLE; used only to check broad staging and useful lot/report fields. Many acceptance/frequency/role cells are blank. It does not set universal criteria, regulatory steps or release authority. Original DOCX files are not redistributed.
CQA-ITP | Construction Quality Australia, How to create an Inspection and Test Plan | Official industry guide, sections 1-4, previously inspected and summarized in skills/au-construction-itp/references/template-writing-guide.md. https://www.cqa.org.au/post/guide-how-to-create-an-inspection-and-test-plan-itp | Method structure only: sequence checkable activities and specify method, acceptance source, trigger/frequency, responsibility, control and records. Does not substantiate earthworks technical limits or project requirements.