## Field record
Check ID | Check, observation and method | Specific record field | Project criterion / source document and revision | Actual record / issue / evidence
TB-01 | Reach identity, service and approved detail What to observe: Service type, asset owner, reach endpoints, drawing/profile revision, material/size and installation stage. How to check: Trace the installed reach between visible endpoints to approved plans and asset schedule before inspection entries are made. Acceptance basis: The recorded segment and service are uniquely identifiable to current approved documents and the actual inspection extent. Reference to confirm: Current utility plan/profile, approved material schedule and inspection lot definition. | Utility / reach / endpoints
Drawing revision / detail
Asset owner / interface party
Result / status (Pass / Fail / N/A / Pending)
Inspector name / role / date
Photo / certificate / report reference
Issue / disposition / recheck evidence and date
TB-02 | Prepared trench support and bedding What to observe: Observed trench bottom/support condition, water or loose material, bedding material/source and installed geometry where observable. How to check: Inspect the exposed reach and link material delivery/source and level/setting evidence; record project-required detail and actual observation separately. Acceptance basis: Support and bedding are checked only against the service-specific approved drawing/specification and documented site evidence; no universal depth/thickness is set. Reference to confirm: Utility installation detail, material submittal, project specification and geotechnical/groundwater direction if applicable. | Support condition
Bedding material / source
Level / photo ref
Result / status (Pass / Fail / N/A / Pending)
Inspector name / role / date
Photo / certificate / report reference
Issue / disposition / recheck evidence and date
TB-03 | Pipe/conduit condition, alignment and joint protection What to observe: Visible damage, joint position, line/level or alignment observations, temporary caps/protection and handling condition before surround. How to check: Observe before concealment, locate each finding and record actual measurement only where an approved reference and method are identified. Acceptance basis: Installed reach remains traceable and observable condition is compared with approved utility requirements; this is not a pressure, leak or continuity test. Reference to confirm: Approved utility drawings, product installation instructions and actual pre-cover observation records. | Joint / point / location
Alignment / damage
Measurement / unit
Result / status (Pass / Fail / N/A / Pending)
Inspector name / role / date
Photo / certificate / report reference
Issue / disposition / recheck evidence and date
TB-04 | Surround, haunch and service separation What to observe: Specified surround material and extent, observed placement around service, other services/crossings and required protection/slabs/markers. How to check: Check visible installation against approved cross-section and crossing details; link photos and survey before cover blocks sight of interfaces. Acceptance basis: Surround, separation and protective measures match the project detail and current asset-owner requirements; no generic clearance or cover value is implied. Reference to confirm: Approved cross-sections, service coordination drawings, asset-owner requirements and product installation detail. | Material / source
Crossing / location
Separation observation
Protection detail / photo
Result / status (Pass / Fail / N/A / Pending)
Inspector name / role / date
Photo / certificate / report reference
Issue / disposition / recheck evidence and date
TB-05 | Staged backfill, cover and reinstatement evidence What to observe: Backfill material/source by stage, lot/layer identity, specified and actual layer thickness/placement where required, actual cover point and unit, final surface condition and separate compaction evidence. How to check: Record each staged placement against the project lot/layer definition, method and drawing; transcribe actual thickness and cover only from observed or surveyed evidence with units and locations. Link separate compaction reports and assigned review; retain final surface/as-built evidence. Acceptance basis: The represented lot/layer, placement, cover and final surface evidence are traceable and compared only with applicable project criteria. Layer thickness, cover, compaction result and acceptance remain project-defined. Compaction requires a separate approved test record and assigned review. Reference to confirm: Project profile/detail and layer/cover criteria, material records, placement log, separate compaction reports and assigned review, survey and as-built requirements. | Backfill material / source
Lot / layer / placement stage
Layer thickness / unit / point
Cover point / location
Actual cover / unit
Criterion source / clause
Compaction report / review ref
Final surface / as-built ref
Result / status (Pass / Fail / N/A / Pending)
Inspector name / role / date
Photo / certificate / report reference
Issue / disposition / recheck evidence and date
TB-06 | Pre-cover testing, notice and reach handover What to observe: Required separate service tests, inspection notice, witness/release documentation, photos, repairs and as-built references. How to check: Index each independent test/report and inspection record by reach; reconcile open issues and notice conditions with the contract/asset-owner schedule. Acceptance basis: This record documents links and status only. It does not certify pipe tests, shoring, design, statutory inspections or grant a contractual release. Reference to confirm: Project inspection and test plan, utility-owner procedures, notice schedule, as-built and NCR requirements. | Test report / ID
Notice / release role
Repair / disposition
As-built / survey ref
Result / status (Pass / Fail / N/A / Pending)
Inspector name / role / date
Photo / certificate / report reference
Issue / disposition / recheck evidence and date

## Project setup
Cavoren ITP | Utility Trench Bedding, Backfill and Cover Record
Field | Project entry | Reason / instructions | Source / locator
Project name / contract
Client / principal
Contractor / trade
Jurisdiction / building class
Room / element / zone / lot
Inspection date / time
Checklist issue / revision
Project / jurisdiction / contractor
Utility type / asset owner
Drawing / revision / profile ref
Reach ID / from-to chainage or nodes
Pipe / conduit material / size / joint system
Bedding / surround material source ref
Crossing / separation / protection detail
Cover measurement location / unit / source
Test / survey / photo / as-built refs
Pre-cover notice / issue / disposition refs
Required project input |  | Why it is needed
Approved utility plans, profiles and details |  | Identify each reach, material/size, design levels, crossings, protection and required cover source.
Utility owner and project installation requirements |  | Confirm service-specific bedding/surround, separation, cover and inspection expectations.
Approved product and material submittals |  | Identify installed pipe/conduit and specified embedment/backfill products.
Trench work method and temporary works controls |  | Coordinate inspection access with the project excavation and temporary support arrangements; this form is not a safety inspection or design.
Pre-cover inspection and testing schedule |  | Identify required notice, witness, release, tests and responsible project/asset-owner role.
As-built survey and defect process |  | Define required location/cover records, photos, repair disposition and transfer to asset records.
Included scope | Inspection of an identified utility trench reach from prepared support through staged bedding/surround, backfill layers and cover handover, including service identity, layer and lot traceability, compaction-report links, pipe/conduit protection, separation and as-built evidence.
Excluded scope | utility design, trench shoring/excavation safety design, pipe pressure/leak/CCTV/continuity testing, commissioning or certification, and compaction acceptance testing except for linking separate approved test evidence.
Use notice | Blank field record. Confirm service-specific material, support, cover, separation and inspection requirements from approved project documents. This record does not certify pipe testing, shoring safety or utility design, and does not create a statutory or contractual release.
How to use
1 | Use a separate record for each defined reach or project inspection lot; identify service and endpoints before recording checks.
2 | Inspect and record the visible work stage before it is concealed; locate photos and measurements to the reach and point.
3 | Record actual materials and observed cover/support separately from the design requirement and its source.
4 | Link separate pipe test or compaction reports by their identifiers; do not treat this sheet as those test certificates.
5 | Record unresolved protection, clearance, damage, missing test or notice evidence as open before backfill/cover handover.
Source title | Role and limits | URL | Locator
Cavoren earthworks baseline | Scope context only; not a project specification, design or acceptance criteria. | https://itp.cavoren.net/templates/bulk-earthworks/ | Original reusable topic baseline for earthworks field records; process and evidence prompts only.
Queensland Department of Transport and Main Roads, MRTS04 General Earthworks (March 2025) | Conditional topic reference for Queensland roadworks/bridgeworks where this edition is adopted. No numeric compaction target, layer thickness, test rate, tolerance, test method or hold/witness point from MRTS04 is generalized into this form. | https://www.tmr.qld.gov.au/-/media/busind/techstdpubs/specifications-and-drawings/specifications/3-roadworks-drainage-culverts-and-geotechnical/mrts04.pdf?extension=pdf&hash=840B4677F54FF4F65E5C80A7EF563206&rev=d832abe7f4fb4ca1bb13425291c3faca&sc_lang=en&size=2763810 | March 2025, Clauses 1.1–1.2 (roadworks/bridgeworks scope); 13.3.3.4 (bottom of confined excavation); 15.1–15.3 and Tables 15.2–15.3 (compaction methods, layers and compliance testing); 19.1–19.3 including 19.3.4 (backfill adjacent to assets and pipe culverts); 21.1–21.1.2 (subgrade construction and levels); Appendix A (testing frequencies).
Hutchies 010 Groundworks Report (public Word example) | Contractor-specific example for record structure and work stages only; blank fields do not establish universal criteria. No source wording or values are reproduced. | https://toolbox.hutchies.com.au/uploads/010-Groundworks-Report.docx | Public report template. Broad sequence and evidence concepts: set-out, excavation/founding, fill/backfill, compaction/density, beds and final review.

## Issues and handover
Utility Trench Bedding, Backfill and Cover Record ¦ Issues and handover
Project | Location / area | Issue date | Open item reference | Person / role
Item ID / date | Affected location and issue | Immediate action / disposition | Recheck evidence / date | Responsible person / role
Utility reach pre-cover handover | Record reach status | Select one status only
[ ] Inspection evidence linked; project handover recorded
[ ] Repair, separate test, cover or as-built item remains open
[ ] Asset-owner/project decision or notice evidence required
Decision boundary | This record logs visible installation and evidence references only. It does not certify a pipe test, approve utility design, assess shoring, establish universal cover/separation criteria or grant statutory/contractual release.
Handover role | Installer / utility role / reach and date
Handover role | Field inspector / role / pre-cover evidence ref
Handover role | Separate pipe-test report / issuing party / reference
Handover role | Assigned asset-owner/project reviewer / notice or decision ref
Handover role | Open repair / NCR / survey / as-built references
Signature note | Signatures record the named person’s stated role and entry only. They do not by themselves approve design, certify compliance, release a contractual control point or authorize the next activity.

## Event log
Utility trench reach, cover and pre-cover log
Use one row per reach or inspection stage. Keep design details separate from actual observations and measurements. Link each lot/layer placement to separate utility test and compaction reports; this log is not a certification or release.
Project / contract |  |  | Element / pour / lot |  |  | Date / shift
Date / stage | Utility / owner | Reach / location | Drawing / detail revision | Lot / layer / stage | Material / source / thickness | Joint / protection / crossing | Cover / value / unit / point | Test / compaction / survey ref | Issue / notice / role / status