## ITP
waterproofing-itp-template ¦ Inspection and Test Plan
[Fill: project name] ¦ Internal Wet Area Waterproofing ITP — Editable Baseline — free editable baseline ¦ [Fill: Australian state/territory] ¦ Rev 00 ¦ 2026-10-06 ¦ For review Contractor: [Fill: contractor] Client: [Fill: client] Scope: Original reusable baseline for membrane waterproofing to internal bathrooms, showers, laundries and similar wet areas in Australian building work. It is a planning aid, not a design or compliance certificate. Exterior/below-ground/roof/facade waterproofing, swimming pools, tanking and proprietary specialist systems are excluded. Confirm NCC edition/state variation, building class, approved compliance pathway, contract and manufacturer system before use. This is a free, editable, proposed baseline and is not tailored to a project, approved by a client, or evidence of completed inspection. Before use, complete the scope questions and bracketed fields, confirm every criterion and control against current project documents, and remove non-applicable rows. Exclusions: Confirm exclusions for this project; use the scope notes above.
ID | Stage | Inspection / test | Method | Acceptance requirement | Reference | Frequency | Responsible role | Point | Approval / witness party | Notice / release | Record | Remarks
WP01 | Scope and compliance basis | Proposed: baseline — Confirm rooms, wet-area types, system limits and interfaces included. | Proposed: baseline — Review approved scope, room schedule, drawings and jurisdiction/compliance pathway. | Proposed: baseline — Included locations and waterproofing extents match the approved scope [Fill: Wet-area drawings/schedule] and pathway [Fill: Compliance pathway]; exclusions are listed. | Guidance only; see Source Register: NCC22-HOUSE, ABCB-WETAREAS | Proposed: Once before work; update on approved scope revision. | Proposed: waterproofing subcontractor; builder/design reviewer to confirm. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Scope and compliance basis register | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
WP02 | Product/system approval | Proposed: baseline — Check specified membrane, primer, bond breaker, reinforcement and accessories are the approved compatible system. | Proposed: baseline — Compare submittals, product labels and current manufacturer data to approved product schedule. | Proposed: baseline — Product/system and components match approved submittal [Fill: Waterproofing system/product]; compatibility and permitted substrate/use are documented. | Guidance only; see Source Register: NCC22-HOUSE, SIKA-1K-PDS | Proposed: Each system/product and each substitution. | Proposed: subcontractor submits; builder/design reviewer approves. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Waterproofing product submittal register | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
WP03 | Delivery and storage | Proposed: baseline — Check delivered product identity, batch, shelf life and storage condition. | Proposed: baseline — Inspect packaging/labels and compare to approved submittal and current manufacturer storage instructions. | Proposed: baseline — Product identity and batch are traceable; packaging is intact and within manufacturer shelf-life/storage limits [Fill: Waterproofing system/product]. | Guidance only; see Source Register: SIKA-1K-PDS | Proposed: Each delivery/batch. | Proposed: waterproofing subcontractor. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Waterproofing delivery and batch register | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
WP04 | Substrate readiness | Proposed: baseline — Inspect substrate type, soundness, cleanliness, dryness/condition and surface preparation before priming. | Proposed: baseline — Visual inspection; check moisture/condition using method and limit in project/manufacturer documents; record defects and remedial preparation. | Proposed: baseline — Substrate is the approved type [Fill: Substrate type], prepared to [Fill: Waterproofing system/product] instructions, free of specified contaminants/defects, and within any stated moisture/condition limits. Specific project/system condition: [Fill: Specified substrate preparation limits]. | Guidance only; see Source Register: NCC22-HOUSE, SIKA-1K-PDS | Proposed: Each room/area before primer. | Proposed: applicator; builder reviewer if specified. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Substrate readiness checklist | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
WP05 | Falls and drainage | Proposed: baseline — Check floor falls, floor waste position, drainage path and any step-down/threshold details before membrane. | Proposed: baseline — Measure levels/falls against approved drawings and jurisdiction/code pathway; confirm waste is secure and interface detail identified. | Proposed: baseline — Falls, waste position and threshold/step details match approved detail [Fill: Falls/drain details] and applicable compliance pathway [Fill: Compliance pathway]; missing design criteria are flagged. | Guidance only; see Source Register: NCC22-HOUSE | Proposed: Each wet room before membrane. | Proposed: subcontractor measures; builder/surveyor where specified. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Falls and drainage check | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
WP06 | Junctions and movement joints | Proposed: baseline — Inspect wall-floor junctions, internal corners, changes of plane, construction/movement joints and bond-breaker detail. | Proposed: baseline — Visual check against approved detail and system instructions; record each junction type and treatment. | Proposed: baseline — Each junction treatment is continuous and matches approved detail [Fill: Penetrations/junction details] and the compatible system instructions [Fill: Waterproofing system/product]. | Guidance only; see Source Register: NCC22-HOUSE, SIKA-1K-PDS | Proposed: Each room and each junction type before covering. | Proposed: waterproofing subcontractor. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Junction and bond-breaker checklist | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
WP07 | Penetrations and outlets | Proposed: baseline — Check pipe penetrations, floor wastes, puddle flanges and fixtures interfaces are stable and treated. | Proposed: baseline — Visual inspection and compare dimensions/details to approved drawings and system instructions. | Proposed: baseline — Penetrations/outlets are correctly located and sealed using the specified compatible detail [Fill: Penetrations/junction details]; no untreated opening remains. | Guidance only; see Source Register: NCC22-HOUSE, SIKA-1K-PDS | Proposed: Each penetration/outlet before membrane. | Proposed: waterproofing subcontractor; plumbing interface role to confirm. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Penetration and outlet checklist | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
WP08 | Primer and preparation coat | Proposed: baseline — Verify primer selection, mixing (if applicable), application and drying/overcoat readiness. | Proposed: baseline — Observe product/batch and application; record ambient/substrate conditions where required by data sheet. | Proposed: baseline — Primer and preparation follow current instructions for [Fill: Waterproofing system/product] on substrate [Fill: Substrate type], including stated coverage and recoat conditions. Specific project/system condition: [Fill: Primer application and readiness criteria]. | Guidance only; see Source Register: SIKA-1K-PDS | Proposed: Each room/application batch. | Proposed: applicator. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Primer/application log | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
WP09 | Membrane first coat | Proposed: baseline — Inspect coverage, continuity, corners, upturns and specified reinforcement at first application. | Proposed: baseline — Visual inspection while accessible; measure wet/dry thickness or consumption only by manufacturer/project-prescribed method. | Proposed: baseline — Coverage, coat build-up, reinforcement and extent meet project detail [Fill: Wet-area drawings/schedule] and system instructions [Fill: Waterproofing system/product]; record actual measurements where required. Specific project/system condition: [Fill: First-coat coverage and build-up criteria]. | Guidance only; see Source Register: NCC22-HOUSE, SIKA-1K-PDS | Proposed: Each room and coat before next coat. | Proposed: waterproofing subcontractor; reviewer per contract. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Membrane coat application log | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
WP10 | Membrane subsequent coat(s) | Proposed: baseline — Check subsequent coats, direction/overlap and cure/recoat interval. | Proposed: baseline — Visual check; record coat time and conditions against product instructions. | Proposed: baseline — Number/order of coats, continuity and recoat interval comply with approved system [Fill: Waterproofing system/product] and project detail [Fill: Wet-area drawings/schedule]. Specific project/system condition: [Fill: Subsequent-coat and recoat criteria]. | Guidance only; see Source Register: SIKA-1K-PDS | Proposed: Every coat/room. | Proposed: applicator. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Membrane coat and cure log | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
WP11 | Upturns and terminations | Proposed: baseline — Inspect membrane height/extents, edges, doorway/threshold termination, hob and bath/shower details. | Proposed: baseline — Measure only against project detail and applicable pathway; visually inspect terminations and continuity. | Proposed: baseline — Extents and terminations match approved detail [Fill: Wet-area drawings/schedule] and applicable NCC/standard pathway [Fill: Compliance pathway]; no generic height substituted. Specific project/system condition: [Fill: Membrane extent and termination criteria]. | Guidance only; see Source Register: NCC22-HOUSE | Proposed: Each room/termination before covering. | Proposed: subcontractor; design reviewer where needed. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Upturn and termination checklist | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
WP12 | Curing and protection | Proposed: baseline — Confirm cure before traffic, flood test or follow-on trade; inspect protection method. | Proposed: baseline — Check elapsed time and conditions against manufacturer instructions; inspect protection and trade interface. | Proposed: baseline — Membrane has reached the system-specified cure condition before test/cover; protection is compatible and does not damage membrane [Fill: Waterproofing system/product]. Specific project/system condition: [Fill: Cure and protection criteria]. | Guidance only; see Source Register: SIKA-1K-PDS | Proposed: Each area before access, test or covering. | Proposed: waterproofing subcontractor and builder. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Cure and protection log | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
WP13 | Specified water test | Proposed: baseline — Where required, inspect test setup and result before finishes/concealment. | Proposed: baseline — Use only project-approved test method, boundaries, duration and limits; document start/end, observed leakage and result. | Proposed: baseline — Result meets the specified test criteria [Fill: Specified water test]; defects are repaired and retested before release. If no criterion is supplied, raise confirmation and do not invent a test. | Guidance only; see Source Register: NCC22-HOUSE, CQA-ITP | Proposed: Only where required; each test area. | Proposed: subcontractor performs; builder/client witnesses only if contract says. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Wet-area water test record | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
WP14 | Pre-cover inspection | Proposed: baseline — Final inspection before screed, tile, lining or other concealment. | Proposed: baseline — Walk down complete system; verify all prior issues closed and photograph critical concealed interfaces. | Proposed: baseline — Installed waterproofing is complete to approved drawings/system; penetrations, junctions, upturns and defects are recorded and resolved before concealment. | Guidance only; see Source Register: NCC22-HOUSE, CQA-ITP | Proposed: Each room/area before concealment. | Proposed: subcontractor; builder/client reviewer if contract requires. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Pre-cover release checklist | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
WP15 | Tiling/screed interface | Proposed: baseline — Check membrane protection and any screed/adhesive interface details before finishes. | Proposed: baseline — Review approved detail and manufacturer compatibility; inspect that membrane is not damaged and required protection/separation is installed. | Proposed: baseline — Interface materials and sequence match approved system [Fill: Waterproofing system/product] and detail [Fill: Wet-area drawings/schedule]; any damage is repaired by approved method before covering. | Guidance only; see Source Register: NCC22-HOUSE, SIKA-1K-PDS | Proposed: Each area before finishes. | Proposed: waterproofing and tiling subcontractors; builder coordinates. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Membrane interface checklist | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
WP16 | Defects, repairs and retest | Proposed: baseline — Track damage, pinholes, delamination or failed test; inspect repair. | Proposed: baseline — Record defect location, approved repair method, product/batch, reinspection and retest where required. | Proposed: baseline — Defects are closed using manufacturer-approved repair and any specified retest passes [Fill: Specified water test]; no undocumented patch accepted. | Guidance only; see Source Register: SIKA-1K-PDS | Proposed: Each defect/repair. | Proposed: waterproofing subcontractor; reviewer per contract. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Waterproofing defect and repair register | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
WP17 | Completion and handover | Proposed: baseline — Check required certificates, warranties, product/batch traceability, photos and maintenance information. | Proposed: baseline — Review handover schedule and project-required documents. | Proposed: baseline — Required handover evidence in [Fill: Compliance pathway] and contract is complete, traceable to rooms/areas, and consistent with installed system. | Guidance only; see Source Register: CQA-ITP | Proposed: Once per package at completion. | Proposed: subcontractor submits; builder compiles. | TBC | Proposed: [Fill: reviewing role / authority assigned by project] | Proposed: Confirm required notice period, who receives notice, release authority and whether a contractual hold/witness point applies. | Waterproofing handover register | Proposed: Check this baseline row against project documents; edit or remove it if it does not apply.
Point key: H = Proposed Hold Point - use only if assigned in the contract ¦ W = Proposed Witness Point - use only if assigned in the contract ¦ R = Proposed Review ¦ S = Proposed Surveillance ¦ TBC = To be confirmed ¦ N/A = Not applicable. External H/W rights and release rules must come from the project contract and approved process.

## Record Forms
Blank Inspection Record Forms
[Fill: project name] ¦ waterproofing-itp-template ¦ Record actual observations during the work. No results or signatures are pre-filled.
ITP ID / Stage | Inspection / method / acceptance | Location / lot | Date and result | Evidence / record ref. | Performed by / signature | Reviewed by / signature
WP01 ¦ Scope and compliance basis | Proposed: baseline — Confirm rooms, wet-area types, system limits and interfaces included. Method: Proposed: baseline — Review approved scope, room schedule, drawings and jurisdiction/compliance pathway. Accept when: Proposed: baseline — Included locations and waterproofing extents match the approved scope [Fill: Wet-area drawings/schedule] and pathway [Fill: Compliance pathway]; exclusions are listed. Record: Scope and compliance basis register |  | Date: __________ Actual result/observation: __________ Evidence/photo/report reference: __________ Result / disposition: __________ Corrective action / retest ref.: __________
WP02 ¦ Product/system approval | Proposed: baseline — Check specified membrane, primer, bond breaker, reinforcement and accessories are the approved compatible system. Method: Proposed: baseline — Compare submittals, product labels and current manufacturer data to approved product schedule. Accept when: Proposed: baseline — Product/system and components match approved submittal [Fill: Waterproofing system/product]; compatibility and permitted substrate/use are documented. Record: Waterproofing product submittal register |  | Date: __________ Actual result/observation: __________ Evidence/photo/report reference: __________ Result / disposition: __________ Corrective action / retest ref.: __________
WP03 ¦ Delivery and storage | Proposed: baseline — Check delivered product identity, batch, shelf life and storage condition. Method: Proposed: baseline — Inspect packaging/labels and compare to approved submittal and current manufacturer storage instructions. Accept when: Proposed: baseline — Product identity and batch are traceable; packaging is intact and within manufacturer shelf-life/storage limits [Fill: Waterproofing system/product]. Record: Waterproofing delivery and batch register |  | Date: __________ Actual result/observation: __________ Evidence/photo/report reference: __________ Result / disposition: __________ Corrective action / retest ref.: __________
WP04 ¦ Substrate readiness | Proposed: baseline — Inspect substrate type, soundness, cleanliness, dryness/condition and surface preparation before priming. Method: Proposed: baseline — Visual inspection; check moisture/condition using method and limit in project/manufacturer documents; record defects and remedial preparation. Accept when: Proposed: baseline — Substrate is the approved type [Fill: Substrate type], prepared to [Fill: Waterproofing system/product] instructions, free of specified contaminants/defects, and within any stated moisture/condition limits. Specific project/system condition: [Fill: Specified substrate preparation limits]. Record: Substrate readiness checklist |  | Date: __________ Actual result/observation: __________ Evidence/photo/report reference: __________ Result / disposition: __________ Corrective action / retest ref.: __________
WP05 ¦ Falls and drainage | Proposed: baseline — Check floor falls, floor waste position, drainage path and any step-down/threshold details before membrane. Method: Proposed: baseline — Measure levels/falls against approved drawings and jurisdiction/code pathway; confirm waste is secure and interface detail identified. Accept when: Proposed: baseline — Falls, waste position and threshold/step details match approved detail [Fill: Falls/drain details] and applicable compliance pathway [Fill: Compliance pathway]; missing design criteria are flagged. Record: Falls and drainage check |  | Date: __________ Actual result/observation: __________ Evidence/photo/report reference: __________ Result / disposition: __________ Corrective action / retest ref.: __________
WP06 ¦ Junctions and movement joints | Proposed: baseline — Inspect wall-floor junctions, internal corners, changes of plane, construction/movement joints and bond-breaker detail. Method: Proposed: baseline — Visual check against approved detail and system instructions; record each junction type and treatment. Accept when: Proposed: baseline — Each junction treatment is continuous and matches approved detail [Fill: Penetrations/junction details] and the compatible system instructions [Fill: Waterproofing system/product]. Record: Junction and bond-breaker checklist |  | Date: __________ Actual result/observation: __________ Evidence/photo/report reference: __________ Result / disposition: __________ Corrective action / retest ref.: __________
WP07 ¦ Penetrations and outlets | Proposed: baseline — Check pipe penetrations, floor wastes, puddle flanges and fixtures interfaces are stable and treated. Method: Proposed: baseline — Visual inspection and compare dimensions/details to approved drawings and system instructions. Accept when: Proposed: baseline — Penetrations/outlets are correctly located and sealed using the specified compatible detail [Fill: Penetrations/junction details]; no untreated opening remains. Record: Penetration and outlet checklist |  | Date: __________ Actual result/observation: __________ Evidence/photo/report reference: __________ Result / disposition: __________ Corrective action / retest ref.: __________
WP08 ¦ Primer and preparation coat | Proposed: baseline — Verify primer selection, mixing (if applicable), application and drying/overcoat readiness. Method: Proposed: baseline — Observe product/batch and application; record ambient/substrate conditions where required by data sheet. Accept when: Proposed: baseline — Primer and preparation follow current instructions for [Fill: Waterproofing system/product] on substrate [Fill: Substrate type], including stated coverage and recoat conditions. Specific project/system condition: [Fill: Primer application and readiness criteria]. Record: Primer/application log |  | Date: __________ Actual result/observation: __________ Evidence/photo/report reference: __________ Result / disposition: __________ Corrective action / retest ref.: __________
WP09 ¦ Membrane first coat | Proposed: baseline — Inspect coverage, continuity, corners, upturns and specified reinforcement at first application. Method: Proposed: baseline — Visual inspection while accessible; measure wet/dry thickness or consumption only by manufacturer/project-prescribed method. Accept when: Proposed: baseline — Coverage, coat build-up, reinforcement and extent meet project detail [Fill: Wet-area drawings/schedule] and system instructions [Fill: Waterproofing system/product]; record actual measurements where required. Specific project/system condition: [Fill: First-coat coverage and build-up criteria]. Record: Membrane coat application log |  | Date: __________ Product/system: __________ Batch/lot: __________ Area/room: __________ Coat number: __________ Measured wet thickness (mm): __________ Product consumption: __________ Substrate temperature (°C): __________ Ambient temperature (°C): __________ Relative humidity (%): __________ Result / disposition: __________ Corrective action / retest ref.: __________
WP10 ¦ Membrane subsequent coat(s) | Proposed: baseline — Check subsequent coats, direction/overlap and cure/recoat interval. Method: Proposed: baseline — Visual check; record coat time and conditions against product instructions. Accept when: Proposed: baseline — Number/order of coats, continuity and recoat interval comply with approved system [Fill: Waterproofing system/product] and project detail [Fill: Wet-area drawings/schedule]. Specific project/system condition: [Fill: Subsequent-coat and recoat criteria]. Record: Membrane coat and cure log |  | Date: __________ Product/system: __________ Batch/lot: __________ Area/room: __________ Coat number: __________ Application start: __________ Application finish: __________ Ambient temperature (°C): __________ Relative humidity (%): __________ Result / disposition: __________ Corrective action / retest ref.: __________
WP11 ¦ Upturns and terminations | Proposed: baseline — Inspect membrane height/extents, edges, doorway/threshold termination, hob and bath/shower details. Method: Proposed: baseline — Measure only against project detail and applicable pathway; visually inspect terminations and continuity. Accept when: Proposed: baseline — Extents and terminations match approved detail [Fill: Wet-area drawings/schedule] and applicable NCC/standard pathway [Fill: Compliance pathway]; no generic height substituted. Specific project/system condition: [Fill: Membrane extent and termination criteria]. Record: Upturn and termination checklist |  | Date: __________ Actual result/observation: __________ Evidence/photo/report reference: __________ Result / disposition: __________ Corrective action / retest ref.: __________
WP12 ¦ Curing and protection | Proposed: baseline — Confirm cure before traffic, flood test or follow-on trade; inspect protection method. Method: Proposed: baseline — Check elapsed time and conditions against manufacturer instructions; inspect protection and trade interface. Accept when: Proposed: baseline — Membrane has reached the system-specified cure condition before test/cover; protection is compatible and does not damage membrane [Fill: Waterproofing system/product]. Specific project/system condition: [Fill: Cure and protection criteria]. Record: Cure and protection log |  | Date: __________ Actual result/observation: __________ Evidence/photo/report reference: __________ Result / disposition: __________ Corrective action / retest ref.: __________
WP13 ¦ Specified water test | Proposed: baseline — Where required, inspect test setup and result before finishes/concealment. Method: Proposed: baseline — Use only project-approved test method, boundaries, duration and limits; document start/end, observed leakage and result. Accept when: Proposed: baseline — Result meets the specified test criteria [Fill: Specified water test]; defects are repaired and retested before release. If no criterion is supplied, raise confirmation and do not invent a test. Record: Wet-area water test record |  | Date: __________ Room/area: __________ Test method: __________ Start date/time: __________ End date/time: __________ Water level at start: __________ Water level at end: __________ Leakage/observations: __________ Repair/retest reference: __________ Result / disposition: __________ Corrective action / retest ref.: __________
WP14 ¦ Pre-cover inspection | Proposed: baseline — Final inspection before screed, tile, lining or other concealment. Method: Proposed: baseline — Walk down complete system; verify all prior issues closed and photograph critical concealed interfaces. Accept when: Proposed: baseline — Installed waterproofing is complete to approved drawings/system; penetrations, junctions, upturns and defects are recorded and resolved before concealment. Record: Pre-cover release checklist |  | Date: __________ Actual result/observation: __________ Evidence/photo/report reference: __________ Result / disposition: __________ Corrective action / retest ref.: __________
WP15 ¦ Tiling/screed interface | Proposed: baseline — Check membrane protection and any screed/adhesive interface details before finishes. Method: Proposed: baseline — Review approved detail and manufacturer compatibility; inspect that membrane is not damaged and required protection/separation is installed. Accept when: Proposed: baseline — Interface materials and sequence match approved system [Fill: Waterproofing system/product] and detail [Fill: Wet-area drawings/schedule]; any damage is repaired by approved method before covering. Record: Membrane interface checklist |  | Date: __________ Actual result/observation: __________ Evidence/photo/report reference: __________ Result / disposition: __________ Corrective action / retest ref.: __________
WP16 ¦ Defects, repairs and retest | Proposed: baseline — Track damage, pinholes, delamination or failed test; inspect repair. Method: Proposed: baseline — Record defect location, approved repair method, product/batch, reinspection and retest where required. Accept when: Proposed: baseline — Defects are closed using manufacturer-approved repair and any specified retest passes [Fill: Specified water test]; no undocumented patch accepted. Record: Waterproofing defect and repair register |  | Date: __________ Actual result/observation: __________ Evidence/photo/report reference: __________ Result / disposition: __________ Corrective action / retest ref.: __________
WP17 ¦ Completion and handover | Proposed: baseline — Check required certificates, warranties, product/batch traceability, photos and maintenance information. Method: Proposed: baseline — Review handover schedule and project-required documents. Accept when: Proposed: baseline — Required handover evidence in [Fill: Compliance pathway] and contract is complete, traceable to rooms/areas, and consistent with installed system. Record: Waterproofing handover register |  | Date: __________ Actual result/observation: __________ Evidence/photo/report reference: __________ Result / disposition: __________ Corrective action / retest ref.: __________

## Source Register
Source Register
Source ID | Title | Revision / check | Type | Path / URL
NCC22-HOUSE | ABCB, NCC 2022 Housing Provisions, Part 10.2 Wet area waterproofing | See linked source; verify current edition and project adoption | guidance | https://ncc.abcb.gov.au/editions/ncc-2022/adopted/housing-provisions/10-health-and-amenity/part-102-wet-area-waterproofing
NCC22-REFDOCS | ABCB, NCC 2022 referenced documents | See linked source; verify current edition and project adoption | guidance | https://ncc.abcb.gov.au/editions/ncc-2022/adopted/volume-three/2-referenced-documents/referenced-documents
ABCB-WETAREAS | ABCB, Waterproofing in houses | See linked source; verify current edition and project adoption | guidance | https://ncc.abcb.gov.au/ncc-navigator/waterproofing-houses
CQA-ITP | Construction Quality Association, Guide: How to create an ITP | See linked source; verify current edition and project adoption | guidance | https://www.cqa.org.au/post/guide-how-to-create-an-inspection-and-test-plan-itp
SIKA-1K-PDS | Sika Australia, Sikalastic-1K Product Data Sheet | See linked source; verify current edition and project adoption | guidance | https://aus.sika.com/dms/getdocument.get/37ce9696-c23c-444d-9df2-02f76226b157/sikalastic_-1k.pdf

## Confirmations
Open Confirmations
Issue ID | Priority | ITP rows | Open item | Action needed
CONF-001 | confirmation | WP01 | WP01: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-002 | confirmation | WP02 | WP02: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-003 | confirmation | WP03 | WP03: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-004 | confirmation | WP04 | WP04: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-005 | confirmation | WP05 | WP05: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-006 | confirmation | WP06 | WP06: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-007 | confirmation | WP07 | WP07: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-008 | confirmation | WP08 | WP08: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-009 | confirmation | WP09 | WP09: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-010 | confirmation | WP10 | WP10: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-011 | confirmation | WP11 | WP11: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-012 | confirmation | WP12 | WP12: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-013 | confirmation | WP13 | WP13: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-014 | confirmation | WP14 | WP14: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-015 | confirmation | WP15 | WP15: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-016 | confirmation | WP16 | WP16: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.
CONF-017 | confirmation | WP17 | WP17: verify scope and project-specific requirements for this proposed baseline row. | Check current contract, drawings, specification, approved method, adopted standards and assigned roles; edit or delete this row as needed.