## Field record
Check ID | Check, observation and method | Specific record field | Project criterion / source document and revision | Actual record / issue / evidence
WT-01 | Installation traceability and completed extent What to observe: Confirm each room/zone proposed for tiling maps to membrane application records, selected product system, batch information and final-coat date where available. How to check: Reconcile room map, installer log, labels and repair records; mark unrecorded or excluded areas clearly. Acceptance basis: Every proposed cover area is traceable to the approved system and actual installation record; missing area/product/date evidence is resolved or explicitly dispositioned. Reference to confirm: Approved room schedule, membrane application record, current product submittal and batch evidence. | Room / zone
Membrane / batch
Final coat date
Install record ref
Result / status (Pass / Fail / N/A / Pending)
Inspector name / role / date
Photo / certificate / report reference
Issue / disposition / recheck evidence and date
WT-02 | Membrane surface and continuity What to observe: Inspect the exposed membrane for visible damage, pinholes, discontinuities, contamination, debonding or unfinished patches. How to check: Walk all accessible surfaces under suitable light; map defects and take location-linked photographs; use only project/product-approved inspection method. Acceptance basis: Surface is complete and free of unresolved visible defects against the project and exact system criteria; visual inspection alone is not represented as proof of watertightness. Reference to confirm: Approved project inspection criteria and current membrane TDS. | Defect / location
Extent / photo
Repair instruction
Recheck result
Result / status (Pass / Fail / N/A / Pending)
Inspector name / role / date
Photo / certificate / report reference
Issue / disposition / recheck evidence and date
WT-03 | Junctions, penetrations and terminations What to observe: Inspect membrane continuity at wall/floor and wall/wall junctions, movement joints, drains, penetrations, waterstops, thresholds and terminations. How to check: Check each detail against approved enlarged drawings and selected tape/sealant/membrane sequence; record inaccessible or damaged interfaces. Acceptance basis: All required interfaces match approved details and current compatible system instructions; any omitted/inaccessible detail is resolved before concealment. Reference to confirm: Approved wet-area details, applicable code pathway and exact accessory/membrane TDS. | Detail / location
System components
Continuity note
Photo / RFI ref
Result / status (Pass / Fail / N/A / Pending)
Inspector name / role / date
Photo / certificate / report reference
Issue / disposition / recheck evidence and date
WT-04 | System-specific cure and covering readiness What to observe: Check whether the system-specific cure, environmental and overcoating/tiling conditions required by approved documents have been met. How to check: Compare final-coat time and recorded site conditions to the exact current local TDS and project specification; record any conditions the source requires. Acceptance basis: Document that the cited product and governing project conditions are met. Resolve conflicting instructions through project document precedence and written clarification; do not silently select the stricter value. No cure or waiting period is supplied by this form. Reference to confirm: Exact approved membrane TDS revision, application log and project specification. | Final coat time
Site conditions
TDS revision
Reviewer / evidence
Result / status (Pass / Fail / N/A / Pending)
Inspector name / role / date
Photo / certificate / report reference
Issue / disposition / recheck evidence and date
WT-05 | Specified water or other performance test What to observe: Confirm whether a test is required and, only when specified, record the actual approved test setup, observations and outcome. How to check: Review contract/specification/system instruction for method, area, isolation, duration, acceptable level/condition and witness; attach test record. If none applies, mark N/A with source/reason. Acceptance basis: Test requirement and acceptance are traceable to this project/system. No generic flood-test duration, depth, pass rule or permission to test is implied; a missing criterion remains Pending. Reference to confirm: Project specification/ITP and current system instructions; named approved test procedure. | Test / N/A basis
Method / criteria ref
Actual observation
Witness / report ref
Result / status (Pass / Fail / N/A / Pending)
Inspector name / role / date
Photo / certificate / report reference
Issue / disposition / recheck evidence and date
WT-06 | Repairs, reinspection and protection What to observe: Confirm all recorded defects have an approved repair, reinspection evidence and protection/interface plan for follow-on trades. How to check: Revisit mapped locations after repair; compare repair materials and sequence to compatible system instructions; record how membrane will be protected from damage. Acceptance basis: Repair and recheck evidence is closed or remains explicitly open; follow-on work has agreed protection/interface measures before covering. Reference to confirm: Approved repair disposition, current system TDS and project follow-on trade method. | Issue / repair ref
Repair product / date
Recheck / inspector
Protection plan
Result / status (Pass / Fail / N/A / Pending)
Inspector name / role / date
Photo / certificate / report reference
Issue / disposition / recheck evidence and date
WT-07 | Installer, site verifier and formal release record What to observe: Record installer completion, independent/site verifier observation, any appointed certifier decision and contractual release/witness outcome as separate items. How to check: Check project ITP/contract for notice, hold, witness and release authority; record actual person/role, scope, date, response and document reference. Acceptance basis: No party’s observation is attributed to another. Tiling/screeding follows the actual project release conditions; blank or pending formal approval is not inferred from an installer signature. Reference to confirm: Contract, project ITP, appointment/authority records, inspection report and any issued certificate/release. | Event / scope
Person / role
Notice / outcome
Release / certificate ref
Result / status (Pass / Fail / N/A / Pending)
Inspector name / role / date
Photo / certificate / report reference
Issue / disposition / recheck evidence and date

## Project setup
Cavoren ITP | Pre-Tiling Waterproofing Inspection Checklist
Field | Project entry | Reason / instructions | Source / locator
Project name / contract
Client / principal
Contractor / trade
Jurisdiction / building class
Room / element / zone / lot
Inspection date / time
Checklist issue / revision
Project / contractor
Room / zone / cover area
Membrane system
Inspection date
Final application record reference
Approved detail / revision
Required project input |  | Why it is needed
Project compliance pathway and current adopted edition |  | Identify the project building class, jurisdiction, adopted edition, variations and approved compliance pathway; a published code edition does not establish applicability.
Exact membrane system and current TDS revision |  | Cure, recoat, over-tile and test windows differ across products and site conditions.
Membrane installation records and room map |  | Pre-cover inspection must trace each area and junction to actual application and repair evidence.
Project-specific test method and acceptance |  | A flood test is not universal; record duration and limits only if approved project evidence requires them.
Contractual notice and release role |  | Installer finish, site verification, independent certification and builder/client release are separate actions.
Included scope | Ordinary indoor wet areas after membrane installation and before tile/screed concealment or downstream trade handover. Captures surface continuity, detail condition, product-specific readiness evidence and project-defined tests/release.
Excluded scope | Installing the membrane, assessing substrate readiness, prescribing a flood test, certifying compliance, authorising tiling or approving defects. A test is included only when required by the approved project/system and must use its specified method and acceptance.
Use notice | Blank record for ordinary indoor wet areas. Fill criteria from the approved project details and exact compatible system instructions, after confirming the applicable project compliance basis. Observations, test results and signatures stay blank until the work is checked. Recording installer work or site observations does not grant certification or contractual release authority.
How to use
1 | Use this record only after the membrane application records are available and before tiles/screed hide the membrane.
2 | Inspect each room and vulnerable detail; compare against exact approved drawings and current system instructions; record defects, repairs and recheck evidence.
3 | Enter cure/overcoating requirements and any water test only from the exact current approved system/project documents. Do not treat dry-to-touch or a marketing claim as permission to cover.
4 | Record installer declaration, site verifier findings, any required certifier inspection and contractual release separately, with named roles and references.
5 | If any area is damaged, contaminated, incomplete or outside its documented window, keep its status Pending and obtain disposition before concealment.
Source title | Role and limits | URL | Locator
ABCB, NCC 2022 Housing Provisions, Part 10.2 Wet area waterproofing | Official topic reference from NCC 2022 Housing Provisions, including the variations shown on that page. Confirm the project building class, compliance pathway, adopted edition and relevant state/territory variations before using any provision. This reference does not set universal acceptance criteria. | https://ncc.abcb.gov.au/editions/ncc-2022/adopted/housing-provisions/10-health-and-amenity/part-102-wet-area-waterproofing | Clauses 10.2.1–10.2.32; especially 10.2.6–10.2.13, 10.2.22–10.2.30
ABCB, Waterproofing in houses | Official introduction for Class 1 houses. Its national overview omits state/territory variations and does not establish requirements for other building classes or compliance pathways. | https://ncc.abcb.gov.au/ncc-navigator/waterproofing-houses | Scope/target audience and sections on NCC 2022 Volume Two H4, Housing Provisions Part 10.2 and AS 3740 options
ABCB, Editions of the National Construction Code | Official NCC edition index. Use it with the project documents and jurisdictional adoption/transition rules to identify the governing edition. Publication of a code edition does not by itself establish which edition applies to a particular project. | https://ncc.abcb.gov.au/editions-national-construction-code | Edition and amendment listings; then consult the project jurisdiction for adoption and transition provisions
ARDEX Australia, WPM 155 Rapid Plus Technical Data Sheet | First-party example of one internal/external under-tile system. Supports prompts to record substrate preparation, selected primer, junction/detail method, application coats, product-specific coverage/film build, curing and pre-cover inspection. Any manufacturer values apply only when this exact product/system is approved and the current local data sheet is verified; none are prefilled as generic acceptance criteria. | https://ardexaustralia.com/pdf/products/datasheets/waterproofing/ARDEX%20WPM%20155%20Rapid%20Plus%20Datasheet.pdf | January 2025 issue, pp. 1–3: substrate preparation, primer, detailing, application, curing, flood testing and tiling; manufacturer warns newer revision may exist
Sika Australia, Sika SealTape F Product Data Sheet | First-party accessory example for compatible Sika systems; supports documenting substrate cleanliness/priming, embedding, tape continuity/overlaps and membrane coat interface. Requirements are accessory/system specific and only apply after checking the selected membrane TDS and approval. | https://aus.sika.com/dms/getdocument.get/51447514-2e04-49ff-83cc-a4274d6f5191/sika-sealtape-f.pdf | December 2025 version 05.01, pp. 1–2, substrate preparation and application instructions
Construction Quality Association, Guide: How to create an ITP | ITP record design guidance only: identify what is checked, how, against what source, who records it, and what evidence follows. It supplies no waterproofing technical acceptance criteria. | https://www.cqa.org.au/post/guide-how-to-create-an-inspection-and-test-plan-itp | Whole article; ITP requirement/inspection/evidence structure

## Issues and handover
Pre-Tiling Waterproofing Inspection Checklist ¦ Issues and handover
Project | Location / area | Issue date | Open item reference | Person / role
Item ID / date | Affected location and issue | Immediate action / disposition | Recheck evidence / date | Responsible person / role
Pre-covering status | Pre-covering / next-trade status | Select one status only
[ ] Inspection recorded — project release evidenced
[ ] Hold — repair, test or recheck
[ ] Formal release pending / refer
Decision boundary | A site observation or installer statement does not authorise tiling. Select the first status only when the applicable project release evidence is recorded; it still does not constitute engineering approval or statutory certification.
Handover role | Installer declaration / role / date
Handover role | Site verifier / role / date
Handover role | Certifier only if appointed/required / reference
Handover role | Contract release authority / reference
Installer / contractor declaration | Record field | Entry / reference
Name / role / company
Areas and dates completed
Exceptions / repair references
Declaration / signature / date
Site verifier observation | Record field | Entry / reference
Name / role
Scope observed and date
Findings / evidence references
Certifier / building surveyor (if required by project) | Record field | Entry / reference
Assigned role and inspection scope
Record / certificate reference and date
Project release / handover role | Record field | Entry / reference
Role assigned by contract
Decision / status and conditions
Notice / ITP reference and date
Signature note | Signatures record the named person’s stated role and entry only. They do not by themselves approve design, certify compliance, release a contractual control point or authorize the next activity.