## Field record
Check ID | Check, observation and method | Specific record field | Project criterion / source document and revision | Actual record / issue / evidence
WVI-01 | Weld identity and examination boundary What to observe: Weld number, member marks, joint location, drawing/weld-map revision, shop or site stage, and the portion included in this examination. How to check: Locate the joint physically and reconcile it to the current weld map and inspection request; record any inaccessible length or boundary. Acceptance basis: The examined joint is uniquely traceable to the controlled drawing/weld map and stated examination extent; unidentified or inaccessible portions remain open. Reference to confirm: Approved drawing connection detail, weld map, inspection request and current revision register; cite drawing sheet, grid/member and weld mark. | Weld ID / joint mark
Member / grid / location
Map and drawing revision
Examined portion / access limit
Result / status (Pass / Fail / N/A / Pending)
Inspector name / role / date
Photo / certificate / report reference
Issue / disposition / recheck evidence and date
WVI-02 | Procedure and personnel traceability What to observe: Applicable WPS/process revision, joint/material scope references and welder identity where the project requires the link. How to check: Compare the weld map and fabrication/site weld record to the controlled WPS register and required personnel records; do not assess qualification beyond supplied project evidence. Acceptance basis: The references attached to the weld are the ones required by the approved project welding plan; any missing or mismatched document remains unresolved before disposition. Reference to confirm: Approved WPS register, project welding specification, weld log and project-required personnel/continuity record; cite exact entry and revision. | WPS / revision / process
Material / thickness range source
Welder ID / project record
Mismatch / query ref
Result / status (Pass / Fail / N/A / Pending)
Inspector name / role / date
Photo / certificate / report reference
Issue / disposition / recheck evidence and date
WVI-03 | Examination stage and method What to observe: Specified visual examination procedure, stage (before/during/after coating or other stated stage), access, lighting/cleanliness conditions where prescribed. How to check: Confirm the method and stage against the approved ITP or inspection request; record the actual conditions relevant to visibility and any limitation. Acceptance basis: The examination follows the specified method and timing; any unavailable surface or method deviation is identified and referred rather than implied complete. Reference to confirm: Project ITP, approved welding inspection procedure, inspection request and coating sequence documents; cite row, revision and stage. | Inspection method / procedure
Required stage / trigger
Observed access condition
Deviation / instruction ref
Result / status (Pass / Fail / N/A / Pending)
Inspector name / role / date
Photo / certificate / report reference
Issue / disposition / recheck evidence and date
WVI-04 | Visible weld profile and surface condition What to observe: Actual visible profile, continuity, termination, surface discontinuities, spatter or arc strikes only where covered by project acceptance rules. How to check: Observe and describe the actual condition at its location; compare each observation with the project-defined visual criteria and record dimensions only where the method requires them. Acceptance basis: Each observation is assessed against the cited project criterion and is traceable to its location; blank criteria or unsupported assumptions remain pending. Reference to confirm: Project-adopted welding standard and project weld criteria, including construction category and relevant acceptance reference; cite exact adopted edition/clause from controlled documents. | Observation / location
Measured feature / unit if required
Acceptance source / clause
Status / photo ref
Result / status (Pass / Fail / N/A / Pending)
Inspector name / role / date
Photo / certificate / report reference
Issue / disposition / recheck evidence and date
WVI-05 | Surface preparation and visible defects before concealment What to observe: Accessible weld surface and adjacent material condition at the project inspection stage, including any preparation needed for examination. How to check: Verify the specified examination access and surface condition; identify coating, dirt or geometry that prevents the required observation. Acceptance basis: The required surface is accessible and examined under the project method, or limitation is recorded for a defined follow-up; obscured weld is not marked visually accepted. Reference to confirm: Approved inspection procedure, coating sequence, weld map and inspection hold/witness schedule where contractually assigned; cite area and stage. | Surface condition
Area not examined / reason
Required follow-up / role
Evidence photo / request ref
Result / status (Pass / Fail / N/A / Pending)
Inspector name / role / date
Photo / certificate / report reference
Issue / disposition / recheck evidence and date
WVI-06 | Indication disposition and repair mapping What to observe: Reported indication description/location, project decision, repair instruction, material removed/deposited reference and repair-weld ID where required. How to check: Raise or cross-reference the project NCR/repair instruction; preserve the original observation and link later work rather than overwrite it. Acceptance basis: Each reported condition has an assigned disposition and a traceable repair/engineering instruction; this record does not determine structural acceptability or repair design. Reference to confirm: Project nonconformance procedure, approved repair/WPS instruction and engineering disposition; cite NCR number, weld location and revisions. | Original indication / location
NCR / disposition ref
Repair WPS / instruction ref
Repair weld / evidence ref
Result / status (Pass / Fail / N/A / Pending)
Inspector name / role / date
Photo / certificate / report reference
Issue / disposition / recheck evidence and date
WVI-07 | Re-examination, linked NDT and closure What to observe: Actual visual reinspection event, specified NDT method/extent if any, original report reference, remaining issue and authorized closeout status. How to check: Record the visual result for the actual reinspection; separately link NDT request/report and retain the original report and evaluator decision. Acceptance basis: Reinspection and any project-required NDT are documented against the same weld identity and their own governing criteria; unresolved findings remain open for assigned disposition. Reference to confirm: Project ITP and NDT schedule, approved NDT procedure, original NDT report, NCR closeout and weld dossier index; cite report revision and weld coverage. | Reinspection date / method
Actual visual result / evidence
NDT report / extent / status
Closeout role / NCR ref
Result / status (Pass / Fail / N/A / Pending)
Inspector name / role / date
Photo / certificate / report reference
Issue / disposition / recheck evidence and date

## Project setup
Cavoren ITP | Structural Steel Weld Visual Inspection Record
Field | Project entry | Reason / instructions | Source / locator
Project name / contract
Client / principal
Contractor / trade
Jurisdiction / building class
Room / element / zone / lot
Inspection date / time
Checklist issue / revision
Project / package
Shop or site weld location
Drawing / weld map revision
Joint / weld ID
WPS ID / revision
Welder ID if project requires
Inspector / assigned role
NCR / repair reference
Required project input |  | Why it is needed
Current weld map and joint details |  | Defines unique weld IDs, joint locations, type and any drawing-specific detail needed for traceability.
Approved welding procedure and project welding specification |  | Supplies the applicable process/procedure and visual acceptance basis for the specific weld.
Project construction category and inspection plan |  | Identifies required inspection stages, responsible roles and any contractual notice or release point.
Specified NDT plan and reporting route |  | Separates visual inspection from any required ultrasonic, radiographic, magnetic-particle or penetrant examination.
Repair and reinspection procedure |  | Defines how a reported indication is dispositioned, repaired and linked to subsequent examination.
Included scope | Visual examination of accessible completed structural-steel welds at the project-defined inspection stage, including joint traceability, surface observations and disposition/reinspection links.
Excluded scope | Welding procedure approval, welder qualification assessment, design of welds, acceptance limits not supplied by the project, NDT execution or interpretation, and certification of welding quality.
Use notice | This is a blank visual inspection record, not an NDT report. Identify the specified visual examination method and project acceptance criteria before inspection; keep actual observations and results blank until the work is examined.
How to use
1 | Use one record for one identifiable weld or a project-defined weld lot with each included weld listed. Confirm shop/site location and current weld-map revision.
2 | Record joint identity, applicable drawing detail, WPS revision and personnel references required by the project before entering an observation.
3 | Inspect only at the stage and by the method specified by the project; record actual visible condition, access limitations and observation evidence.
4 | Enter the project clause or approved weld-acceptance document used. Do not copy a threshold from a different construction category or standard edition.
5 | If an indication or inaccessible area is found, describe it, map it to the weld and leave disposition pending until the assigned welding/engineering role directs action.
6 | Link repairs and reinspection to the original weld ID. Record NDT only as a separate report reference and do not use this form as a substitute for that report.
Source title | Role and limits | URL | Locator
Cavoren structural steel fabrication and erection baseline | Scope/topic context only; not independent technical authority or project acceptance criteria. | https://itp.cavoren.net/templates/structural-steel/ | Existing public baseline rows STE-02 to STE-16 for material certificates, weld documentation/inspection, fasteners, erection, traceability and closeout.
Queensland Department of Transport and Main Roads, MRTS78 Fabrication of Structural Steelwork (November 2020 listing) | Topic and process-interface guidance only. Do not transfer TMR project criteria, registered-supplier conditions, Hold Points, values, frequencies or role assignments to general building work. Check the actual adopted edition and amendments. | https://www.tmr.qld.gov.au/business-industry/Technical-standards-publications/Specifications/2-Bridges-Marine-and-Structures | Current Category 2 listing identifies MRTS78 for fabrication of structural steelwork; MRTS278 is separately listed for supply of structural fasteners. TMR May 2026 amendment register describes MRTS78 suite changes including traceability and removal of structural-bolt provisions into MRTS278. The TMR technical specification is scoped to Queensland transport/bridge structures.
Queensland Department of Transport and Main Roads, Amendment Register (May 2026) | Amendment summary only. The register does not replace the adopted technical specification and project annexures or supply universal building criteria. | https://www.tmr.qld.gov.au/RSS-Feeds/-/media/8A5A858423EA4B3CAEB558C6394B728C.ashx | MRTS78 Suite amendment entry: additional documentation for Hold Points 1 and 2, fabricator responsibility for material traceability, structural-bolt information moved to separate MRTS278, Hold Point order changes and welding-topic additions.
Standards Australia, Australian Standards supporting the steel sector | High-level scope reference only; project must identify adopted standards, amendments, construction category and contract criteria. | https://www.standards.org.au/news/australian-standards-r-supporting-the-steel-sector | Public summary of AS/NZS 5131:2016 scope: fabrication including bolting/welding, corrosion-protection preparation/processes and site erection/modification. The standard text is not reproduced or used for clause-level criteria.
Steelwork Compliance Australia, compliance scheme overview | Explains that scheme/certification status is project-specific. This blank site form does not certify fabricators, welding quality or product compliance. | https://www.scacompliance.com.au/ | Public overview describes the scheme as certification/audit for supply, fabrication and erection against project-specified AS/NZS 5131 and, where specified, AS/NZS ISO 3834; it identifies the engineer/project as choosing and specifying the construction category.

## Issues and handover
Structural Steel Weld Visual Inspection Record ¦ Issues and handover
Project | Location / area | Issue date | Open item reference | Person / role
Item ID / date | Affected location and issue | Immediate action / disposition | Recheck evidence / date | Responsible person / role
Weld examination and disposition handover | Record inspection handover status | Select one status only
[ ] Record complete; source evidence linked
[ ] Issue, recheck or project decision remains open
[ ] Assigned project role review / disposition required
Decision boundary | A completed visual record does not certify the weld or replace specified NDT, procedure qualification evidence, engineering disposition or contractual release. Keep each original examination and repair event traceable.
Handover role | Recorder / inspector name and role / date
Handover role | Assigned technical or project decision role / date
Handover role | Supplier / fabricator contact if clarification is needed
Handover role | Related register, report, NCR or instruction reference
Signature note | Signatures record the named person’s stated role and entry only. They do not by themselves approve design, certify compliance, release a contractual control point or authorize the next activity.

## Event log
Weld inspection and repair log
Use one line for each actual weld examination or repair/re-examination event. Keep the original weld ID constant across events and use the weld map and NCR/repair reference to preserve the sequence. Enter NDT only as a linked report reference.
Project / contract |  |  | Element / pour / lot |  |  | Date / shift
Inspection date / stage | Weld ID / drawing ref | Joint / location / side | WPS / revision | Actual visual observation | Project criterion / clause | Repair / NCR / recheck ref | NDT report ref if specified | Inspector / role / status